## Financial Status
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-19
Project Code: | 1014
Project Name: | Site Formation and Foundation Works For Campus Expansion at Ho Man Tin Slope for the Hong Kong Polytechnic University
Report Date: | 2025-12-31
Start Date: | 2020-10-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-04-10 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2026-06-30 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 324198.019 | 324198 | 0 | 324198 | 324198 | 324198 | 0 | 324198 | 323190 | 99.69% | 1008 | 253022 | 251902 | 77.94% | 71288
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 46383 | 0 | 46383 | 76910 | 76910 | 0 | 76910 | 751.66 | 1.621% | 45631.34 | 773 | 0 | 0% | 751.66
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 243871 | 243871 | 0 | 243871 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 0 | 18750 | 0 | 18750 | 21301 | 21301 | 0 | 21301 | 10104 | 53.89% | 8646 | 12900 | 12621 | 124.9% | -2517
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | -1500 | 0 | -1500 | 0 | 0 | 0 | 0 | 0 | 0% | -1500 | 0 | 13251.2 | 0% | -13251.2
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Income | 324198.019 | 387831 | 0 | 387831 | 666280 | 666280 | 0 | 666280 | 334045.66 | 86.13% | 53785.34 | 266695 | 277774.2 | 83.15% | 56271.46
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 21495.258 | 23880 | 0 | 23880 | 50051 | 50051 | 0 | 50051 | 49267.2025 | 206.3% | -25387.2025 | 49267.2025 | 49267.2025 | 100% | 0
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 12 | 12 | 307 | 319 | 212.2467 | 0% | -212.2467 | 212.2467 | 212.2467 | 100% | 0
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.3 | -Manpower (Labour) | 0 | 0 | 0 | 0 | 8408 | 8408 | -600 | 7808 | 7576.8983 | 0% | -7576.8983 | 7576.8983 | 7576.8983 | 100% | 0
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 10142.532 | 8555.973 | 0 | 8555.973 | 12550 | 12550 | 0 | 12550 | 11600.8987 | 135.6% | -3044.9257 | 11600.8987 | 11600.8987 | 100% | 1.819e-12
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 6595.1726 | 8495.8488 | 0 | 8495.8488 | 32111 | 32111 | 0 | 32111 | 26490.1044 | 311.8% | -17994.2556 | 26170.4876 | 25929.8382 | 97.88% | 560.2662
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 954 | 954 | 0 | 954 | 658.2 | 0% | -658.2 | 658.2 | 658.2 | 100% | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0 | 0 | 233 | 233 | 0 | 233 | 171.3658 | 0% | -171.3658 | 171.3658 | 165.6361 | 96.66% | 5.7297
2.1.8 | -DSC | 9375.6403 | 30667.7788 | 0 | 30667.7788 | 13357.95 | 13357.95 | 0 | 13357.95 | 12739.177 | 41.54% | 17928.6018 | 12675.103 | 12367.281 | 97.08% | 371.896
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 176.75 | 1435.9148 | 0 | 1435.9148 | 3000 | 3000 | 212 | 3212 | 3042.3884 | 211.9% | -1606.4736 | 2944.6717 | 2732.1937 | 89.8% | 310.1947
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 730 | 730 | 357 | 1087 | 901.274 | 0% | -901.274 | 900.062 | 900.062 | 99.87% | 1.212
2.2.2 | -Reinforcement | 0 | 10480.945 | 0 | 10480.945 | 2315 | 2315 | 0 | 2315 | 464.2969 | 4.43% | 10016.6481 | 464.2969 | 464.2969 | 100% | 0
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 1.18 | 0% | -1.18 | 1.18 | 1.18 | 100% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 2551.1513 | 0 | 2551.1513 | 198.437 | 198.437 | -0.437 | 198 | 198 | 7.761% | 2353.1513 | 198 | 198 | 100% | 0
2.2.5 | -Structural Steel Member | 0 | 885.9132 | 0 | 885.9132 | 885.913 | 885.913 | 0.087 | 886 | 575.072 | 64.91% | 310.8412 | 575.072 | 271.2608 | 47.17% | 303.8112
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 250 | 14.693 | 0% | -14.693 | 14.693 | 14.693 | 100% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 2666 | 2666 | 0 | 2666 | 1992.0811 | 0% | -1992.0811 | 1709.3771 | 1702.4371 | 85.46% | 289.644
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 244.7915 | 328.8185 | 0% | -328.8185
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 100 | 0.4 | 0% | -0.4 | 0.4 | 0.4 | 100% | 0
2.3.2 | -Plant, Equipments & Tools (external hire) | 5322.7593 | 4850.6631 | 0 | 4850.6631 | 14562.8 | 14562.8 | 0 | 14562.8 | 13106.3765 | 270.2% | -8255.7135 | 9698.2775 | 9234.1765 | 70.46% | 3872.2
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 150 | 125.7461 | 0% | -125.7461 | 125.7461 | 125.7461 | 100% | 0
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 7.8 | 0% | -7.8 | 7.8 | 7.8 | 100% | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 257652.1976 | 370395.2654 | 0 | 370395.2654 | 463274 | 463274 | 6859.951 | 470133.951 | 469306.1114 | 126.7% | -98910.846 | 334316.1888 | 322615.1807 | 68.74% | 146690.9307
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 30313 | 30313 | -486 | 29827 | 26957.5693 | 0% | -26957.5693 | 23939.2077 | 3865.1801 | 14.34% | 23092.3892
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | -15445.955 | -12288.015 | 0% | 12288.015
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -17908.8618 | 0% | 17908.8618
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -43819 | -43819 | -8250 | -52069 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 3414 | 3414 | 1600 | 5014 | 4128.348 | 0% | -4128.348 | 4128.398 | 4128.348 | 100% | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 310760.3098 | 462199.4534 | 0 | 462199.4534 | 595730.1 | 595730.1 | -0.399 | 595729.701 | 629537.4301 | 136.2% | -167337.9767 | 472154.6098 | 424171.0982 | 67.38% | 205366.3319
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 13437.7092 | -74368.4534 | 0 | -74368.4534 | 70549.9 | 70549.9 | 0.399 | 70550.299 | -295491.7701 | 397.3% | 221123.3167 | -205459.6098 | -146396.8982 | 49.54% | -149094.8719
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | -954 |  |  | -954 | -658.2 | 0% |  | -658.2 | -658.2 | 100% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | 0 |  |  | 0 | 0 | 0% |  | 0 | 0 | 0% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | -697 | 0 | -697 | 0 |  |  | 14381.3568 | 14381.3568 | -2063% | -15078.3568 | 14381.3568 | 14381.3568 | 100% | -3.055e-08
4.3 | Total Adjustment | 0 | -697 | 0 | -697 | -954 |  |  | 13427.3568 | 13723.1568 | -1969% | -14420.1568 | 13723.1568 | 13723.1568 | 100% | -3.055e-08
5 | Gross Profit (Item 3.0-4.3) | 13437.7092 | -73671.4534 | 0 | -73671.4534 | 71503.9 |  |  | 57122.9422 | -309214.9269 | 419.7% | 235543.4735 | -219182.7666 | -160120.055 | 51.78% | -149094.8719
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 19451.8811 | 23269.86 | 0 | 23269.86 | 39976.8 |  |  | 20173.83 | 10021.3698 | 43.07% | 13248.4902 | 8128.11 | 8548.536 | 85.3% | 1472.8338
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 3241.9802 | 3878.31 | 0 | 3878.31 | 6662.8 |  |  | 6662.8 | 3340.4566 | 86.13% | 537.8534 | 2666.95 | 2777.742 | 83.15% | 562.7146
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -9256.1521 | -100819.6234 | 0 | -100819.6234 | 24864.3 |  |  | 30286.3122 | -322576.7533 | 320% | 221757.1299 | -229977.8266 | -171446.333 | 53.15% | -151130.4203
(=Item5.0 - 6.0 + 6.2)

## Projection
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-19
Project Code: | 1014
Project Name: | Site Formation and Foundation Works For Campus Expansion at Ho Man Tin Slope for the Hong Kong Polytechnic University
Report Date: | 2025-12-31
Start Date: | 2020-10-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-04-10 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-06-30 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 324198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 324198
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 60200 | 0 | 0 | 0 | 0 | 0 | 0 | 16710 | 0 | 0 |  |  |  | 76910
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 254400 | 0 | 0 | 0 | 0 | 0 | 0 | -10529 | 0 | 0 |  |  |  | 243871
1.8 | Price Fluctuation / CPF | 21301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 21301
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 660099 | 0 | 0 | 0 | 0 | 0 | 0 | 6181 | 0 | 0 | 0 | 0 | 0 | 666280
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 47251 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50051
2.1.13 | -Manpower (HO-Consultant) | 6 | 0 | 6 | 20 | 0 | 20 | 17 | 0 | 50 | 200 |  |  |  | 319
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 9408 | -1000 | 0 | 0 | 0 | 0 | 0 | -600 | 0 | 0 |  |  |  | 7808
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 12550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12550
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 33111 | -1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 32111
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 954
2.1.7 | -Adm. Cost Messing | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 233
2.1.8 | -DSC | 12357.95 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13357.95
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 3000 | 0 | 0 | 0 | 0 | 0 | 12 | 200 | 0 | 0 |  |  |  | 3212
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 700 | 30 | 0 | 50 | 0 | 50 | 57 | 200 | 0 | 0 |  |  |  | 1087
2.2.2 | -Reinforcement | 2345 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2315
2.2.3 | -Tile, Granite & Marble | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 198
2.2.5 | -Structural Steel Member | 886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 886
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 250
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 2666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2666
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100
2.3.2 | -Plant, Equipments & Tools (external hire) | 14562.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14562.8
2.3.3 | -Diesel & Lubricant | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 150
2.3.4 | -Repairing | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 466073.951 | 0 | -2800 | -70 | 0 | -70 | 0 | 0 | 0 | 7000 |  |  |  | 470133.951
2.4.2 | -Variation | 30313 | 0 | 0 | 0 | 0 | 0 | 0 | -486 | 0 | 0 |  |  |  | 29827
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43819 | -50 | -8200 |  |  |  | -52069
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 2420 | 1000 | -6 | 0 | 0 | 0 | 0 | 600 | 0 | 1000 |  |  |  | 5014
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 639548.701 | 0 | 0 | 0 | 0 | 0 | 86 | -43905 | 0 | 0 | 0 | 0 | 0 | 595729.701
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 20550.299 | 0 | 0 | 0 | 0 | 0 | -86 | 50086 | 0 | 0 |  |  |  | 70550.299
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -954
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 8770.4522 | 527.8008 | 586.0875 | 599.0572 | 606.9812 | 617.2121 | 632.9453 | 653.0852 | 676.3398 | 711.3956 |  |  |  | 14381.3568
4.3 | Total Adjustment | 7816.4522 | 527.8008 | 586.0875 | 599.0572 | 606.9812 | 617.2121 | 632.9453 | 653.0852 | 676.3398 | 711.3956 | 0 | 0 | 0 | 13427.3568
5 | Gross Profit (Item 3.0-4.3) | 12733.8468 | -527.8008 | -586.0875 | -599.0572 | -606.9812 | -617.2121 | -718.9453 | 49432.9148 | -676.3398 | -711.3956 |  |  |  | 57122.9422
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 19802.97 | 0 | 0 | 0 | 0 | 0 | 0 | 370.86 | 0 | 0 |  |  |  | 20173.83
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 6600.99 | 0 | 0 | 0 | 0 | 0 | 0 | 61.81 | 0 | 0 |  |  |  | 6662.8
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -13670.1132 | -527.8008 | -586.0875 | -599.0572 | -606.9812 | -617.2121 | -718.9453 | 49000.2448 | -676.3398 | -711.3956 |  |  |  | 30286.3122
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-19
Project Code: | 1014
Project Name: | Site Formation and Foundation Works For Campus Expansion at Ho Man Tin Slope for the Hong Kong Polytechnic University
Report Date: | 2025-12-31
Start Date: | 2020-10-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-04-10 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-06-30 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 323190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 323190
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 751.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 751.66
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 10104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10104
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 334045.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334045.66
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 43025.9849 | 418.11 | 594.82 | 656.12 | 798.22 | 671.06 | 840.03 | 608.8081 | 661.0447 | 993.0048 |  |  |  | 49267.2025
2.1.13 | -Manpower (HO-Consultant) | 6 | 0 | 4.69 | 4.7635 | 0 | 23.62 | 29.6138 | 0.15927 | 26.8401 | 116.56 |  |  |  | 212.2467
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 7590.2812 | 15.74 | 10 | 9.19 | 0 | 11.3 | 0 | -62.6129 | 0 | 3 |  |  |  | 7576.8983
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 10849.8389 | 0 | 0 | 0 | -615.735 | 0 | 1008.657 | 340.2548 | 2.256 | 15.627 |  |  |  | 11600.8987
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 22324.2736 | 279.1535 | 812.1285 | 713.047 | 246.7669 | 544.2364 | 522.6143 | 206.7045 | 313.3558 | 527.824 |  |  |  | 26490.1044
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 658.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 658.2
2.1.7 | -Adm. Cost Messing | 159.5872 | 2.1786 | 0 | 1.2489 | 0 | 2.0813 | 5.485 | 0.09412 | 0 | 0.6907 |  |  |  | 171.3658
2.1.8 | -DSC | 12255.277 | 53 | 53 | 53 | 53 | 53 | 53 | 76.3 | 83.6 | 6 |  |  |  | 12739.177
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 2864.6404 | 24.009 | 9.912 | 26.88 | 13.69 | 37.888 | 14.872 | 24.285 | 2.4 | 23.812 |  |  |  | 3042.3884
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 655.5235 | 46.3745 | 5.832 | 1.212 | 63.556 | 33.288 | 0 | 71.618 | 23.87 | 0 |  |  |  | 901.274
2.2.2 | -Reinforcement | 464.2969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 464.2969
2.2.3 | -Tile, Granite & Marble | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1.18
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 198
2.2.5 | -Structural Steel Member | 575.072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 575.072
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 14.693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14.693
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 1984.8269 | 0 | 7.2542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1992.0811
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.4
2.3.2 | -Plant, Equipments & Tools (external hire) | 12313.5184 | 0 | 217.14 | 0 | 421 | 58.4681 | 0 | 0 | 91 | 5.25 |  |  |  | 13106.3765
2.3.3 | -Diesel & Lubricant | 110.0163 | 0 | 0 | 0 | 7.3834 | 0 | 0 | 8.3463 | 0 | 0 |  |  |  | 125.7461
2.3.4 | -Repairing | 7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7.8
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 436730.3864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32575.725 |  |  |  | 469306.1114
2.4.2 | -Variation | 26957.5693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 26957.5693
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 2413.2904 | 386.04 | 197 | 153.3028 | 160.75 | 156.96 | 156.9559 | 185.9613 | 149.3711 | 168.7166 |  |  |  | 4128.348
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 582160.6563 | 1224.6056 | 1911.7766 | 1618.7641 | 1148.6313 | 1591.9018 | 2631.2281 | 1459.9185 | 1353.7377 | 34436.2101 | 0 | 0 | 0 | 629537.4301
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -248114.9963 | -1224.6056 | -1911.7766 | -1618.7641 | -1148.6313 | -1591.9018 | -2631.2281 | -1459.9185 | -1353.7377 | -34436.2101 |  |  |  | -295491.7701
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -658.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -658.2
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 8770.4522 | 527.8008 | 586.0875 | 599.0572 | 606.9812 | 617.2121 | 632.9453 | 653.0852 | 676.3398 | 711.3956 |  |  |  | 14381.3568
4.3 | Total Adjustment | 8112.2522 | 527.8008 | 586.0875 | 599.0572 | 606.9812 | 617.2121 | 632.9453 | 653.0852 | 676.3398 | 711.3956 | 0 | 0 | 0 | 13723.1568
5 | Gross Profit (Item 3.0-4.3) | -256227.2485 | -1752.4064 | -2497.8641 | -2217.8213 | -1755.6125 | -2209.1139 | -3264.1734 | -2113.0036 | -2030.0775 | -35147.6057 |  |  |  | -309214.9269
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 10021.3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10021.3698
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 3340.4566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3340.4566
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -269589.0749 | -1752.4064 | -2497.8641 | -2217.8213 | -1755.6125 | -2209.1139 | -3264.1734 | -2113.0036 | -2030.0775 | -35147.6057 |  |  |  | -322576.7533
(=Item5.0 - 6.0 + 6.2)

## Accrual
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-19
Project Code: | 1014
Project Name: | Site Formation and Foundation Works For Campus Expansion at Ho Man Tin Slope for the Hong Kong Polytechnic University
Report Date: | 2025-12-31
Start Date: | 2020-10-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-04-10 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-06-30 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 246280 | 0 | 1379 | 1498 | 1336 | 1170 | 1240 | 119 | 0 | 0 |  |  |  | 253022
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 773
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 12465 | 0 | -106 | 164 | 168 | 47 | 147 | 15 | 0 | 0 |  |  |  | 12900
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 259518 | 0 | 1273 | 1662 | 1504 | 1217 | 1387 | 134 | 0 | 0 | 0 | 0 | 0 | 266695
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 43025.9849 | 418.11 | 594.82 | 656.12 | 798.22 | 671.06 | 840.03 | 608.8081 | 661.0447 | 993.0048 |  |  |  | 49267.2025
2.1.13 | -Manpower (HO-Consultant) | 6 | 0 | 4.69 | 4.7635 | 0 | 23.62 | 29.6138 | 0.15927 | 26.8401 | 116.56 |  |  |  | 212.2467
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 7600.2812 | 5.74 | 10 | 9.19 | 0 | 11.3 | 0 | -62.6129 | 0 | 3 |  |  |  | 7576.8983
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 10849.8389 | 0 | 0 | 0 | -615.735 | 0 | 1008.657 | 340.2548 | 2.256 | 15.627 |  |  |  | 11600.8987
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 22020.8427 | 324.4975 | 791.1685 | 659.657 | 260.4769 | 462.1864 | 522.0643 | 267.1745 | 334.5958 | 527.824 |  |  |  | 26170.4876
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 658.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 658.2
2.1.7 | -Adm. Cost Messing | 159.5872 | 2.1786 | 0 | 1.2489 | 0 | 2.0813 | 5.485 | 0.09412 | 0 | 0.6907 |  |  |  | 171.3658
2.1.8 | -DSC | 11878.9688 | 48.679 | 68.9222 | 53 | 123.606 | 53 | 53 | 306.327 | 83.6 | 6 |  |  |  | 12675.103
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 2733.6993 | 76.783 | 25.4634 | 30.52 | 9.85 | 24.818 | 2.443 | 38.495 | 2.4 | 0.2 |  |  |  | 2944.6717
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 655.5235 | 52.2065 | 63.556 | 0 | 33.288 | 0 | 0 | 95.488 | 0 | 0 |  |  |  | 900.062
2.2.2 | -Reinforcement | 464.2969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 464.2969
2.2.3 | -Tile, Granite & Marble | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1.18
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 198
2.2.5 | -Structural Steel Member | 575.072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 575.072
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 14.693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14.693
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 1696.5929 | 12.3041 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1709.3771
2.2.14 | -Deposit | 214.7915 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 |  |  |  | 244.7915
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.4
2.3.2 | -Plant, Equipments & Tools (external hire) | 8514.3924 | 394.216 | 230.74 | 130.4 | 130.961 | 64.1681 | 0 | 178.4 | 55 | 0 |  |  |  | 9698.2775
2.3.3 | -Diesel & Lubricant | 110.0163 | 0 | 0 | 7.3834 | 0 | 0 | 0 | 8.3463 | 0 | 0 |  |  |  | 125.7461
2.3.4 | -Repairing | 7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7.8
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 320713.6062 | 1958.84 | 2081.6241 | 181.25 | 2936.5726 | 0 | 0 | 3681.928 | 2762.368 | 0 |  |  |  | 334316.1888
2.4.2 | -Variation | 3532.2602 | 8332.3127 | 433.4345 | 5082.2412 | 4119.6312 | 0 | 0 | 2397.552 | 41.7759 | 0 |  |  |  | 23939.2077
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | -16431.4605 | -316.9353 | 439.103 | -589.01 | 332.485 | 716.3147 | 0 | 403.5481 | 0 | 0 |  |  |  | -15445.955
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 2631.2904 | 167.66 | 197.4 | 153.3028 | 160.75 | 156.96 | 156.9559 | 185.9913 | 149.3711 | 168.7166 |  |  |  | 4128.398
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 421831.8578 | 11476.5922 | 4941.4016 | 6380.0667 | 8290.1057 | 2185.5084 | 2618.2491 | 8479.9536 | 4119.2517 | 1831.6231 | 0 | 0 | 0 | 472154.6098
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -162313.8577 | -11476.5922 | -3668.4016 | -4718.0667 | -6786.1057 | -968.5084 | -1231.2491 | -8345.9536 | -4119.2517 | -1831.6231 |  |  |  | -205459.6098
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -658.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -658.2
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 8770.4522 | 527.8008 | 586.0875 | 599.0572 | 606.9812 | 617.2121 | 632.9453 | 653.0852 | 676.3398 | 711.3956 |  |  |  | 14381.3568
4.3 | Total Adjustment | 8112.2522 | 527.8008 | 586.0875 | 599.0572 | 606.9812 | 617.2121 | 632.9453 | 653.0852 | 676.3398 | 711.3956 | 0 | 0 | 0 | 13723.1568
5 | Gross Profit (Item 3.0-4.3) | -170426.1099 | -12004.393 | -4254.4891 | -5317.1239 | -7393.0869 | -1585.7205 | -1864.1944 | -8999.0387 | -4795.5915 | -2543.0187 |  |  |  | -219182.7666
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 7785.54 | 0 | 38.19 | 49.86 | 90.24 | 73.02 | 83.22 | 8.04 | 0 | 0 |  |  |  | 8128.11
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 2595.18 | 0 | 12.73 | 16.62 | 15.04 | 12.17 | 13.87 | 1.34 | 0 | 0 |  |  |  | 2666.95
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -180806.8299 | -12004.393 | -4305.4091 | -5383.6039 | -7498.3669 | -1670.9105 | -1961.2844 | -9008.4187 | -4795.5915 | -2543.0187 |  |  |  | -229977.8266
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-19
Project Code: | 1014
Project Name: | Site Formation and Foundation Works For Campus Expansion at Ho Man Tin Slope for the Hong Kong Polytechnic University
Report Date: | 2025-12-31
Start Date: | 2020-10-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-04-10 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-06-30 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 244783 | 0 | 0 | 0 | 1379 | 1498 | 1504 | 1217 | 1387 | 134 |  |  |  | 251902
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 12563 | 0 | 0 | 0 | -106 | 164 | 0 | 0 | 0 | 0 |  |  |  | 12621
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 13251.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13251.2
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 270597.2 | 0 | 0 | 0 | 1273 | 1662 | 1504 | 1217 | 1387 | 134 | 0 | 0 | 0 | 277774.2
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 43025.9849 | 418.11 | 594.82 | 656.12 | 798.22 | 671.06 | 840.03 | 608.8081 | 661.0447 | 993.0048 |  |  |  | 49267.2025
2.1.13 | -Manpower (HO-Consultant) | 6 | 0 | 4.69 | 4.7635 | 0 | 23.62 | 29.6138 | 0.15927 | 26.8401 | 116.56 |  |  |  | 212.2467
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 7600.2812 | 5.74 | 10 | 9.19 | 0 | 11.3 | 0 | -62.6129 | 0 | 3 |  |  |  | 7576.8983
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 10284.3389 | 565.5 | 0 | 0 | -615.735 | 0 | 258.657 | 590.2548 | 252.256 | 265.627 |  |  |  | 11600.8987
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 21810.6239 | 305.1761 | 828.549 | 503.5672 | 249.6657 | 524.9667 | 607.9244 | 192.8151 | 293.1223 | 613.4279 |  |  |  | 25929.8382
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 658.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 658.2
2.1.7 | -Adm. Cost Messing | 149.5785 | 5.0776 | 1.38 | 0 | 0 | 1.2489 | 2.0813 | 1.226 | 0 | 5.0438 |  |  |  | 165.6361
2.1.8 | -DSC | 11756.6485 | 106 | 53 | 40.2043 | 53 | 68.9222 | 106 | 23.3 | 101.206 | 59 |  |  |  | 12367.281
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 2528.7693 | 4.069 | 93.828 | 28.734 | 33.0714 | 0.744 | 1.788 | 0.2 | 32.5 | 8.49 |  |  |  | 2732.1937
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 621.9955 | 33.528 | 46.3745 | 5.832 | 63.556 | 0 | 9.312 | 54.351 | 65.113 | 0 |  |  |  | 900.062
2.2.2 | -Reinforcement | 464.2969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 464.2969
2.2.3 | -Tile, Granite & Marble | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1.18
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 198
2.2.5 | -Structural Steel Member | 271.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 271.2608
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 14.693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14.693
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 1653.3361 | 2.97 | 30.6438 | 7.753 | 7.7341 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1702.4371
2.2.14 | -Deposit | 298.8185 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 |  |  |  | 328.8185
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.4
2.3.2 | -Plant, Equipments & Tools (external hire) | 8140.1934 | 183.7 | 106.655 | 110 | 55 | 2.25 | 246.188 | 110 | 77.6681 | 202.522 |  |  |  | 9234.1765
2.3.3 | -Diesel & Lubricant | 94.9444 | 0 | 0 | 9.1379 | 5.934 | 0 | 7.3834 | 0 | 0 | 8.3463 |  |  |  | 125.7461
2.3.4 | -Repairing | 7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7.8
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 292354.7817 | 978.8003 | 11909.4553 | 835.0444 | 1505.6978 | 1248.3218 | 1709.2226 | 2990.1912 | 3365.8377 | 5717.8277 |  |  |  | 322615.1807
2.4.2 | -Variation | 741.7104 | 0.88 | 432.3432 | 225.9202 | 253.7803 | 385.9318 | 322.0876 | 755.6751 | 782.652 | -35.8004 |  |  |  | 3865.1801
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | -13306.1917 | 210.0717 | -729.7107 | 32.3811 | 0 | 439.103 | 286.701 | 51.5773 | 618.2014 | 109.8519 |  |  |  | -12288.015
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | -16565.4607 | -97.88 | -118.0287 | -95.3096 | -84.0871 | -140.3182 | -26.4685 | -199.4841 | -207.8703 | -373.9545 |  |  |  | -17908.8618
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 2631.6704 | 167.66 | 197 | 153.3028 | 160.75 | 156.96 | 156.9559 | 185.9613 | 149.3711 | 168.7166 |  |  |  | 4128.348
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 375443.854 | 2889.4026 | 13460.9994 | 2526.6408 | 2486.5872 | 3394.1102 | 4557.4766 | 5332.4221 | 6217.942 | 7861.6632 | 0 | 0 | 0 | 424171.0982
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -104846.654 | -2889.4026 | -13460.9994 | -2526.6408 | -1213.5872 | -1732.1102 | -3053.4766 | -4115.4221 | -4830.942 | -7727.6632 |  |  |  | -146396.8982
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -658.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -658.2
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 8770.4522 | 527.8008 | 586.0875 | 599.0572 | 606.9812 | 617.2121 | 632.9453 | 653.0852 | 676.3398 | 711.3956 |  |  |  | 14381.3568
4.3 | Total Adjustment | 8112.2522 | 527.8008 | 586.0875 | 599.0572 | 606.9812 | 617.2121 | 632.9453 | 653.0852 | 676.3398 | 711.3956 | 0 | 0 | 0 | 13723.1568
5 | Gross Profit (Item 3.0-4.3) | -112958.9061 | -3417.2035 | -14047.0869 | -3125.698 | -1820.5683 | -2349.3223 | -3686.4219 | -4768.5073 | -5507.2818 | -8439.0588 |  |  |  | -160120.055
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 8117.916 | 0 | 0 | 0 | 76.38 | 99.72 | 90.24 | 73.02 | 83.22 | 8.04 |  |  |  | 8548.536
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 2705.972 | 0 | 0 | 0 | 12.73 | 16.62 | 15.04 | 12.17 | 13.87 | 1.34 |  |  |  | 2777.742
6.2 | Acc. Profit/(Loss) ~ B/F |  | -123782.7941 | -127199.9976 | -141247.0845 | -144372.7825 | -146282.4609 | -148748.1232 | -152539.8251 | -157393.5224 | -162997.8942
7 | Acc. Net Profit/(Loss) | -123782.7941 | -127199.9976 | -141247.0845 | -144372.7825 | -146282.4609 | -148748.1232 | -152539.8251 | -157393.5224 | -162997.8942 | -171446.333 |  |  |  | -171446.333
(=Item5.0 - 6.0 + 6.2)