## Financial Status
KL-CW JV
Print Date: 2026-01-19
Project Code: | 1027
Project Name: | DC/2020/02 Construction of San Shek Wan Sewage Treatment Works, Associated Submarine Outfall and Pui O Sewerage Works
Report Date: | 2025-12-31
Start Date: | 2021-04-02 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-04-01 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2026-06-12 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 481663 | 481663.3 | 0 | 481663.3 | 481663.3 | 481663 | 0.3 | 481663.3 | 481663.3 | 100% | 0 | 682072.551 | 662371.476 | 137.5% | -180708.176
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 17380.55 | 0 | 17380.55 | 201681 | 201681 | 11724.98 | 213405.98 | 82345 | 473.8% | -64964.45 | 0 | 0 | 0% | 82345
1.2.2 | -Fee of C.E. | 18327 | 177310 | 0 | 177310 | 38319 | 38319 | 2228.84 | 40547.84 | 15646 | 8.824% | 161664 | 0 | 0 | 0% | 15646
1.3 | Provisional Sum | 8727 | -8653.85 | 0 | -8653.85 | 8727 | 8727 | -99.6 | 8627.4 | 4643.86 | -53.66% | -13297.71 | 4644.42 | 0 | 0% | 4643.86
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 40025 | 57422.541 | 0 | 57422.541 | 136409 | 136409 | -180.46 | 136228.54 | 101235 | 176.3% | -43812.459 | 0 | 0 | 0% | 101235
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 76500 | 76500 | 0 | 0% | 0 | 0 | -0.34775 | 0% | 0.34775
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.2 | -Pain Gain Sharing | 25228 | 35819.792 | 0 | 35819.792 | 42904 | 42904 | 488.19 | 43392.19 | 0 | 0% | 35819.792 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5891.8979 | 0% | 5891.8979
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Income | 573970 | 760942.333 | 0 | 760942.333 | 909703.3 | 909703 | 90662.25 | 1000365.25 | 685533.16 | 90.09% | 75409.173 | 686716.971 | 656479.2304 | 95.76% | 29053.9296
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 34111.047 | 51975.22 | 0 | 51975.22 | 103956 | 103956 | -10342.28 | 93613.72 | 90858.7798 | 174.8% | -38883.5598 | 90858.6398 | 90858.5798 | 100% | 0.2
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 174.5 | 175 | 99.5 | 274.5 | 248.4076 | 0% | -248.4076 | 248.4076 | 248.4076 | 100% | 0
2.1.2 | -Manpower (RE) | 9796.453 | 8901.484 | 0 | 8901.484 | 7249 | 7249 | 0.48 | 7249.48 | 5156.1211 | 57.92% | 3745.3628 | 5156.269 | 5156.269 | 100% | -0.14785
2.1.3 | -Manpower (Labour) | 7938.752 | 9543.927 | 0 | 9543.927 | 10358 | 10358 | 449.93 | 10807.93 | 10401.3823 | 109% | -857.4553 | 10401.1223 | 10401.1223 | 100% | 0.26
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 15663.987 | 14061.491 | 0 | 14061.491 | 17292 | 17292 | -999.51 | 16292.49 | 15435.763 | 109.8% | -1374.272 | 15435.763 | 15312.663 | 99.2% | 123.1
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 42223.811 | 50052.4021 | 0 | 50052.4021 | 63491 | 63491 | 6500.23 | 69991.23 | 68882.3451 | 137.6% | -18829.9431 | 61552.8365 | 55123.5351 | 80.03% | 13758.81
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0 | 0 | 397 | 397 | 187 | 584 | 446.7019 | 0% | -446.7019 | 446.7019 | 446.7019 | 100% | -1.7053e-13
2.1.8 | -DSC | 16625.413 | 22599.7506 | 0 | 22599.7506 | 34261 | 34261 | -0.26 | 34260.74 | 30887.268 | 136.7% | -8287.5174 | 23521.8237 | 23518.0242 | 76.14% | 7369.2438
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 1870.41 | 2320.404 | 0 | 2320.404 | 13993 | 13993 | -0.26 | 13992.74 | 13447.6484 | 579.5% | -11127.2444 | 5651.6193 | 4526.9777 | 33.66% | 8920.6707
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 10176.066 | 17811.312 | 0 | 17811.312 | 26529 | 26529 | 10500.18 | 37029.18 | 34790.226 | 195.3% | -16978.914 | 31288.08 | 25227.911 | 72.51% | 9562.315
2.2.2 | -Reinforcement | 8044.979 | 9352.2254 | 0 | 9352.2254 | 21404 | 21404 | 4500.07 | 25904.07 | 25390.0065 | 271.5% | -16037.7811 | 18102.0621 | 17946.4849 | 70.68% | 7443.5216
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 1712.9527 | 0 | 1712.9527 | 0 | 0 | 0 | 0 | 0 | 0% | 1712.9527 | 0 | 0 | 0% | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 1713 | 1713 | -1713 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 5391.151 | 7928.7439 | 0% | -7928.7439
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 2201.408 | 4684.09 | 0 | 4684.09 | 3845 | 3845 | 0.14 | 3845.14 | 1782.7192 | 38.06% | 2901.3708 | 1782.7192 | 1782.7192 | 100% | 0
2.3.2 | -Plant, Equipments & Tools (external hire) | 328.865 | 328.865 | 5534.7763 | 5863.6413 | 8639 | 8639 | 0.48 | 8639.48 | 8310.5495 | 141.7% | -2446.9082 | 6550.6 | 5593.4555 | 67.31% | 2717.094
2.3.3 | -Diesel & Lubricant | 0 | 0 | 180 | 180 | 2464 | 2464 | 0.18 | 2464.18 | 1787.6016 | 993.1% | -1607.6016 | 1787.6016 | 1648.8511 | 92.24% | 138.7505
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 7.3092 | 0% | -7.3092 | 7.3092 | 7.3092 | 100% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 394493.638 | 537102.7558 | -5714.7763 | 531387.9795 | 632446 | 632446 | 12553.82 | 644999.82 | 642841.3221 | 121% | -111453.3426 | 332169.118 | 312796.3945 | 48.66% | 330044.9276
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 1211 | 1211 | 77342.5 | 78553.5 | 22464.1644 | 0% | -22464.1644 | 17978.2898 | 16941.805 | 75.42% | 5522.3594
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 25050.2604 | 24844.6947 | 0% | -24844.6947
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1077 | 0% | -1077
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -19031.4216 | 0% | 19031.4216
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -122800 | -122800 | 48499.99 | -74300.01 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | -25866.4442 | -25597.6305 | 0% | 25597.6305
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 543474.829 | 730446.8795 | 0 | 730446.8795 | 826630.5 | 826631 | 147579.19 | 974210.19 | 973138.3158 | 133.2% | -242691.4362 | 627513.9302 | 576758.5973 | 59.27% | 396379.7184
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 30495.171 | 30495.4535 | 0 | 30495.4535 | 83072.8 | 83072 | -56916.94 | 26155.06 | -287605.1558 | -943.1% | 318100.6092 | 59203.0408 | 79720.633 | -27.72% | -367325.7888
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | 0 |  |  | 0 | 0 | 0% |  | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | -8 |  |  | -8 | -7.3092 | 0% |  | -7.3092 | -7.3092 | 100% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | 0 |  |  | -4966.3042 | -4966.3042 | 0% | 4966.3042 | -4966.3042 | -4966.3042 | 100% | -2.5797e-08
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | -8 |  |  | -4974.3042 | -4973.6134 | 0% | 4973.6134 | -4973.6134 | -4973.6134 | 100% | -2.5797e-08
5 | Gross Profit (Item 3.0-4.3) | 30495.171 | 30495.4535 | 0 | 30495.4535 | 83080.8 |  |  | 31129.3642 | -282631.5424 | -926.8% | 313126.9959 | 64176.6542 | 84694.2464 | -29.97% | -367325.7888
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 33914.58 | 46175.771 | 0 | 46175.771 | 54058.578 |  |  | 29872.1355 | 22044.639 | 47.74% | 24131.132 | 24418.2465 | 23254.9426 | 105.5% | -1210.3036
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 5652.43 | 7695.9618 | 0 | 7695.9618 | 9009.763 |  |  | 9917.3785 | 6808.893 | 88.47% | 887.0688 | 6820.7255 | 6564.7923 | 96.41% | 244.1007
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -9071.839 | -23376.2794 | 0 | -23376.2794 | 20012.459 |  |  | -8660.1498 | -311485.0744 | 1332% | 288108.795 | 32937.6822 | 54874.5115 | -17.62% | -366359.5859
(=Item5.0 - 6.0 + 6.2)

## Projection
KL-CW JV
Print Date: 2026-01-19
Project Code: | 1027
Project Name: | DC/2020/02 Construction of San Shek Wan Sewage Treatment Works, Associated Submarine Outfall and Pui O Sewerage Works
Report Date: | 2025-12-31
Start Date: | 2021-04-02 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-04-01 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-06-12 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 481663.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 481663.3
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 140953.48 | 37964.5 | 31127 | 0 | 0 | 0 | 0 | 3361 | 0 | 0 |  |  |  | 213405.98
1.2.2 | -Fee of C.E. | 27053.84 | 6940 | 5915 | 0 | 0 | 0 | 0 | 639 | 0 | 0 |  |  |  | 40547.84
1.3 | Provisional Sum | 8727.4 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8627.4
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 140260.54 | -3148 | -884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 136228.54
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 76500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 76500
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 39342.19 | 2244 | 1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 43392.19
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 914500.75 | 44000.5 | 37864 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1000365.25
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 83073.72 | 6100 | 4440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 93613.72
2.1.13 | -Manpower (HO-Consultant) | 40 | 134.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 |  |  |  | 274.5
2.1.2 | -Manpower (RE) | 7249.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7249.48
2.1.3 | -Manpower (Labour) | 7642.93 | 2000 | 1165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10807.93
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 14292.49 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16292.49
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 57491.23 | 6000 | 0 | 0 | 1500 | 1000 | 0 | 2000 | 1000 | 1000 |  |  |  | 69991.23
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 397 | 0 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 584
2.1.8 | -DSC | 33260.74 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 34260.74
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 12092.74 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13992.74
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 26529.18 | 0 | 0 | 0 | 0 | 0 | 4500 | 2000 | 1000 | 3000 |  |  |  | 37029.18
2.2.2 | -Reinforcement | 21404.07 | 0 | 2000 | 0 | 1500 | 1000 | 0 | 0 | 0 | 0 |  |  |  | 25904.07
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 1712.95 | 0 | -1712.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 3845.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3845.14
2.3.2 | -Plant, Equipments & Tools (external hire) | 8119.48 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8639.48
2.3.3 | -Diesel & Lubricant | 2464.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2464.18
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 624446.22 | -0.4 | 23554 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 |  |  |  | 644999.82
2.4.2 | -Variation | 57011 | 4199.5 | -21225 | 0 | -3000 | -2000 | -4500 | 51168 | -2000 | -1100 |  |  |  | 78553.5
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | -100947.01 | -21853 | 105000 | 0 | 0 | 0 | 0 | -56500 | 0 | 0 |  |  |  | -74300.01
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 860133.54 | 0.6 | 115408.05 | 0 | 0 | 0 | 0 | -1332 | 0 | 0 | 0 | 0 | 0 | 974210.19
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 54367.21 | 43999.9 | -77544.05 | 0 | 0 | 0 | 0 | 5332 | 0 | 0 |  |  |  | 26155.06
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -3342.3823 | -207.8973 | -186.4134 | -182.3963 | -165.0283 | -160.671 | -142.7533 | -143.1521 | -207.9151 | -227.6951 |  |  |  | -4966.3042
4.3 | Total Adjustment | -3350.3823 | -207.8973 | -186.4134 | -182.3963 | -165.0283 | -160.671 | -142.7533 | -143.1521 | -207.9151 | -227.6951 | 0 | 0 | 0 | -4974.3042
5 | Gross Profit (Item 3.0-4.3) | 57717.5923 | 44207.7973 | -77357.6366 | 182.3963 | 165.0283 | 160.671 | 142.7533 | 5475.1521 | 207.9151 | 227.6951 |  |  |  | 31129.3642
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 27173.2005 | 1320.015 | 1138.92 | 0 | 0 | 0 | 0 | 240 | 0 | 0 |  |  |  | 29872.1355
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 9057.7335 | 440.005 | 379.64 | 0 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  | 9917.3785
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 21486.6583 | 42447.7773 | -78876.1966 | 182.3963 | 165.0283 | 160.671 | 142.7533 | 5195.1521 | 207.9151 | 227.6951 |  |  |  | -8660.1498
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
KL-CW JV
Print Date: 2026-01-19
Project Code: | 1027
Project Name: | DC/2020/02 Construction of San Shek Wan Sewage Treatment Works, Associated Submarine Outfall and Pui O Sewerage Works
Report Date: | 2025-12-31
Start Date: | 2021-04-02 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-04-01 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-06-12 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 481663.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 481663.3
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 46807 | 7241 | 0 | 0 | 9360 | 4638 | 7658 | 3029 | 3612 | 0 |  |  |  | 82345
1.2.2 | -Fee of C.E. | 8884 | 1375 | 0 | 0 | 1840 | 830 | 1455 | 576 | 686 | 0 |  |  |  | 15646
1.3 | Provisional Sum | 4071.86 | 35 | 292 | 35 | 35 | 35 | 0 | 35 | 70 | 35 |  |  |  | 4643.86
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 72842 | 2626 | 2933 | 2586 | 3706 | 1784 | 2997 | 2125 | 5295 | 4341 |  |  |  | 101235
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 614268.16 | 11277 | 3225 | 2621 | 14941 | 7287 | 12110 | 5765 | 9663 | 4376 | 0 | 0 | 0 | 685533.16
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 77600.16 | 1762.26 | 1475 | 1509.26 | 1467.18 | 1467.42 | 1466.6159 | 1334.5838 | 1459.8823 | 1316.4178 |  |  |  | 90858.7798
2.1.13 | -Manpower (HO-Consultant) | 34.38 | 9.38 | 9.38 | 9.53 | 0 | 20.1286 | 38.9773 | 13.5435 | 11.124 | 101.9642 |  |  |  | 248.4076
2.1.2 | -Manpower (RE) | 3509.68 | 123.85 | 198.71 | 187.58 | 184.38 | 167.94 | 196.6687 | 183.3478 | 180.8965 | 223.0682 |  |  |  | 5156.1211
2.1.3 | -Manpower (Labour) | 7508.28 | 296.15 | 300.04 | 319.83 | 318.23 | 295.58 | 347.7579 | 335.3432 | 331.3441 | 348.8271 |  |  |  | 10401.3823
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 14017.533 | 42.606 | 136.895 | 0 | 48.924 | 144.508 | 452.198 | 216.332 | 80.44 | 296.327 |  |  |  | 15435.763
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 56711.4948 | 940.6376 | 639.5201 | 1809.5764 | 2623.9853 | 1687.0655 | 716.0767 | 1517.1068 | 1596.1849 | 640.6971 |  |  |  | 68882.3451
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 363.6767 | 2.506 | 23.031 | 7.3905 | 22.355 | 1.462 | 2.9185 | 6.1112 | 4.959 | 12.292 |  |  |  | 446.7019
2.1.8 | -DSC | 30879.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 |  |  |  | 30887.268
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 12063.2784 | 59.1403 | 48.6014 | 59.6216 | 84.3508 | 194.5263 | 167.738 | 593.0885 | 167.3941 | 9.909 |  |  |  | 13447.6484
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 16229.628 | 70.442 | 4448.664 | 887.15 | 2594.065 | 134.88 | 3650.2625 | 2939.8595 | 1793.546 | 2041.729 |  |  |  | 34790.226
2.2.2 | -Reinforcement | 22083.7156 | 66.7299 | 0 | 22.5747 | 2806.14 | 131.0555 | 0 | 113.7486 | 0 | 166.0422 |  |  |  | 25390.0065
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1770.2542 | 0 | 12.465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1782.7192
2.3.2 | -Plant, Equipments & Tools (external hire) | 8077.1495 | 0 | 0 | 0 | 233.4 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8310.5495
2.3.3 | -Diesel & Lubricant | 1435.8274 | 64.8258 | 32.3891 | 35.7145 | 41.3159 | 34.9104 | 0 | 70.2275 | 36.033 | 36.358 |  |  |  | 1787.6016
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 7.3092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7.3092
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 622136.6011 | 1176.8 | 9746.888 | 2193.333 | 7587.7 | 0 | 0 | 0 | 0 | 0 |  |  |  | 642841.3221
2.4.2 | -Variation | 22464.1644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 22464.1644
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 896892.4003 | 4615.3276 | 17071.5836 | 7041.5607 | 18012.026 | 4279.4761 | 7039.2135 | 7323.2925 | 5661.8039 | 5201.6316 | 0 | 0 | 0 | 973138.3158
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -282624.2403 | 6661.6724 | -13846.5836 | -4420.5607 | -3071.026 | 3007.5239 | 5070.7865 | -1558.2925 | 4001.1961 | -825.6316 |  |  |  | -287605.1558
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -7.3092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -7.3092
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -3342.3823 | -207.8973 | -186.4134 | -182.3963 | -165.0283 | -160.671 | -142.7533 | -143.1521 | -207.9151 | -227.6951 |  |  |  | -4966.3042
4.3 | Total Adjustment | -3349.6915 | -207.8973 | -186.4134 | -182.3963 | -165.0283 | -160.671 | -142.7533 | -143.1521 | -207.9151 | -227.6951 | 0 | 0 | 0 | -4973.6134
5 | Gross Profit (Item 3.0-4.3) | -279274.5488 | 6869.5697 | -13660.1702 | -4238.1643 | -2905.9976 | 3168.1948 | 5213.5398 | -1415.1404 | 4209.1112 | -597.9366 |  |  |  | -282631.5424
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 18305.889 | 337.26 | 87.99 | 77.58 | 894.36 | 435.12 | 726.6 | 343.8 | 575.58 | 260.46 |  |  |  | 22044.639
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 6101.963 | 112.42 | 29.33 | 25.86 | 149.06 | 72.52 | 121.1 | 57.3 | 95.93 | 43.41 |  |  |  | 6808.893
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -303682.4008 | 6419.8897 | -13777.4902 | -4341.6043 | -3949.4176 | 2660.5548 | 4365.8398 | -1816.2404 | 3537.6012 | -901.8066 |  |  |  | -311485.0744
(=Item5.0 - 6.0 + 6.2)

## Accrual
KL-CW JV
Print Date: 2026-01-19
Project Code: | 1027
Project Name: | DC/2020/02 Construction of San Shek Wan Sewage Treatment Works, Associated Submarine Outfall and Pui O Sewerage Works
Report Date: | 2025-12-31
Start Date: | 2021-04-02 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-04-01 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-06-12 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 522843.551 | 14932 | 16096 | 15524 | 21984 | 11948 | 14662 | 11225 | 29241 | 23617 |  |  |  | 682072.551
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 4072.42 | 35 | 292 | 35 | 35 | 35 | 0 | 35 | 70 | 35 |  |  |  | 4644.42
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | -6661 | -5587 | -2689 | -4255 | -4208 | -34 | -1458 | 40 | 24852 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 520254.971 | 9380 | 13699 | 11304 | 17811 | 11949 | 13204 | 11300 | 54163 | 23652 | 0 | 0 | 0 | 686716.971
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 77600.02 | 1762.26 | 1475 | 1509.26 | 1467.18 | 1467.42 | 1466.6159 | 1334.5838 | 1459.8823 | 1316.4178 |  |  |  | 90858.6398
2.1.13 | -Manpower (HO-Consultant) | 34.38 | 9.38 | 9.38 | 9.53 | 0 | 20.1286 | 38.9773 | 13.5435 | 11.124 | 101.9642 |  |  |  | 248.4076
2.1.2 | -Manpower (RE) | 3509.81 | 123.85 | 198.71 | 187.58 | 184.38 | 167.94 | 196.6865 | 183.3478 | 180.8965 | 223.0682 |  |  |  | 5156.269
2.1.3 | -Manpower (Labour) | 7508.02 | 296.15 | 300.04 | 319.83 | 318.23 | 295.58 | 347.7579 | 335.3432 | 331.3441 | 348.8271 |  |  |  | 10401.1223
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 14017.533 | 42.606 | 136.895 | 0 | 48.924 | 144.508 | 452.198 | 216.332 | 80.44 | 296.327 |  |  |  | 15435.763
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 51361.0314 | 839.3095 | 916.8324 | 947.1453 | 791.4263 | 1121.0539 | 332.8487 | 3547.3935 | 1470.9673 | 224.8282 |  |  |  | 61552.8365
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 363.6767 | 2.506 | 23.031 | 7.3905 | 22.355 | 1.462 | 2.9185 | 6.1112 | 4.959 | 12.292 |  |  |  | 446.7019
2.1.8 | -DSC | 22407.4267 | 405.1386 | 210.1796 | 85.8 | 21.6 | 163.5 | 0 | 220.1788 | 0 | 8 |  |  |  | 23521.8237
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 3908.0637 | 148.1139 | 17.9524 | 69.0066 | 28.7908 | 106.3162 | 1.069 | 743.5705 | 626.2361 | 2.5 |  |  |  | 5651.6193
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 11031.113 | 4553.966 | 2474.7175 | 1006.4975 | 1737.77 | 793.99 | 0 | 7051.138 | 2638.888 | 0 |  |  |  | 31288.08
2.2.2 | -Reinforcement | 7884.5227 | 7024.6704 | 192.0998 | 378.0615 | 225.4554 | 57.0158 | 0 | 2211.3395 | 128.897 | 0 |  |  |  | 18102.0621
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.14 | -Deposit | 4216.046 | 304.3615 | 64 | 0 | -19.5 | -59.3615 | 40 | 0 | -385 | 1230.605 |  |  |  | 5391.151
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1770.2542 | 12.465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1782.7192
2.3.2 | -Plant, Equipments & Tools (external hire) | 5278.56 | 302.6 | 95 | 136.04 | 105 | 95 | 0 | 443.4 | 95 | 0 |  |  |  | 6550.6
2.3.3 | -Diesel & Lubricant | 1435.8274 | 64.8258 | 32.3891 | 35.7145 | 41.3159 | 34.9104 | 0 | 70.2275 | 36.033 | 36.358 |  |  |  | 1787.6016
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 7.3092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7.3092
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 245451.7581 | 25246.0529 | 5730.9419 | 6898.2804 | 6752.6414 | 0 | 0 | 37565.6667 | 4523.7767 | 0 |  |  |  | 332169.118
2.4.2 | -Variation | 15370.5932 | 395.7097 | 696.6 | 283.4006 | 190.9878 | 0 | 0 | 1040.9985 | 0 | 0 |  |  |  | 17978.2898
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 24946.1454 | -20.463 | 2.466 | 424.0213 | -373.6021 | 0 | 0 | 63.0928 | 0 | 8.6 |  |  |  | 25050.2604
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | -25791.2412 | -40.6085 | -4.513 | -18.777 | -2.119 | 0 | 0 | -9.1855 | 0 | 0 |  |  |  | -25866.4442
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 472310.8494 | 41472.8938 | 12571.7216 | 12278.7812 | 11540.8355 | 4409.4634 | 2879.0718 | 55037.0819 | 11203.444 | 3809.7875 | 0 | 0 | 0 | 627513.9302
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 47944.1216 | -32092.8938 | 1127.2784 | -974.7812 | 6270.1645 | 7539.5366 | 10324.9282 | -43737.0819 | 42959.556 | 19842.2125 |  |  |  | 59203.0408
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -7.3092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -7.3092
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -3342.3823 | -207.8973 | -186.4134 | -182.3963 | -165.0283 | -160.671 | -142.7533 | -143.1521 | -207.9151 | -227.6951 |  |  |  | -4966.3042
4.3 | Total Adjustment | -3349.6915 | -207.8973 | -186.4134 | -182.3963 | -165.0283 | -160.671 | -142.7533 | -143.1521 | -207.9151 | -227.6951 | 0 | 0 | 0 | -4973.6134
5 | Gross Profit (Item 3.0-4.3) | 51293.8131 | -31884.9965 | 1313.6918 | -792.3848 | 6435.1928 | 7700.2075 | 10467.6815 | -43593.9299 | 43167.4711 | 20069.9075 |  |  |  | 64176.6542
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 15485.4765 | 280.35 | 402.21 | 338.07 | 1066.56 | 714.84 | 792.24 | 675.9 | 3245.58 | 1417.02 |  |  |  | 24418.2465
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 5161.8255 | 93.45 | 134.07 | 112.69 | 177.76 | 119.14 | 132.04 | 112.65 | 540.93 | 236.17 |  |  |  | 6820.7255
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 30646.5111 | -32258.7965 | 777.4118 | -1243.1448 | 5190.8728 | 6866.2275 | 9543.4015 | -44382.4799 | 39380.9611 | 18416.7175 |  |  |  | 32937.6822
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
KL-CW JV
Print Date: 2026-01-19
Project Code: | 1027
Project Name: | DC/2020/02 Construction of San Shek Wan Sewage Treatment Works, Associated Submarine Outfall and Pui O Sewerage Works
Report Date: | 2025-12-31
Start Date: | 2021-04-02 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-04-01 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-06-12 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 509332.0366 | 17427 | 14931.9 | 16096 | 15524.68 | 21983.91 | 11947.85 | 14661.95 | 36229.27 | 4236.8794 |  |  |  | 662371.476
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | -4018.4 | -2643 | -5586.78 | -2689 | -4255.61 | -4208.0953 | -34 | -1458.02 | 89.37 | 24803.1875 |  |  |  | -0.34775
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | -4933.43 | -139.3 | -114.32 | 131 | -120.25 | -184.8391 | -84.48 | -146.62 | -327.29 | 27.6312 |  |  |  | -5891.8979
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 500380.2066 | 14644.7 | 9230.8 | 13538 | 11148.82 | 17590.9756 | 11829.37 | 13057.31 | 35991.35 | 29067.6982 | 0 | 0 | 0 | 656479.2304
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 77599.96 | 1762.26 | 1475 | 1509.26 | 1467.18 | 1467.42 | 1466.6159 | 1334.5838 | 1459.8823 | 1316.4178 |  |  |  | 90858.5798
2.1.13 | -Manpower (HO-Consultant) | 34.38 | 9.38 | 9.38 | 9.53 | 0 | 20.1286 | 38.9773 | 13.5435 | 11.124 | 101.9642 |  |  |  | 248.4076
2.1.2 | -Manpower (RE) | 3509.81 | 123.85 | 198.71 | 187.58 | 184.38 | 167.94 | 196.6865 | 183.3478 | 180.8965 | 223.0682 |  |  |  | 5156.269
2.1.3 | -Manpower (Labour) | 7508.02 | 296.15 | 300.04 | 319.83 | 318.23 | 295.58 | 347.7579 | 335.3432 | 331.3441 | 348.8271 |  |  |  | 10401.1223
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 14017.533 | 42.606 | 136.895 | 0 | 48.924 | 127.873 | 452.198 | 93.232 | 97.075 | 296.327 |  |  |  | 15312.663
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 46150.3 | 2022.8621 | 731.3379 | 513.4364 | 916.8188 | 511.6047 | 638.1865 | 1163.2841 | 1363.9041 | 1111.8006 |  |  |  | 55123.5351
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 361.4107 | 0 | 27.803 | 4.648 | 20.769 | 4.3285 | 1.462 | 2.9185 | 7.7112 | 15.651 |  |  |  | 446.7019
2.1.8 | -DSC | 22407.4267 | 0 | 83.1994 | 57 | 153.1796 | 26.6 | 177.5766 | 256.6998 | 185.6 | 170.7421 |  |  |  | 23518.0242
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 3344.407 | 4.235 | 3.161 | 186.8941 | 67.47 | 54.9704 | 73.7126 | 7.139 | 386.1465 | 398.8421 |  |  |  | 4526.9777
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 9805.0075 | 590.826 | 705.7215 | 2034.865 | 894.74 | 2438.669 | 2594.065 | 1246.2 | 2477.4925 | 2440.3245 |  |  |  | 25227.911
2.2.2 | -Reinforcement | 6266.2618 | 382.9 | 1183.761 | 1069.3173 | 890.3643 | 2299.7817 | 3383.6334 | 802.8807 | 1597.2497 | 70.3351 |  |  |  | 17946.4849
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.14 | -Deposit | 6753.6389 | 304.3615 | 64 | 0 | -19.5 | -59.3615 | 40 | 0 | -385 | 1230.605 |  |  |  | 7928.7439
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1770.2542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.465 | 0 |  |  |  | 1782.7192
2.3.2 | -Plant, Equipments & Tools (external hire) | 3937.6378 | 65.05 | 238.5677 | 663.4 | 95 | 190 | 0 | 200 | 13.8 | 190 |  |  |  | 5593.4555
2.3.3 | -Diesel & Lubricant | 1333.4349 | 0 | 64.8258 | 32.3891 | 35.7145 | 41.3159 | 34.9104 | 37.5099 | 32.7176 | 36.033 |  |  |  | 1648.8511
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 7.3092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7.3092
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 233164.7259 | 2355.6286 | 9623.9415 | 8166.4929 | 10168.6547 | 9711.4441 | 6889.6301 | 7070.6206 | 10768.4643 | 14876.7918 |  |  |  | 312796.3945
2.4.2 | -Variation | 15066.773 | 202.0533 | 240.4458 | 144.981 | 237.7797 | 697.7224 | 53.7212 | 78.2401 | 199.5748 | 20.5137 |  |  |  | 16941.805
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 24327.2408 | 351.757 | 13.5 | 220.562 | 124.451 | 191.0619 | -374.9518 | 0 | -0.04969 | -8.8765 |  |  |  | 24844.6947
2.4.5 | -Down Payment | 1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1077
2.4.6 | -Retention | -14024.9753 | -130.9209 | -843.2097 | -521.0817 | -731.8305 | -593.4865 | -548.8845 | -625.1245 | -667.1342 | -344.7739 |  |  |  | -19031.4216
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | -24795.8922 | -126.4144 | -31.4799 | -452.104 | -153.2157 | -23.1837 | -3.0695 | -10.0769 | -1.2895 | -0.90459 |  |  |  | -25597.6305
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 439621.6639 | 8256.5842 | 14225.5999 | 14147 | 14719.1092 | 17570.4085 | 15462.2276 | 12190.3416 | 18071.9741 | 22493.6883 | 0 | 0 | 0 | 576758.5973
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 60758.5426 | 6388.1158 | -4994.7999 | -609 | -3570.2892 | 20.5671 | -3632.8576 | 866.9684 | 17919.3759 | 6574.0099 |  |  |  | 79720.633
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -7.3092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -7.3092
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -3342.3823 | -207.8973 | -186.4134 | -182.3963 | -165.0283 | -160.671 | -142.7533 | -143.1521 | -207.9151 | -227.6951 |  |  |  | -4966.3042
4.3 | Total Adjustment | -3349.6915 | -207.8973 | -186.4134 | -182.3963 | -165.0283 | -160.671 | -142.7533 | -143.1521 | -207.9151 | -227.6951 | 0 | 0 | 0 | -4973.6134
5 | Gross Profit (Item 3.0-4.3) | 64108.2341 | 6596.0131 | -4808.3865 | -426.6037 | -3405.2609 | 181.2381 | -3490.1043 | 1010.1205 | 18127.2911 | 6801.7049 |  |  |  | 84694.2464
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 15011.4062 | 439.341 | 276.924 | 406.14 | 668.9292 | 1055.4585 | 709.7622 | 783.4386 | 2159.481 | 1744.0619 |  |  |  | 23254.9426
6.1.2 | BU Overhead (1.0000% of Total Income excl. PC & Provisional Sum) | 5003.8021 | 146.447 | 92.308 | 135.38 | 111.4882 | 175.9098 | 118.2937 | 130.5731 | 359.9135 | 290.677 |  |  |  | 6564.7923
6.2 | Acc. Profit/(Loss) ~ B/F |  | 44093.0259 | 50103.251 | 44925.6325 | 43957.5088 | 39771.8305 | 38721.7003 | 34403.54 | 34499.6488 | 50107.5454
7 | Acc. Net Profit/(Loss) | 44093.0259 | 50103.251 | 44925.6325 | 43957.5088 | 39771.8305 | 38721.7003 | 34403.54 | 34499.6488 | 50107.5454 | 54874.5115 |  |  |  | 54874.5115
(=Item5.0 - 6.0 + 6.2)