## Financial Status
Vasteam Construction Limited
Print Date: 2026-01-13
Project Code: | 1057
Project Name: | Contract No. 18/WSD/21 Uprating of Pui O Raw Water Pumping Station and Pui O No. 2 Raw Water Pumping Station and Laying of Raw Water Mains along South Lantau Road
Report Date: | 2025-12-31
Start Date: | 2022-06-08 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-10-08 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2026-11-25 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 342900 | 342900 | 0 | 342900 | 342900 | 342900 | 0 | 342900 | 342900 | 100% | 0 | 362872.99 | 354090.93 | 103.3% | -11190.93
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 38553 | 54468 | 0 | 54468 | 74852 | 74852 | 0 | 74852 | 49356.73 | 90.62% | 5111.27 | 0 | 0 | 0% | 49356.73
1.2.2 | -Fee of C.E. | 7325 | 10349 | 0 | 10349 | 14222 | 14222 | 0 | 14222 | 9378.17 | 90.62% | 970.83 | 0 | 0 | 0% | 9378.17
1.3 | Provisional Sum | 10002 | 5569 | 0 | 5569 | 5569 | 5569 | 0 | 5569 | 3856.62 | 69.25% | 1712.38 | 6763.58 | 6020.08 | 156.1% | -2163.46
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 58086 | 64910 | 0 | 64910 | 21191 | 21191 | 0 | 21191 | 8448.5 | 13.02% | 56461.5 | 0 | 0 | 0% | 8448.5
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 153962 | 153962 | 0 | 153962 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.2 | -Pain Gain Sharing | 16660 | 23910 | 0 | 23910 | 23910 | 23910 | 0 | 23910 | 0 | 0% | 23910 | -9759 | -8652.68 | 0% | 8652.68
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3541.02 | 0% | 3541.02
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Income | 473526 | 502106 | 0 | 502106 | 636606 | 636606 | 0 | 636606 | 413940.02 | 82.44% | 88165.98 | 359877.57 | 347917.31 | 84.05% | 66022.71
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 29947.232 | 38671.019 | 0 | 38671.019 | 47271 | 47271 | 4000 | 51271 | 47547.1691 | 123% | -8876.1501 | 47547.1691 | 47547.1591 | 100% | 0.01
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 49 | 334 | 80 | 414 | 413.5996 | 0% | -413.5996 | 413.5996 | 413.5996 | 100% | 0
2.1.2 | -Manpower (RE) | 9776 | 9776 | 0 | 9776 | 7776 | 7776 | 0 | 7776 | 6231.0796 | 63.74% | 3544.9204 | 6231.0796 | 6231.0796 | 100% | 0
2.1.3 | -Manpower (Labour) | 0 | 3517.455 | 0 | 3517.455 | 5799 | 5799 | 0 | 5799 | 5308.3534 | 150.9% | -1790.8984 | 5308.3534 | 5308.3534 | 100% | 0
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 10912.877 | 11882.192 | 0 | 11882.192 | 11879 | 11879 | 0 | 11879 | 9080.198 | 76.42% | 2801.994 | 9080.198 | 9034.667 | 99.5% | 45.531
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | -113426.4247 | 31536.3627 | 0 | 31536.3627 | 25645.59 | 28671 | 3499.59 | 32170.59 | 31690.0176 | 100.5% | -153.6549 | 29074.2368 | 27136.0257 | 85.63% | 4553.9919
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0 | 0 | 275 | 325 | 0 | 325 | 283.9157 | 0% | -283.9157 | 283.9157 | 280.0867 | 98.65% | 3.829
2.1.8 | -DSC | 20991.9554 | 19966.2084 | 0 | 19966.2084 | 15483 | 15583 | 0 | 15583 | 15572.166 | 77.99% | 4394.0423 | 12817.7492 | 12608.3092 | 80.97% | 2963.8568
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 5 | 0% | -5 | 0 | 0 | 0% | 5
2.1.10 | -Plant | 3277.393 | 3277.393 | 0 | 3277.393 | 9525 | 9860 | 40 | 9900 | 9876.1864 | 301.3% | -6598.7934 | 9438.9983 | 7799.8608 | 78.98% | 2076.3256
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | -10 | -10 | 0 | -10 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 4800 | 5150 | 250 | 5400 | 5353.65 | 0% | -5353.65 | 5331.368 | 5110.118 | 95.45% | 243.532
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 2680 | 2680 | 0 | 2680 | 2649.1974 | 0% | -2649.1974 | 2617.3 | 2617.3 | 98.8% | 31.8974
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 9250 | 9250 | 0 | 9250 | 9207.6108 | 0% | -9207.6108 | 5835.1304 | 5482.1205 | 59.54% | 3725.4904
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 700 | 750 | 0 | 750 | 729.2181 | 0% | -729.2181 | 726.5311 | 306.263 | 42% | 422.9551
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 6464.2304 | 7206.2615 | 0% | -7206.2615
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 4734.598 | 5204.437 | 0 | 5204.437 | 1728 | 1728 | 0 | 1728 | 1109.93 | 21.33% | 4094.507 | 1109.93 | 1109.93 | 100% | 0
2.3.2 | -Plant, Equipments & Tools (external hire) | 0 | 0 | 0 | 0 | 13740 | 14540 | 0 | 14540 | 14526.2821 | 0% | -14526.2821 | 13894.942 | 13566.7847 | 93.39% | 959.4974
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 1475 | 1775 | 50 | 1825 | 1814.1652 | 0% | -1814.1652 | 1773.6852 | 1698.072 | 93.6% | 116.0932
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 1315.541 | 1315.541 | 0 | 1315.541 | 65 | 70 | 0 | 70 | 69.6766 | 5.296% | 1245.8644 | 69.6766 | 69.6766 | 100% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 348350.9294 | 349891.0941 | 0 | 349891.0941 | 378637 | 373337 | -7920 | 365417 | 200123.2206 | 57.2% | 149767.8736 | 122135.6646 | 110275.5467 | 55.1% | 89847.6739
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 55967 | 55967 | 0 | 55967 | 50449.7912 | 0% | -50449.7912 | 33212.0587 | 31696.793 | 62.83% | 18752.9983
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | -11855.9041 | -10305.02 | 0% | 10305.02
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -11955.8374 | 0% | 11955.8374
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -44926 | -44926 | 0 | -44926 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 57429.3 | 57429 | 0.3 | 57429.3 | 57428.8 | 0% | -57428.8 | 17175.2975 | 11963.0197 | 20.83% | 45465.7803
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 2251.41 | 2251.41 | 0 | 2251.41 | 2251.4082 | 0% | -2251.4082 | 2251.4082 | 2251.4082 | 100% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 315880.101 | 475037.7022 | 0 | 475037.7022 | 607499.3 | 607499.41 | -0.11 | 607499.3 | 471720.6357 | 99.3% | 3317.0665 | 320936.6185 | 287451.5776 | 60.94% | 184269.0581
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 157645.899 | 27068.2978 | 0 | 27068.2978 | 29106.7 | 29106.59 | 0.11 | 29106.7 | -57780.6157 | -213.5% | 84848.9135 | 38940.9515 | 60465.7324 | -104.6% | -118246.3481
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | 0 |  |  | 0 | 0 | 0% |  | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | -65 |  |  | -70 | -69.6766 | 0% |  | -69.6766 | -69.6766 | 100% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | 0 |  |  | -4565.8759 | -4565.8759 | 0% | 4565.8759 | -4565.8759 | -4565.8759 | 100% | -4.9022e-10
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | -65 |  |  | -4635.8759 | -4635.5525 | 0% | 4635.5525 | -4635.5525 | -4635.5525 | 100% | -4.9022e-10
5 | Gross Profit (Item 3.0-4.3) | 157645.899 | 27068.2978 | 0 | 27068.2978 | 29171.7 |  |  | 33742.5759 | -53145.0632 | -196.3% | 80213.361 | 43576.504 | 65101.2849 | -122.5% | -118246.3481
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 27811.44 | 29792.22 | 0 | 29792.22 | 37862.22 |  |  | 18925.11 | 12405.414 | 41.64% | 17386.806 | 12306.5631 | 12037.3044 | 97.03% | 368.1096
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 129834.459 | -2723.9222 | 0 | -2723.9222 | -8690.52 |  |  | 14817.4659 | -65550.4772 | 2406% | 62826.555 | 31269.9409 | 53063.9805 | -80.95% | -118614.4577
(=Item5.0 - 6.0 + 6.2)

## Projection
Vasteam Construction Limited
Print Date: 2026-01-13
Project Code: | 1057
Project Name: | Contract No. 18/WSD/21 Uprating of Pui O Raw Water Pumping Station and Pui O No. 2 Raw Water Pumping Station and Laying of Raw Water Mains along South Lantau Road
Report Date: | 2025-12-31
Start Date: | 2022-06-08 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-10-08 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-11-25 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 342900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 342900
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 75020 | -3529 | 3529 | 0 | 0 | 0 | 0 | 0 | -168 | 0 |  |  |  | 74852
1.2.2 | -Fee of C.E. | 14254 | -671 | 671 | 0 | 0 | 0 | 0 | 0 | -32 | 0 |  |  |  | 14222
1.3 | Provisional Sum | 5569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5569
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 21191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 21191
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 153962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 153962
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 23910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 23910
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 636806 | -4200 | 4200 | 0 | 0 | 0 | 0 | 0 | -200 | 0 | 0 | 0 | 0 | 636606
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 47471 | -2200 | 2200 | 0 | 0 | 0 | 0 | 0 | -200 | 4000 |  |  |  | 51271
2.1.13 | -Manpower (HO-Consultant) | 39 | 0 | 10 | 10 | 10 | 145 | 120 | 0 | 20 | 60 |  |  |  | 414
2.1.2 | -Manpower (RE) | 7776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7776
2.1.3 | -Manpower (Labour) | 5517 | -1718 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5799
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 11879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11879
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 23465.59 | 1180 | 1000 | 335 | 350 | 1340 | 500 | 500 | 1700 | 1800 |  |  |  | 32170.59
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 |  |  |  | 325
2.1.8 | -DSC | 15483 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15583
2.1.9 | -General Material | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10
2.1.10 | -Plant | 9175 | 150 | 215 | 160 | 100 | 0 | 50 | 10 | 40 | 0 |  |  |  | 9900
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -10
2.2 | Materials
2.2.1 | -Concrete | 4450 | 150 | 250 | 150 | 0 | 100 | 0 | 50 | 200 | 50 |  |  |  | 5400
2.2.2 | -Reinforcement | 2580 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2680
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 9200 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9250
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 350 | 0 | 350 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  | 750
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1728
2.3.2 | -Plant, Equipments & Tools (external hire) | 12800 | 640 | 300 | 0 | 200 | 0 | 300 | 300 | 0 | 0 |  |  |  | 14540
2.3.3 | -Diesel & Lubricant | 1375 | 0 | 100 | 50 | 50 | 50 | 150 | 0 | 50 | 0 |  |  |  | 1825
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 65 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 |  |  |  | 70
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 383349 | -2452 | -2260 | -780 | -850 | -1050 | -1710 | -910 | -2010 | -5910 |  |  |  | 365417
2.4.2 | -Variation | 55967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 55967
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | -44926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -44926
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 57429.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 57429.3
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 2251.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2251.41
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 607699.3 | -4200 | 4265 | 25 | -90 | 590 | -590 | 0 | -200 | 0 | 0 | 0 | 0 | 607499.3
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 29106.7 | 0 | -65 | -25 | 90 | -590 | 590 | 0 | 0 | 0 |  |  |  | 29106.7
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -65 | 0 | 0 | 0 | 0 | -5 | 0 | 0 | 0 | 0 |  |  |  | -70
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -2756.1141 | -177.0403 | -179.3332 | -193.9286 | -199.41 | -209.6256 | -204.4633 | -205.4939 | -220.2845 | -220.1825 |  |  |  | -4565.8759
4.3 | Total Adjustment | -2821.1141 | -177.0403 | -179.3332 | -193.9286 | -199.41 | -214.6256 | -204.4633 | -205.4939 | -220.2845 | -220.1825 | 0 | 0 | 0 | -4635.8759
5 | Gross Profit (Item 3.0-4.3) | 31927.8141 | 177.0403 | 114.3332 | 168.9286 | 289.41 | -375.3744 | 794.4633 | 205.4939 | 220.2845 | 220.1825 |  |  |  | 33742.5759
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 18937.11 | -126 | 126 | 0 | 0 | 0 | 0 | 0 | -12 | 0 |  |  |  | 18925.11
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 12990.7041 | 303.0403 | -11.6668 | 168.9286 | 289.41 | -375.3744 | 794.4633 | 205.4939 | 232.2845 | 220.1825 |  |  |  | 14817.4659
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
Vasteam Construction Limited
Print Date: 2026-01-13
Project Code: | 1057
Project Name: | Contract No. 18/WSD/21 Uprating of Pui O Raw Water Pumping Station and Pui O No. 2 Raw Water Pumping Station and Laying of Raw Water Mains along South Lantau Road
Report Date: | 2025-12-31
Start Date: | 2022-06-08 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-10-08 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-11-25 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 342900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 342900
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 35019.13 | 0 | 263.4 | 12482 | 30.8 | 0 | 325.4 | -380 | 0 | 1616 |  |  |  | 49356.73
1.2.2 | -Fee of C.E. | 6653.57 | 0 | 50 | 2371 | 6 | 0 | 61.8 | -71.2 | 0 | 307 |  |  |  | 9378.17
1.3 | Provisional Sum | 2743.02 | 38.6 | 77 | 0 | 0 | 138.24 | 0 | 115.86 | 0 | 743.9 |  |  |  | 3856.62
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 6054.9 | 225 | 394 | 240 | 129.6 | -20 | 403 | 372 | 364 | 286 |  |  |  | 8448.5
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 393370.62 | 263.6 | 784.4 | 15093 | 166.4 | 118.24 | 790.2 | 36.66 | 364 | 2952.9 | 0 | 0 | 0 | 413940.02
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 36781.01 | 1104.11 | 1337.92 | 1178.1733 | 1271.43 | 1194.67 | 1171.6728 | 1183.4441 | 1191.9038 | 1132.8351 |  |  |  | 47547.1691
2.1.13 | -Manpower (HO-Consultant) | 37.75 | 0 | 9.38 | 11.527 | 6.08 | 143.51 | 102.9523 | 13.3185 | 19.57 | 69.5118 |  |  |  | 413.5996
2.1.2 | -Manpower (RE) | 4313.17 | 222.26 | 219.32 | 219.9343 | 184.54 | 210.75 | 220.5549 | 224.8569 | 214.15 | 201.5435 |  |  |  | 6231.0796
2.1.3 | -Manpower (Labour) | 3584.56 | 213.7 | 182.21 | 152.8305 | 168.96 | 157.76 | 168.3394 | 217.3633 | 221.32 | 241.3102 |  |  |  | 5308.3534
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 8293.378 | 83.485 | 97.365 | 97.771 | 91.994 | 99.518 | 55.56 | 70.102 | 128.884 | 62.141 |  |  |  | 9080.198
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 23944.5424 | 881.8059 | 751.7131 | 382.7477 | 392.7138 | 745.2696 | 609.6169 | 863.5974 | 1400.5974 | 1717.4135 |  |  |  | 31690.0176
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 257.4442 | 2.0825 | 5.079 | 3.531 | 2.843 | 0 | 0 | 4.259 | 4.848 | 3.829 |  |  |  | 283.9157
2.1.8 | -DSC | 15452.166 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15572.166
2.1.9 | -General Material | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5
2.1.10 | -Plant | 9131.5323 | 172.876 | 193.3179 | 63.562 | 167.249 | 37.0609 | 14.829 | 34.3063 | 45.76 | 15.693 |  |  |  | 9876.1864
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 4423.1675 | 131.915 | 203.2425 | 167.875 | 34.9275 | 38.175 | 39.6875 | 65.6 | 218.1825 | 30.8775 |  |  |  | 5353.65
2.2.2 | -Reinforcement | 2569.3974 | 0 | 79.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2649.1974
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 9177.6108 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9207.6108
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 322.0781 | 0 | 0 | 357.28 | 0 | 49.86 | 0 | 0 | 0 | 0 |  |  |  | 729.2181
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1107.93 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  |  |  | 1109.93
2.3.2 | -Plant, Equipments & Tools (external hire) | 12791.6901 | 328.4404 | 433.954 | 132.0626 | 58.245 | 147.347 | 9.4 | 600.613 | 24.53 | 0 |  |  |  | 14526.2821
2.3.3 | -Diesel & Lubricant | 1306.776 | 55.9185 | 111.3834 | 44.7269 | 40.3128 | 29.9935 | 43.0673 | 144.3357 | 29.2026 | 8.4484 |  |  |  | 1814.1652
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 61.902 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 0 | 0 | 0 |  |  |  | 69.6766
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 200123.2206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 200123.2206
2.4.2 | -Variation | 50209.7912 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50449.7912
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 57428.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 57428.8
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 2251.4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2251.4082
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 443574.3248 | 3220.889 | 3632.9807 | 2813.3171 | 2780.5909 | 2855.2098 | 2436.9758 | 3423.7962 | 3498.9483 | 3483.6031 | 0 | 0 | 0 | 471720.6357
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -50203.7048 | -2957.289 | -2848.5807 | 12279.6829 | -2614.1909 | -2736.9698 | -1646.7758 | -3387.1362 | -3134.9483 | -530.7031 |  |  |  | -57780.6157
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -61.902 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | 0 | 0 | 0 |  |  |  | -69.6766
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -2756.1141 | -177.0403 | -179.3332 | -193.9286 | -199.41 | -209.6256 | -204.4633 | -205.4939 | -220.2845 | -220.1825 |  |  |  | -4565.8759
4.3 | Total Adjustment | -2818.016 | -178.3361 | -180.6289 | -195.2243 | -200.7057 | -210.9213 | -205.7591 | -205.4939 | -220.2845 | -220.1825 | 0 | 0 | 0 | -4635.5525
5 | Gross Profit (Item 3.0-4.3) | -47385.6887 | -2778.9529 | -2667.9518 | 12474.9073 | -2413.4852 | -2526.0484 | -1441.0168 | -3181.6423 | -2914.6638 | -310.5206 |  |  |  | -53145.0632
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 11718.828 | 6.75 | 21.222 | 452.79 | 9.984 | -1.2 | 47.412 | -4.752 | 21.84 | 132.54 |  |  |  | 12405.414
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -59104.5167 | -2785.7029 | -2689.1738 | 12022.1173 | -2423.4692 | -2524.8484 | -1488.4288 | -3176.8903 | -2936.5038 | -443.0606 |  |  |  | -65550.4772
(=Item5.0 - 6.0 + 6.2)

## Accrual
Vasteam Construction Limited
Print Date: 2026-01-13
Project Code: | 1057
Project Name: | Contract No. 18/WSD/21 Uprating of Pui O Raw Water Pumping Station and Pui O No. 2 Raw Water Pumping Station and Laying of Raw Water Mains along South Lantau Road
Report Date: | 2025-12-31
Start Date: | 2022-06-08 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-10-08 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-11-25 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 258890.11 | 10623 | 15891.6 | 12132.9 | 11931.4 | 10956.5 | 10262.96 | 11550.12 | 11851.9 | 8782.5 |  |  |  | 362872.99
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 5650.02 | 38.6 | 77 | 0 | 0 | 138.2 | 0 | 115.86 | 0 | 743.9 |  |  |  | 6763.58
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | -1528.4 | -1503.1 | -1380.2 | -1292.9 | -1455 | -1493 | -1106.4 |  |  |  | -9759
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 264540.13 | 10661.6 | 15968.6 | 10604.5 | 10428.3 | 9714.5 | 8970.06 | 10210.98 | 10358.9 | 8420 | 0 | 0 | 0 | 359877.57
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 36781.01 | 1104.11 | 1337.92 | 1178.1733 | 1271.43 | 1194.67 | 1171.6728 | 1183.4441 | 1191.9038 | 1132.8351 |  |  |  | 47547.1691
2.1.13 | -Manpower (HO-Consultant) | 37.75 | 0 | 9.38 | 11.527 | 6.08 | 143.51 | 102.9523 | 13.3185 | 19.57 | 69.5118 |  |  |  | 413.5996
2.1.2 | -Manpower (RE) | 4313.17 | 222.26 | 219.32 | 219.9343 | 184.54 | 210.75 | 220.5549 | 224.8569 | 214.15 | 201.5435 |  |  |  | 6231.0796
2.1.3 | -Manpower (Labour) | 3584.56 | 213.7 | 182.21 | 152.8305 | 168.96 | 157.76 | 168.3394 | 217.3633 | 221.32 | 241.3102 |  |  |  | 5308.3534
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 8293.378 | 83.485 | 97.365 | 97.771 | 91.994 | 99.518 | 55.56 | 70.102 | 128.884 | 62.141 |  |  |  | 9080.198
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 21822.2659 | 1679.1094 | 595.9158 | 455.9889 | 300.8162 | 1329.9783 | 0.60866 | 1045.3112 | 607.85 | 1236.3925 |  |  |  | 29074.2368
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 257.4442 | 2.0825 | 5.079 | 3.531 | 2.843 | 0 | 0 | 4.259 | 4.848 | 3.829 |  |  |  | 283.9157
2.1.8 | -DSC | 10972.2674 | 294.7 | 68.9 | 527.5618 | 442.52 | 66.16 | 0 | 319.04 | 126.6 | 0 |  |  |  | 12817.7492
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 6068.688 | 433.27 | 86.0199 | 1178.3482 | 24.054 | 109.7059 | 0 | 1486.4993 | 51.7 | 0.713 |  |  |  | 9438.9983
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 4416.2255 | 329.7125 | 167.875 | 32.2675 | 30.94 | 39.6875 | 0 | 283.7825 | 30.8775 | 0 |  |  |  | 5331.368
2.2.2 | -Reinforcement | 2540.1 | 0 | 77.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2617.3
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 5383.0554 | 99.065 | 0 | 0 | 0 | 0 | 0 | 353.01 | 0 | 0 |  |  |  | 5835.1304
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 328.3911 | 0 | 0 | 0 | 0 | 0 | 0 | 398.14 | 0 | 0 |  |  |  | 726.5311
2.2.14 | -Deposit | 7542.4122 | 194.0562 | 0 | 0 | -17.674 | -757.748 | 107.184 | -420 | 0 | -184 |  |  |  | 6464.2304
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1107.93 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  |  |  | 1109.93
2.3.2 | -Plant, Equipments & Tools (external hire) | 12473.3585 | 609.7243 | 134.8549 | 48.332 | 151.055 | 96.172 | 0 | 333.118 | 48.3272 | 0 |  |  |  | 13894.942
2.3.3 | -Diesel & Lubricant | 1266.296 | 134.1673 | 33.1346 | 44.7269 | 83.3802 | 29.9935 | 0 | 150.5272 | 31.4596 | 0 |  |  |  | 1773.6852
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 61.902 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 0 | 0 | 0 |  |  |  | 69.6766
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 84801.0958 | 11775.23 | 4296.848 | 1120.1 | 3683 | 753.8 | 0 | 14091.0907 | 1614.5 | 0 |  |  |  | 122135.6646
2.4.2 | -Variation | 22217.9828 | 2426.4244 | 5312.2087 | 1047.9835 | 104.1694 | 1277.2 | 0 | 754.4158 | 71.6742 | 0 |  |  |  | 33212.0587
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | -12971.4832 | 85.254 | 45.536 | -6.8036 | 2910.763 | 5.1191 | 14.0438 | -1820.5374 | -130.1285 | 12.3327 |  |  |  | -11855.9041
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 8534.0273 | 1890.4127 | 271.6 | 1063.7795 | 1912.025 | 140 | 0 | 1798.6045 | 1564.8485 | 0 |  |  |  | 17175.2975
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 2251.4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2251.4082
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 232083.2352 | 21578.0591 | 12942.6626 | 7177.3476 | 11352.1915 | 4897.5721 | 1842.2116 | 20488.3457 | 5798.3843 | 2776.6088 | 0 | 0 | 0 | 320936.6185
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 32456.8948 | -10916.4591 | 3025.9374 | 3427.1524 | -923.8915 | 4816.9279 | 7127.8484 | -10277.3657 | 4560.5157 | 5643.3912 |  |  |  | 38940.9515
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -61.902 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | 0 | 0 | 0 |  |  |  | -69.6766
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -2756.1141 | -177.0403 | -179.3332 | -193.9286 | -199.41 | -209.6256 | -204.4633 | -205.4939 | -220.2845 | -220.1825 |  |  |  | -4565.8759
4.3 | Total Adjustment | -2818.016 | -178.3361 | -180.6289 | -195.2243 | -200.7057 | -210.9213 | -205.7591 | -205.4939 | -220.2845 | -220.1825 | 0 | 0 | 0 | -4635.5525
5 | Gross Profit (Item 3.0-4.3) | 35274.9108 | -10738.123 | 3206.5663 | 3622.3767 | -723.1858 | 5027.8493 | 7333.6074 | -10071.8718 | 4780.8002 | 5863.5737 |  |  |  | 43576.504
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 7766.7033 | 318.69 | 476.748 | 318.135 | 625.698 | 574.578 | 538.2036 | 605.7072 | 621.534 | 460.566 |  |  |  | 12306.5631
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 27508.2075 | -11056.813 | 2729.8183 | 3304.2417 | -1348.8838 | 4453.2713 | 6795.4038 | -10677.579 | 4159.2662 | 5403.0077 |  |  |  | 31269.9409
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
Vasteam Construction Limited
Print Date: 2026-01-13
Project Code: | 1057
Project Name: | Contract No. 18/WSD/21 Uprating of Pui O Raw Water Pumping Station and Pui O No. 2 Raw Water Pumping Station and Laying of Raw Water Mains along South Lantau Road
Report Date: | 2025-12-31
Start Date: | 2022-06-08 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-10-08 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-11-25 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 244696.41 | 14193.8 | 10623.4 | 15891.56 | 12132.9 | 11931.4 | 10956.5 | 10262.96 | 11550.1 | 11851.9 |  |  |  | 354090.93
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 5324.42 | 326 | 38.6 | 77 | 0 | 0 | 138.2 | 0 | 115.86 | 0 |  |  |  | 6020.08
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | -1528.4 | -1503.1 | -1380.3 | -1292.88 | -1455 | -1493 |  |  |  | -8652.68
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | -2447.37 | -141.9 | -106 | -158.92 | -121.3 | -119.3 | -109.6 | -102.63 | -115.5 | -118.5 |  |  |  | -3541.02
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 247573.46 | 14377.9 | 10556 | 15809.64 | 10483.2 | 10309 | 9604.8 | 8867.45 | 10095.46 | 10240.4 | 0 | 0 | 0 | 347917.31
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 36781 | 1104.11 | 1337.92 | 1178.1733 | 1271.43 | 1194.67 | 1171.6728 | 1183.4441 | 1191.9038 | 1132.8351 |  |  |  | 47547.1591
2.1.13 | -Manpower (HO-Consultant) | 37.75 | 0 | 9.38 | 11.527 | 6.08 | 143.51 | 102.9523 | 13.3185 | 19.57 | 69.5118 |  |  |  | 413.5996
2.1.2 | -Manpower (RE) | 4313.17 | 222.26 | 219.32 | 219.9343 | 184.54 | 210.75 | 220.5549 | 224.8569 | 214.15 | 201.5435 |  |  |  | 6231.0796
2.1.3 | -Manpower (Labour) | 3584.56 | 213.7 | 182.21 | 152.8305 | 168.96 | 157.76 | 168.3394 | 217.3633 | 221.32 | 241.3102 |  |  |  | 5308.3534
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 8263.671 | 83.485 | 87.365 | 97.771 | 91.994 | 109.518 | 55.56 | 70.102 | 78.614 | 96.587 |  |  |  | 9034.667
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 20242.5731 | 1290.9549 | 722.579 | 509.2431 | 415.4661 | 654.3694 | 1029.6473 | 371.6613 | 299.4803 | 1600.0512 |  |  |  | 27136.0257
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 252.5071 | 4.9371 | 7.1615 | 0 | 0 | 3.531 | 2.843 | 0 | 8.259 | 0.848 |  |  |  | 280.0867
2.1.8 | -DSC | 10765.0674 | 147.2 | 137.1 | 101.6 | 124.9 | 479.5618 | 550.52 | 66.16 | 131.6 | 104.6 |  |  |  | 12608.3092
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 5307.4095 | 209.3126 | 95.629 | 284.163 | 92.5358 | 1108.5364 | 186.3578 | 109.541 | 82.9988 | 323.377 |  |  |  | 7799.8608
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 4139.2105 | 282.6525 | 120.35 | 271.145 | 99.5725 | 25.0325 | 77.8625 | 7.4825 | 86.81 | 0 |  |  |  | 5110.118
2.2.2 | -Reinforcement | 2295.7324 | 244.3676 | 0 | 0 | 77.2 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2617.3
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 5197.1231 | 89.3 | 65.1324 | 31.5 | 99.065 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5482.1205
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 305.413 | 0 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 306.263
2.2.14 | -Deposit | 8284.4433 | 194.0562 | 0 | 0 | -17.674 | -757.748 | 107.184 | -420 | 0 | -184 |  |  |  | 7206.2615
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1107.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | 1109.93
2.3.2 | -Plant, Equipments & Tools (external hire) | 10499.4585 | 1051.0441 | 556.795 | 425.5473 | 420.9529 | 35.7 | 156.932 | 200.592 | 137.903 | 81.86 |  |  |  | 13566.7847
2.3.3 | -Diesel & Lubricant | 1187.1982 | 17.8645 | 55.9185 | 111.6434 | 44.7269 | 34.2079 | 55.4413 | 133.476 | 31.8671 | 25.7282 |  |  |  | 1698.072
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 61.902 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 1.2958 | 0 | 0 | 0 |  |  |  | 69.6766
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 74687.8484 | 3564.4475 | 3204.65 | 5850.28 | 3754.0657 | 2231.1741 | 4965.808 | 4738.5649 | 3038.8059 | 4239.9022 |  |  |  | 110275.5467
2.4.2 | -Variation | 19538.1471 | 589.5297 | 1521.9163 | 1880.5917 | 615.3051 | 1966.7504 | 1960.5407 | 1586.6662 | 809.7744 | 1227.5713 |  |  |  | 31696.793
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | -10161.4981 | 85.78 | 41.4251 | 1.3925 | 1.7466 | 1.3401 | 14.0438 | -89.3615 | -3.1553 | -196.7332 |  |  |  | -10305.02
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | -8015.9072 | -407.779 | -525.5759 | -942.8279 | -608.683 | -199.0119 | -437.1189 | -181.8202 | -235.9438 | -401.1696 |  |  |  | -11955.8374
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 4232.2246 | 445.1002 | 2027.1165 | 1829.586 | 1890.4127 | 38.4773 | 96.2309 | 60.4644 | 38.4773 | 1304.9297 |  |  |  | 11963.0197
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 2251.4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2251.4082
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 205158.3419 | 9433.6187 | 9868.5381 | 12015.3959 | 8733.8921 | 7439.4248 | 10486.6677 | 8292.5114 | 6152.4346 | 9870.7524 | 0 | 0 | 0 | 287451.5776
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 42415.1181 | 4944.2813 | 687.4619 | 3794.2441 | 1749.3079 | 2869.5752 | -881.8677 | 574.9386 | 3943.0254 | 369.6476 |  |  |  | 60465.7324
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -61.902 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | -1.2958 | 0 | 0 | 0 |  |  |  | -69.6766
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -2756.1141 | -177.0403 | -179.3332 | -193.9286 | -199.41 | -209.6256 | -204.4633 | -205.4939 | -220.2845 | -220.1825 |  |  |  | -4565.8759
4.3 | Total Adjustment | -2818.016 | -178.3361 | -180.6289 | -195.2243 | -200.7057 | -210.9213 | -205.7591 | -205.4939 | -220.2845 | -220.1825 | 0 | 0 | 0 | -4635.5525
5 | Gross Profit (Item 3.0-4.3) | 45233.1341 | 5122.6174 | 868.0909 | 3989.4684 | 1950.0137 | 3080.4965 | -676.1086 | 780.4325 | 4163.31 | 589.83 |  |  |  | 65101.2849
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 7267.4712 | 421.557 | 315.522 | 471.9792 | 628.992 | 618.54 | 567.996 | 532.047 | 598.776 | 614.424 |  |  |  | 12037.3044
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F |  | 37965.6629 | 42666.7233 | 43219.2922 | 46736.7814 | 48057.8031 | 50519.7596 | 49275.655 | 49524.0405 | 53088.5745
7 | Acc. Net Profit/(Loss) | 37965.6629 | 42666.7233 | 43219.2922 | 46736.7814 | 48057.8031 | 50519.7596 | 49275.655 | 49524.0405 | 53088.5745 | 53063.9805 |  |  |  | 53063.9805
(=Item5.0 - 6.0 + 6.2)