## Financial Status
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-16
Project Code: | 1062
Project Name: | Contract No. HY/2021/21 - Retrofitting of Noise Barrier on Po Lam Road North (near King Ming Court)
Report Date: | 2025-12-31
Start Date: | 2022-06-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2025-06-04 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2025-07-31 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 0 | 0 | 0 | 0 | 26122 | 26122 | 6500 | 32622 | 21004 | 0% | -21004 | 37935.7936 | 30982.1868 | 147.5% | -9978.1868
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 7090.0695 | 0% | -7090.0695
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 23211 | 23211 | -5944 | 17267 | 10322 | 0% | -10322 | 1177.07 | 3359.76 | 32.55% | 6962.24
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 5290.0655 | 0 | 0% | 0
| Total Income | 0 | 0 | 0 | 0 | 49333 | 49333 | 556 | 49889 | 31326 | 0% | -31326 | 44402.9291 | 41432.0163 | 132.3% | -10106.0163
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 0 | 0 | 0 | 0 | 12245 | 12245 | 1298 | 13543 | 13542.6053 | 0% | -13542.6053 | 13542.6053 | 13542.6053 | 100% | 0
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 25 | 25 | -2 | 23 | 22.6012 | 0% | -22.6012 | 22.6012 | 22.5992 | 99.99% | 0.00204
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 3566 | 3566 | 31 | 3597 | 3595.7678 | 0% | -3595.7678 | 3595.7678 | 3595.7678 | 100% | 0
2.1.3 | -Manpower (Labour) | 0 | 0 | 0 | 0 | 1580 | 1580 | -5.9 | 1574.1 | 1555.5233 | 0% | -1555.5233 | 1555.5233 | 1555.5233 | 100% | 0
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 0 | 0 | 0 | 0 | 1000 | 1000 | -735.2 | 264.8 | 103.072 | 0% | -103.072 | 103.072 | 75.237 | 72.99% | 27.835
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 0 | 0 | 0 | 0 | 8568 | 8568 | -558 | 8010 | 7762.7935 | 0% | -7762.7935 | 7509.1162 | 7240.8719 | 93.28% | 521.9216
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0 | 0 | 150 | 150 | -42.8 | 107.2 | 76.967 | 0% | -76.967 | 76.967 | 76.664 | 99.61% | 0.303
2.1.8 | -DSC | 0 | 0 | 0 | 0 | 1533 | 1533 | -568 | 965 | 959.404 | 0% | -959.404 | 34.404 | 34.404 | 3.586% | 925
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 100 | 100 | -21 | 79 | 78.575 | 0% | -78.575 | 70.415 | 43.965 | 55.95% | 34.61
2.1.10 | -Plant | 0 | 0 | 0 | 0 | 4500 | 4500 | -388.2 | 4111.8 | 3944.6059 | 0% | -3944.6059 | 3387.5609 | 3129.0054 | 79.32% | 815.6005
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 3407 | 3407 | 3406.2073 | 0% | -3406.2073 | 3406.2073 | 3349.4063 | 98.33% | 56.801
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 2470 | 2470 | 2469.8231 | 0% | -2469.8231 | 1652.0666 | 1652.0666 | 66.89% | 817.7565
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 2542 | 2542 | 2485.697 | 0% | -2485.697 | 2484.697 | 2484.697 | 99.96% | 1
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 0 | 0 | 733 | 733 | 732.0405 | 0% | -732.0405 | 631.0264 | 628.3055 | 85.83% | 103.735
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 552.759 | 610.517 | 0% | -610.517
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0 | 0 | 0 | 0 | 455 | 455 | 1 | 456 | 454.914 | 0% | -454.914 | 433.114 | 433.114 | 95.21% | 21.8
2.3.2 | -Plant, Equipments & Tools (external hire) | 0 | 0 | 0 | 0 | 1363 | 1363 | 720 | 2083 | 1901.003 | 0% | -1901.003 | 927.0648 | 774.4848 | 40.74% | 1126.5182
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 289 | 289 | 91.5 | 380.5 | 368.1506 | 0% | -368.1506 | 367.3687 | 342.5591 | 93.05% | 25.5916
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -558.104 | 0% | 558.104
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 0 | 0 | 0 | 0 | 35374 | 35374 | 8972.4 | 44346.4 | 43459.7505 | 0% | -43459.7505 | 40352.3365 | 39033.689 | 89.82% | 4426.0615
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 0 | 0 | 0 | 0 | 13959 | 13959 | -8416.4 | 5542.6 | -12133.7505 | 0% | 12133.7505 | 4050.5927 | 2398.3273 | -19.77% | -14532.0778
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | 0 |  |  | 0 | 0 | 0% |  | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | 0 |  |  | 0 | 0 | 0% |  | 0 | 0 | 0% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | 0 |  |  | -837.2644 | -837.2644 | 0% | 837.2644 | -837.2644 | -837.2644 | 100% | -1.8448e-08
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | 0 |  |  | -837.2644 | -837.2644 | 0% | 837.2644 | -837.2644 | -837.2644 | 100% | -1.8448e-08
5 | Gross Profit (Item 3.0-4.3) | 0 | 0 | 0 | 0 | 13959 |  |  | 6379.8644 | -11296.4861 | 0% | 11296.4861 | 4887.8571 | 3235.5917 | -28.64% | -14532.0778
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 2959.98 |  |  | 1691.67 | 939.78 | 0% | -939.78 | 1422.4724 | 1363.0805 | 145% | -423.3005
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 0 | 0 | 0 | 0 | 10999.02 |  |  | 4688.1944 | -12236.2661 | 0% | 12236.2661 | 3465.3847 | 1872.5112 | -15.3% | -14108.7773
(=Item5.0 - 6.0 + 6.2)

## Projection
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-16
Project Code: | 1062
Project Name: | Contract No. HY/2021/21 - Retrofitting of Noise Barrier on Po Lam Road North (near King Ming Court)
Report Date: | 2025-12-31
Start Date: | 2022-06-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2025-06-04 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2025-07-31 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 26122 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 |  |  |  | 32622
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 10322 | 6945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 17267
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 36444 | 6945 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49889
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 10050 | 1424 | 0 | 242 | 214 | 367 | 7 | 610 | 350 | 279 |  |  |  | 13543
2.1.13 | -Manpower (HO-Consultant) | 9 | 11 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 |  |  |  | 23
2.1.2 | -Manpower (RE) | 2481 | 146 | 151 | 141 | 146 | 108 | 394 | 0 | 0 | 30 |  |  |  | 3597
2.1.3 | -Manpower (Labour) | 1236.1 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1574.1
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 56.8 | 0 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 264.8
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 6783 | 1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8010
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 107.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 107.2
2.1.8 | -DSC | 965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 965
2.1.9 | -General Material | 17 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 79
2.1.10 | -Plant | 3989.8 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4111.8
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 1911 | 676 | 330 | 172 | 158 | 0 | 22 | 44 | 70 | 24 |  |  |  | 3407
2.2.2 | -Reinforcement | 1314 | 1030 | 125 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2470
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 2542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2542
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 592 | 0 | 135 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  |  |  | 733
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 456
2.3.2 | -Plant, Equipments & Tools (external hire) | 1209 | 195 | 30 | 0 | 4 | 103 | 92 | 110 | 130 | 210 |  |  |  | 2083
2.3.3 | -Diesel & Lubricant | 271.5 | 14 | 15 | 4 | 8 | 26 | 0 | 10 | 30 | 2 |  |  |  | 380.5
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 33990.4 | 5245 | 786 | 767 | 531 | 604 | 522 | 774 | 580 | 547 | 0 | 0 | 0 | 44346.4
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 2453.6 | 1700 | -786 | -767 | 5969 | -604 | -522 | -774 | -580 | -547 |  |  |  | 5542.6
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -738.2108 | -14.7715 | -13.5582 | -10.8302 | -12.3223 | -12.5495 | -10.1405 | -8.2573 | -8.8544 | -7.7698 |  |  |  | -837.2644
4.3 | Total Adjustment | -738.2108 | -14.7715 | -13.5582 | -10.8302 | -12.3223 | -12.5495 | -10.1405 | -8.2573 | -8.8544 | -7.7698 | 0 | 0 | 0 | -837.2644
5 | Gross Profit (Item 3.0-4.3) | 3191.8108 | 1714.7715 | -772.4418 | -756.1698 | 5981.3223 | -591.4505 | -511.8595 | -765.7427 | -571.1456 | -539.2302 |  |  |  | 6379.8644
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 1093.32 | 208.35 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1691.67
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 2098.4908 | 1506.4215 | -772.4418 | -756.1698 | 5591.3223 | -591.4505 | -511.8595 | -765.7427 | -571.1456 | -539.2302 |  |  |  | 4688.1944
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-16
Project Code: | 1062
Project Name: | Contract No. HY/2021/21 - Retrofitting of Noise Barrier on Po Lam Road North (near King Ming Court)
Report Date: | 2025-12-31
Start Date: | 2022-06-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2025-06-04 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2025-07-31 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 21004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 21004
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 10322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10322
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 31326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31326
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 10049.15 | 713.11 | 566.4 | 386.6 | 214.5 | 366.88 | 292.3223 | 319.523 | 317.1 | 317.02 |  |  |  | 13542.6053
2.1.13 | -Manpower (HO-Consultant) | 8.05 | 2.61 | 4.14 | 2 | 0 | 0 | 3.6612 | 0 | 0 | 2.14 |  |  |  | 22.6012
2.1.2 | -Manpower (RE) | 2480.99 | 145.02 | 151 | 141.23 | 146.32 | 108.03 | 105.8028 | 105.725 | 105.92 | 105.73 |  |  |  | 3595.7678
2.1.3 | -Manpower (Labour) | 1235.22 | 43 | 35 | 32.75 | 35.38 | 34 | 36.95 | 35.3833 | 32.75 | 35.09 |  |  |  | 1555.5233
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 56.511 | 18.726 | 0 | 0 | 0 | 0 | 0 | 0 | 27.835 | 0 |  |  |  | 103.072
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 6864.8237 | 181.5639 | 158.0673 | 91.4732 | 22.5531 | 81.3806 | 101.8052 | 172.4312 | 75.1729 | 13.5225 |  |  |  | 7762.7935
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 72.3739 | 0.653 | 1.367 | 0.333 | 2.2401 | 0 | 0 | 0 | 0 | 0 |  |  |  | 76.967
2.1.8 | -DSC | 959.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 959.404
2.1.9 | -General Material | 16.145 | 0 | 35.98 | 0 | 0 | 0 | 0 | 0 | 0 | 26.45 |  |  |  | 78.575
2.1.10 | -Plant | 3893.5569 | 3.972 | 4.9405 | 12.4435 | 2.754 | 6.061 | 1.956 | 6.576 | 8.226 | 4.12 |  |  |  | 3944.6059
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 1910.6297 | 0 | 522.9752 | 554.9596 | 245.1836 | 13.0825 | 0 | 21.3075 | 44.603 | 93.4662 |  |  |  | 3406.2073
2.2.2 | -Reinforcement | 1347.8646 | 960.3127 | 161.6458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2469.8231
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 2485.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2485.697
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 591.4155 | 0 | 0 | 132 | 0 | 0 | 8.625 | 0 | 0 | 0 |  |  |  | 732.0405
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 454.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 454.914
2.3.2 | -Plant, Equipments & Tools (external hire) | 1209.383 | 24.161 | 132.449 | 71.61 | 3.3 | 30.25 | 75.9 | 99.2 | 91 | 163.75 |  |  |  | 1901.003
2.3.3 | -Diesel & Lubricant | 270.8058 | 10.6138 | 7.5153 | 7.4375 | 8.9249 | 6.3495 | 16.5458 | 15.1483 | 0 | 24.8097 |  |  |  | 368.1506
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 33906.934 | 2103.7424 | 1781.4801 | 1432.8368 | 681.1558 | 646.0336 | 643.5682 | 775.2943 | 702.6069 | 786.0983 | 0 | 0 | 0 | 43459.7505
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -2580.934 | -2103.7424 | -1781.4801 | -1432.8368 | -681.1558 | -646.0336 | -643.5682 | -775.2943 | -702.6069 | -786.0983 |  |  |  | -12133.7505
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -738.2108 | -14.7715 | -13.5582 | -10.8302 | -12.3223 | -12.5495 | -10.1405 | -8.2573 | -8.8544 | -7.7698 |  |  |  | -837.2644
4.3 | Total Adjustment | -738.2108 | -14.7715 | -13.5582 | -10.8302 | -12.3223 | -12.5495 | -10.1405 | -8.2573 | -8.8544 | -7.7698 | 0 | 0 | 0 | -837.2644
5 | Gross Profit (Item 3.0-4.3) | -1842.7232 | -2088.9709 | -1767.9219 | -1422.0066 | -668.8335 | -633.4841 | -633.4278 | -767.037 | -693.7526 | -778.3286 |  |  |  | -11296.4861
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 939.78
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -2782.5032 | -2088.9709 | -1767.9219 | -1422.0066 | -668.8335 | -633.4841 | -633.4278 | -767.037 | -693.7526 | -778.3286 |  |  |  | -12236.2661
(=Item5.0 - 6.0 + 6.2)

## Accrual
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-16
Project Code: | 1062
Project Name: | Contract No. HY/2021/21 - Retrofitting of Noise Barrier on Po Lam Road North (near King Ming Court)
Report Date: | 2025-12-31
Start Date: | 2022-06-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2025-06-04 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2025-07-31 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 28512.0415 | 3410.9342 | 0 | 0 | 558.104 | 0 | 2403.7139 | 0 | 0 | 3051 |  |  |  | 37935.7936
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 1177.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1177.07
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 8290.0655 | 0 | 0 | 0 | -1500 | -1500 | 0 | 0 | 0 | 0 |  |  |  | 5290.0655
| Total Income | 37979.177 | 3410.9342 | 0 | 0 | -941.896 | -1500 | 2403.7139 | 0 | 0 | 3051 | 0 | 0 | 0 | 44402.9291
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 10049.15 | 713.11 | 566.4 | 386.6 | 214.5 | 366.88 | 292.3223 | 319.523 | 317.1 | 317.02 |  |  |  | 13542.6053
2.1.13 | -Manpower (HO-Consultant) | 8.05 | 2.61 | 4.14 | 2 | 0 | 0 | 3.6612 | 0 | 0 | 2.14 |  |  |  | 22.6012
2.1.2 | -Manpower (RE) | 2480.99 | 145.02 | 151 | 141.23 | 146.32 | 108.03 | 105.8028 | 105.725 | 105.92 | 105.73 |  |  |  | 3595.7678
2.1.3 | -Manpower (Labour) | 1235.22 | 43 | 35 | 32.75 | 35.38 | 34 | 36.95 | 35.3833 | 32.75 | 35.09 |  |  |  | 1555.5233
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 56.511 | 18.726 | 0 | 0 | 0 | 0 | 0 | 0 | 27.835 | 0 |  |  |  | 103.072
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 5979.7074 | 762.4339 | 235.4413 | 159.8782 | 37.5931 | 8.8006 | 40.2352 | 195.6812 | 77.3229 | 12.0225 |  |  |  | 7509.1162
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 72.3739 | 0.653 | 1.367 | 0.333 | 2.2401 | 0 | 0 | 0 | 0 | 0 |  |  |  | 76.967
2.1.8 | -DSC | 34.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 34.404
2.1.9 | -General Material | 16.145 | 27.82 | 0 | 0 | 0 | 0 | 0 | 0 | 26.45 | 0 |  |  |  | 70.415
2.1.10 | -Plant | 2662.9939 | 586.446 | 124.1005 | 12.4435 | -13.506 | 3.9 | 0 | 10.157 | 1.026 | 0 |  |  |  | 3387.5609
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 1910.6297 | 1001.752 | 76.1828 | 245.1836 | 13.0825 | 0 | 0 | 147.7322 | 11.6445 | 0 |  |  |  | 3406.2073
2.2.2 | -Reinforcement | 883.7908 | 646.8702 | 121.4056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1652.0666
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 2484.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2484.697
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 549.4055 | 3 | 0 | 75.9 | 0 | 0 | 0 | 2.7209 | 0 | 0 |  |  |  | 631.0264
2.2.14 | -Deposit | 750.953 | 22.89 | -197.584 | 58.8 | -138.4 | 0 | 0 | 0 | 0 | 56.1 |  |  |  | 552.759
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 433.114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 433.114
2.3.2 | -Plant, Equipments & Tools (external hire) | 585.9698 | 95.326 | 99.839 | 6.5 | 6.5 | 0 | 0 | 126.43 | 6.5 | 0 |  |  |  | 927.0648
2.3.3 | -Diesel & Lubricant | 265.9775 | 18.3474 | 7.4507 | 11.7166 | 11.9739 | 11.9446 | 0 | 23.7733 | 16.1847 | 0 |  |  |  | 367.3687
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | -558.104 | 0 | 558.104 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 30460.0825 | 4088.0045 | 1224.7428 | 1133.3349 | 315.6837 | -24.5488 | 478.9715 | 1525.2298 | 622.7331 | 528.1025 | 0 | 0 | 0 | 40352.3365
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 7519.0946 | -677.0703 | -1224.7428 | -1133.3349 | -1257.5796 | -1475.4512 | 1924.7425 | -1525.2298 | -622.7331 | 2522.8975 |  |  |  | 4050.5927
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -738.2108 | -14.7715 | -13.5582 | -10.8302 | -12.3223 | -12.5495 | -10.1405 | -8.2573 | -8.8544 | -7.7698 |  |  |  | -837.2644
4.3 | Total Adjustment | -738.2108 | -14.7715 | -13.5582 | -10.8302 | -12.3223 | -12.5495 | -10.1405 | -8.2573 | -8.8544 | -7.7698 | 0 | 0 | 0 | -837.2644
5 | Gross Profit (Item 3.0-4.3) | 8257.3053 | -662.2988 | -1211.1846 | -1122.5047 | -1245.2574 | -1462.9017 | 1934.8829 | -1516.9726 | -613.8787 | 2530.6673 |  |  |  | 4887.8571
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 1139.3753 | 102.328 | 0 | 0 | -56.5138 | -90 | 144.2228 | 0 | 0 | 183.06 |  |  |  | 1422.4724
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 7117.93 | -764.6268 | -1211.1846 | -1122.5047 | -1188.7436 | -1372.9017 | 1790.6601 | -1516.9726 | -613.8787 | 2347.6073 |  |  |  | 3465.3847
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-16
Project Code: | 1062
Project Name: | Contract No. HY/2021/21 - Retrofitting of Noise Barrier on Po Lam Road North (near King Ming Court)
Report Date: | 2025-12-31
Start Date: | 2022-06-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2025-06-04 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2025-07-31 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 22410.7788 | 2000 | 1567.408 | 1000 | 2000 | 0 | 0 | 604 | 1000 | 400 |  |  |  | 30982.1868
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 7090.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7090.0695
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 3359.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3359.76
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 32860.6084 | 2000 | 1567.408 | 1000 | 2000 | 0 | 0 | 604 | 1000 | 400 | 0 | 0 | 0 | 41432.0163
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 10049.15 | 713.11 | 566.4 | 386.6 | 214.5 | 366.88 | 292.3223 | 319.523 | 317.1 | 317.02 |  |  |  | 13542.6053
2.1.13 | -Manpower (HO-Consultant) | 8.05 | 2.61 | 4.14 | 2 | 0 | -0.00204 | 3.6612 | 0 | 0 | 2.14 |  |  |  | 22.5992
2.1.2 | -Manpower (RE) | 2480.99 | 145.02 | 151 | 141.23 | 146.32 | 108.03 | 105.8028 | 105.725 | 105.92 | 105.73 |  |  |  | 3595.7678
2.1.3 | -Manpower (Labour) | 1235.22 | 43 | 35 | 32.75 | 35.38 | 34 | 36.95 | 35.3833 | 32.75 | 35.09 |  |  |  | 1555.5233
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 28.703 | 27.808 | 0 | 0 | 0 | 0 | 0 | 18.726 | 0 | 0 |  |  |  | 75.237
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 5329.6263 | 368.3713 | 447.9989 | 205.9101 | 541.86 | 3.0829 | 21.4209 | 134.7608 | 122.9628 | 64.8778 |  |  |  | 7240.8719
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 61.3089 | 7.855 | 2.907 | 2.02 | 0.333 | 0 | 0 | 0 | 2.2401 | 0 |  |  |  | 76.664
2.1.8 | -DSC | 34.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 34.404
2.1.9 | -General Material | 0 | 16.145 | 0 | 0 | 27.82 | 0 | 0 | 0 | 0 | 0 |  |  |  | 43.965
2.1.10 | -Plant | 2443.6499 | 108.081 | 178.401 | 80.0835 | 306.36 | 3.9 | 0 | 5.396 | 3.134 | 0 |  |  |  | 3129.0054
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 1827.218 | 83.4117 | 176.8761 | 558.104 | 176.4899 | 0 | 99.3121 | 244.0043 | 121.38 | 62.6102 |  |  |  | 3349.4063
2.2.2 | -Reinforcement | 883.7908 | 0 | 364.3694 | 109.7756 | 172.7251 | 0 | 0 | 55.8169 | 65.5887 | 0 |  |  |  | 1652.0666
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 2484.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2484.697
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 540.7655 | 8.64 | 0 | 3 | 0 | 0 | 0 | 75.9 | 0 | 0 |  |  |  | 628.3055
2.2.14 | -Deposit | 808.711 | 22.89 | -197.584 | 58.8 | -138.4 | 0 | 0 | 0 | 0 | 56.1 |  |  |  | 610.517
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 433.114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 433.114
2.3.2 | -Plant, Equipments & Tools (external hire) | 455.9068 | 89.613 | 86.1 | 50.561 | 49.344 | 0 | 10.9 | 11.28 | 20.78 | 0 |  |  |  | 774.4848
2.3.3 | -Diesel & Lubricant | 257.5116 | 8.4658 | 10.7352 | 7.4507 | 0 | 0 | 20.3521 | 23.3485 | 13.1017 | 1.5934 |  |  |  | 342.5591
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | -558.104 | 0 | 0 | 0 | 0 |  |  |  | -558.104
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 29362.8168 | 1645.0209 | 1826.3436 | 1638.2849 | 1532.732 | -42.2131 | 590.7214 | 1029.8638 | 804.9573 | 645.1614 | 0 | 0 | 0 | 39033.689
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 3497.7915 | 354.9791 | -258.9357 | -638.2849 | 467.268 | 42.2131 | -590.7214 | -425.8638 | 195.0427 | -245.1614 |  |  |  | 2398.3273
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -738.2108 | -14.7715 | -13.5582 | -10.8302 | -12.3223 | -12.5495 | -10.1405 | -8.2573 | -8.8544 | -7.7698 |  |  |  | -837.2644
4.3 | Total Adjustment | -738.2108 | -14.7715 | -13.5582 | -10.8302 | -12.3223 | -12.5495 | -10.1405 | -8.2573 | -8.8544 | -7.7698 | 0 | 0 | 0 | -837.2644
5 | Gross Profit (Item 3.0-4.3) | 4236.0023 | 369.7506 | -245.3774 | -627.4547 | 479.5903 | 54.7627 | -580.581 | -417.6065 | 203.8971 | -237.3916 |  |  |  | 3235.5917
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 985.8183 | 60 | 47.0222 | 30 | 120 | 0 | 0 | 36.24 | 60 | 24 |  |  |  | 1363.0805
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F |  | 3250.1841 | 3559.9347 | 3267.535 | 2610.0803 | 2969.6706 | 3024.4333 | 2443.8523 | 1990.0058 | 2133.9029
7 | Acc. Net Profit/(Loss) | 3250.1841 | 3559.9347 | 3267.535 | 2610.0803 | 2969.6706 | 3024.4333 | 2443.8523 | 1990.0058 | 2133.9029 | 1872.5112 |  |  |  | 1872.5112
(=Item5.0 - 6.0 + 6.2)