## Financial Status
CW-KL JV
Print Date: 2026-01-20
Project Code: | 1069
Project Name: | Contract No. DC/2022/01 - Drainage Improvement Works in Tsim Sha Tsui
Report Date: | 2025-12-31
Start Date: | 2022-08-19 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-11-10 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2026-11-10 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 520000 | 520000 | 0 | 520000 | 520000 | 520000 | 0 | 520000 | 520000 | 100% | 0 | 564653.968 | 553959.6969 | 106.5% | -33959.6969
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 18000 | 18500 | 0 | 18500 | 239757 | 125200 | 0 | 125200 | 133700.907 | 722.7% | -115200.907 | 0 | 0 | 0% | 133700.907
1.2.2 | -Fee of C.E. | 0 | 4625 | 0 | 4625 | 71726 | 31300 | 0 | 31300 | 0 | 0% | 4625 | 0 | 0 | 0% | 0
1.3 | Provisional Sum | 6356 | 6356 | 0 | 6356 | 6281 | 6281 | 0 | 6281 | 2447.84 | 38.51% | 3908.16 | 2537.44 | 0 | 0% | 2447.84
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | -750.8 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 66649 | 66649 | 0 | 66649 | 9202 | 6456 | 0 | 6456 | 0 | 0% | 66649 | 0 | 0 | 0% | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 212162 | 0 | 212162 | 0 | 0% | 0 | 0 | 0.01667 | 0% | -0.01667
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 16 | 0 | 0% | 0
1.12.2 | -Pain Gain Sharing | 24752 | 30806 | 0 | 30806 | 42034 | 33825 | 0 | 33825 | 0 | 0% | 30806 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5397.3938 | 0% | 5397.3938
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Income | 635757 | 646936 | 0 | 646936 | 889000 | 935224 | 0 | 935224 | 656148.747 | 101.4% | -9212.747 | 566456.608 | 548562.3198 | 83.6% | 107586.4272
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 48601.3772 | 56839.433 | 0 | 56839.433 | 74217 | 74217 | 0 | 74217 | 62582.353 | 110.1% | -5742.92 | 62582.353 | 62582.3498 | 100% | 0.0032
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 1924 | 1924 | 0 | 1924 | 1648.366 | 0% | -1648.366 | 1648.366 | 1648.366 | 100% | 0
2.1.2 | -Manpower (RE) | 4395 | 4395 | 0 | 4395 | 3815 | 3815 | 0 | 3815 | 3086.5912 | 70.23% | 1308.4088 | 3086.5912 | 3086.5987 | 100% | -0.0075
2.1.3 | -Manpower (Labour) | 2204.82 | 10544.707 | 0 | 10544.707 | 13759 | 13759 | 0 | 13759 | 9881.9214 | 93.71% | 662.7857 | 9882.3826 | 9882.4193 | 100% | -0.4979
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 15146.568 | 15146.568 | 0 | 15146.568 | 16133 | 15633 | 0 | 15633 | 14152.356 | 93.44% | 994.212 | 14152.356 | 14152.356 | 100% | 0
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 30792.2939 | 25017.8021 | 0 | 25017.8021 | 47407 | 47552 | 4743 | 52295 | 47878.3433 | 191.4% | -22860.5411 | 41867.0509 | 39490.143 | 82.48% | 8388.2003
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 1.2 | 0% | -1.2 | 1.2 | 1.2 | 100% | 0
2.1.7 | -Adm. Cost Messing | 298.83 | 298.83 | 0 | 298.83 | 625 | 625 | 0 | 625 | 529.7698 | 177.3% | -230.9398 | 236.4298 | 236.4298 | 44.63% | 293.34
2.1.8 | -DSC | 17730.228 | 27686.073 | 0 | 27686.073 | 31064 | 32414 | 0 | 32414 | 32056.31 | 115.8% | -4370.237 | 23369.41 | 21917.83 | 68.37% | 10138.48
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 2273.316 | 2273.316 | 0 | 2273.316 | 16115 | 14615 | 0 | 14615 | 13526.4011 | 595% | -11253.0851 | 10838.7009 | 8966.9542 | 66.29% | 4559.4469
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 2550 | 3550 | 0 | 3550 | 2865.334 | 0% | -2865.334 | 2708.754 | 2701.884 | 94.3% | 163.45
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 624 | 2752 | 0 | 2752 | 2290.7779 | 0% | -2290.7779 | 1934.6447 | 1934.6447 | 84.45% | 356.1332
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 9648 | 16673 | 0 | 16673 | 12992.068 | 0% | -12992.068 | 8353.1329 | 7596.7022 | 58.47% | 5395.3658
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 692 | 692 | 0 | 692 | 659.7627 | 0% | -659.7627 | 536.7201 | 435.689 | 66.04% | 224.0737
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 1966.6895 | 1740.5251 | 0% | -1740.5251
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | -7183 | 0 | -7183 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1182.3347 | 1182.3347 | 0 | 1182.3347 | 1500 | 1480 | 0 | 1480 | 1473.058 | 124.6% | -290.7233 | 1473.058 | 1473.058 | 100% | 0
2.3.2 | -Plant, Equipments & Tools (external hire) | 2802 | 2802 | 0 | 2802 | 6316 | 8016 | 0 | 8016 | 7346.1044 | 262.2% | -4544.1044 | 4404.6044 | 3888.5594 | 52.93% | 3457.545
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 198 | 353 | 0 | 353 | 322.2787 | 0% | -322.2787 | 297.563 | 297.563 | 92.33% | 24.7157
2.3.4 | -Repairing | 92 | 92 | 0 | 92 | 138 | 138 | 0 | 138 | 137.7688 | 149.7% | -45.7688 | 137.7688 | 137.7688 | 100% | 0
2.3.5 | -Resale | -131.0139 | -131.0139 | 0 | -131.0139 | 0 | 0 | 0 | 0 | 0 | -0% | -131.0139 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 90 | 90 | 0 | 90 | 47.07 | 0% | -47.07 | 47.07 | 47.07 | 100% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | -2304 | -2604 | 0 | -2604 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 516454.3024 | 506179.3339 | 0 | 506179.3339 | 677075 | 660475 | -18233 | 642242 | 493093.6098 | 97.41% | 13085.7241 | 216793.2468 | 211226.8496 | 42.84% | 281866.7602
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 28288 | 34888 | 13490 | 48378 | 47904.7193 | 0% | -47904.7193 | 31478.9722 | 29360.7816 | 61.29% | 18543.9377
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 45654 | 0 | 45654 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 1205.8676 | 1739.8791 | 0% | -1739.8791
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -13623.5153 | 0% | 13623.5153
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -82588 | -82588 | 0 | -82588 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 255.609 | 0% | -255.609 | 255.609 | 255.609 | 100% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 6800 | 11800 | 0 | 11800 | 10522.9141 | 0% | -10522.9141 | 10522.9141 | 10522.9126 | 100% | 0.0015
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | -32290.175 | -49395.9172 | 0 | -49395.9172 | 0 | 0 | 0 | 0 | 0 | -0% | -49395.9172 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 5940 | 5940 | 0 | 5940 | 5940 | 5940 | 0 | 5940 | 5939.9388 | 100% | 0.06124 | 5939.9388 | 5939.9388 | 100% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 615491.8814 | 608870.4667 | 0 | 608870.4667 | 860028 | 905682 | 0 | 905682 | 771194.6252 | 126.7% | -162324.1584 | 455721.3943 | 427640.5663 | 55.45% | 343554.0588
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 20265.1186 | 38065.5333 | 0 | 38065.5333 | 28972 | 29542 | 0 | 29542 | -115045.8782 | -302.2% | 153111.4115 | 110735.2137 | 120921.7535 | -105.1% | -235967.6316
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | -2 |  |  | -2 | -1.2 | 0% |  | -1.2 | -1.2 | 100% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | -90 |  |  | -90 | -47.07 | 0% |  | -47.07 | -47.07 | 100% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | 0 |  |  | -8635.5356 | -8635.5356 | 0% | 8635.5356 | -8635.5356 | -8635.5356 | 100% | -3.6616e-09
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | -92 |  |  | -8727.5356 | -8683.8056 | 0% | 8683.8056 | -8683.8056 | -8683.8056 | 100% | -3.6616e-09
5 | Gross Profit (Item 3.0-4.3) | 20265.1186 | 38065.5333 | 0 | 38065.5333 | 29064 |  |  | 38269.5356 | -106362.0726 | -279.4% | 144427.6058 | 119419.0193 | 129605.5591 | -121.9% | -235967.6316
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 37764.06 | 38434.8 | 0 | 38434.8 | 52963.14 |  |  | 29255.01 | 20013.4772 | 52.07% | 18421.3228 | 20703.281 | 20167.7591 | 100.8% | -154.2819
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -17498.9414 | -369.2667 | 0 | -369.2667 | -23899.14 |  |  | 9014.5256 | -126375.5498 | 34223% | 126006.2831 | 98715.7383 | 109437.8 | -86.6% | -235813.3498
(=Item5.0 - 6.0 + 6.2)

## Projection
CW-KL JV
Print Date: 2026-01-20
Project Code: | 1069
Project Name: | Contract No. DC/2022/01 - Drainage Improvement Works in Tsim Sha Tsui
Report Date: | 2025-12-31
Start Date: | 2022-08-19 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-11-10 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-11-10 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 520000
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 239165 | 592 | 0 | 0 | 0 | 4480 | -4480 | -114557 | 0 | 0 |  |  |  | 125200
1.2.2 | -Fee of C.E. | 71541 | 185 | 0 | 0 | 0 | 1120 | -1120 | -40426 | 0 | 0 |  |  |  | 31300
1.3 | Provisional Sum | 7097 | -741 | -75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6281
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 9202 | 0 | 0 | 0 | 0 | -2746 | 2746 | -2746 | 0 | 0 |  |  |  | 6456
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212162 | 0 | 0 |  |  |  | 212162
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 41995 | 39 | 0 | 0 | 0 | 0 | 0 | -8209 | 0 | 0 |  |  |  | 33825
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 889000 | 75 | -75 | 0 | 0 | 2854 | -2854 | 46224 | 0 | 0 | 0 | 0 | 0 | 935224
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 71271 | 0 | 0 | 2946 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 74217
2.1.13 | -Manpower (HO-Consultant) | 1924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1924
2.1.2 | -Manpower (RE) | 5598 | 0 | 0 | -1783 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3815
2.1.3 | -Manpower (Labour) | 14647 | 0 | 0 | -888 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13759
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 16141 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | -500 | 0 |  |  |  | 15633
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 37629 | 9778 | 0 | 0 | 0 | -355 | 0 | 0 | 500 | 4743 |  |  |  | 52295
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2
2.1.7 | -Adm. Cost Messing | 225 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 625
2.1.8 | -DSC | 31064 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 1000 | 0 |  |  |  | 32414
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 17115 | -1000 | 0 | 0 | -1000 | 0 | 0 | -500 | 0 | 0 |  |  |  | 14615
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 2550 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 |  |  |  | 3550
2.2.2 | -Reinforcement | 624 | 0 | 158 | 1470 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2752
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 17072 | -241 | -158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16673
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 692
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | -7183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -7183
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1500 | 0 | 0 | 0 | 0 | 0 | -20 | 0 | 0 | 0 |  |  |  | 1480
2.3.2 | -Plant, Equipments & Tools (external hire) | 4816 | 1000 | 500 | 300 | 1000 | 0 | 0 | 450 | -50 | 0 |  |  |  | 8016
2.3.3 | -Diesel & Lubricant | 168 | 0 | 30 | 0 | 30 | 5 | 20 | 50 | 50 | 0 |  |  |  | 353
2.3.4 | -Repairing | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 138
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 90
2.3.8 | -Potential Savings (Plants) | -1424 | 0 | -605 | -575 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -2604
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 675674 | 2401 | -1000 | -1470 | -2830 | -1200 | -8100 | 0 | -3000 | -18233 |  |  |  | 642242
2.4.2 | -Variation | 24388 | 3900 | 0 | 0 | 300 | 5300 | 0 | 0 | 1000 | 13490 |  |  |  | 48378
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45654 | 0 | 0 |  |  |  | 45654
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | -72762 | -9826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -82588
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 |  |  |  | 1000
2.5 | Manpower (Labour) for Works | 5800 | 0 | 1000 | 0 | 2000 | 0 | 3000 | 0 | 0 | 0 |  |  |  | 11800
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 5940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5940
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 860882 | -779 | -75 | 0 | 0 | 4100 | -4100 | 45654 | 0 | 0 | 0 | 0 | 0 | 905682
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 28118 | 854 | 0 | 0 | 0 | -1246 | 1246 | 570 | 0 | 0 |  |  |  | 29542
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -2
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -90
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -4930.9435 | -358.5613 | -368.2844 | -389.4513 | -399.6396 | -423.4506 | -425.9379 | -435.039 | -450.1292 | -454.0988 |  |  |  | -8635.5356
4.3 | Total Adjustment | -5022.9435 | -358.5613 | -368.2844 | -389.4513 | -399.6396 | -423.4506 | -425.9379 | -435.039 | -450.1292 | -454.0988 | 0 | 0 | 0 | -8727.5356
5 | Gross Profit (Item 3.0-4.3) | 33140.9435 | 1212.5613 | 368.2844 | 389.4513 | 399.6396 | -822.5494 | 1671.9379 | 1005.039 | 450.1292 | 454.0988 |  |  |  | 38269.5356
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 26457.09 | 24.48 | 0 | 0 | 0 | 171.24 | -171.24 | 2773.44 | 0 | 0 |  |  |  | 29255.01
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 6683.8535 | 1188.0813 | 368.2844 | 389.4513 | 399.6396 | -993.7894 | 1843.1779 | -1768.401 | 450.1292 | 454.0988 |  |  |  | 9014.5256
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
CW-KL JV
Print Date: 2026-01-20
Project Code: | 1069
Project Name: | Contract No. DC/2022/01 - Drainage Improvement Works in Tsim Sha Tsui
Report Date: | 2025-12-31
Start Date: | 2022-08-19 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-11-10 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-11-10 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 520000
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 116284.907 | 2887 | 0 | 1114 | 673 | 2879 | 2647 | 4763 | 2453 | 0 |  |  |  | 133700.907
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 2075.84 | 97 | 33 | 0 | 145 | 32 | 33 | 32 | 0 | 0 |  |  |  | 2447.84
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 638360.747 | 2984 | 33 | 1114 | 818 | 2911 | 2680 | 4795 | 2453 | 0 | 0 | 0 | 0 | 656148.747
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 48306.0322 | 1515.17 | 1690.9108 | 1486.9152 | 1492.6812 | 1574.6665 | 1565.4596 | 1609.663 | 1517.2176 | 1823.6369 |  |  |  | 62582.353
2.1.13 | -Manpower (HO-Consultant) | 1212.76 | 22.58 | 46.2006 | 55.494 | 53.8447 | 58.8254 | 90.7553 | 45.7871 | -77.2811 | 139.4 |  |  |  | 1648.366
2.1.2 | -Manpower (RE) | 1983.5877 | 95.63 | 108.7791 | 142.0101 | 117.7894 | 126.082 | 125.7492 | 117.77 | 137.1037 | 132.09 |  |  |  | 3086.5912
2.1.3 | -Manpower (Labour) | 6225.2644 | 333.17 | 335.0202 | 364.9512 | 400.2488 | 372.9771 | 447.6 | 472.1585 | 438.5697 | 491.9614 |  |  |  | 9881.9214
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 12821.904 | 293.319 | 0 | 124.082 | 232.26 | 0 | 109.774 | 91.785 | 124.17 | 355.062 |  |  |  | 14152.356
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 36035.7636 | 1233.7987 | 2465.8039 | 981.9385 | 1985.1624 | 829.2213 | 840.769 | 1910.6346 | 761.3557 | 833.8956 |  |  |  | 47878.3433
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1.2
2.1.7 | -Adm. Cost Messing | 170.4238 | 282.578 | 26.655 | 27.9426 | 3.291 | 2.558 | 6.568 | -3.3426 | 7.509 | 5.587 |  |  |  | 529.7698
2.1.8 | -DSC | 30808.31 | 208 | 0 | 0 | 0 | 0 | 396 | 640 | 2 | 2 |  |  |  | 32056.31
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 11544.7392 | 49.3025 | 92.6009 | 139.495 | 461.6698 | 90.1124 | 397.0778 | 261.1939 | 108.1194 | 382.0902 |  |  |  | 13526.4011
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 2312.8405 | 0 | 6.63 | 0 | 41.893 | 73.865 | 100.818 | 50.2525 | 122.655 | 156.38 |  |  |  | 2865.334
2.2.2 | -Reinforcement | 610.3253 | 1.2 | 1.2 | 0 | 1555.0983 | 189.5 | 0 | -66.5457 | 0 | 0 |  |  |  | 2290.7779
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 7347.5334 | 176.7418 | 962.0494 | 202.001 | 737.2106 | 2.7928 | 1289.8144 | -25.3954 | 1518.0894 | 781.2307 |  |  |  | 12992.068
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 540.8577 | 0 | 8.8 | 52.225 | 17.82 | 0 | 40.06 | 0 | 0 | 0 |  |  |  | 659.7627
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1473.058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1473.058
2.3.2 | -Plant, Equipments & Tools (external hire) | 3846.3504 | 299.006 | 821.75 | 331.5 | 551.448 | 414.8 | 127.5 | 407 | 275.25 | 271.5 |  |  |  | 7346.1044
2.3.3 | -Diesel & Lubricant | 153.0441 | 3.3912 | 33.4337 | 3.9951 | 16.5047 | 12.5405 | 5.722 | 36.0224 | 32.9094 | 24.7157 |  |  |  | 322.2787
2.3.4 | -Repairing | 137.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 137.7688
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 41.1953 | 0.97911 | 0.97912 | 0.97911 | 0.97911 | 0.97912 | 0.97911 | 0 | 0 | 0 |  |  |  | 47.07
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 376980.5158 | -38 | 830.725 | 0 | 100435.918 | 7728.05 | 0 | 4445.991 | 0 | 2710.41 |  |  |  | 493093.6098
2.4.2 | -Variation | 47774.2193 | 2.5 | 98.5 | 0 | 0 | 0 | 29.5 | 0 | 0 | 0 |  |  |  | 47904.7193
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.609 | 0 | 0 |  |  |  | 255.609
2.5 | Manpower (Labour) for Works | 5290.0835 | 189.02 | 418.3824 | 654.802 | 798.454 | 741.7951 | 638.2621 | 594.7951 | 579.0479 | 618.272 |  |  |  | 10522.9141
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 5939.9388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5939.9388
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 601557.7158 | 4668.3864 | 7948.4201 | 4568.3308 | 108902.273 | 12218.7652 | 6212.4085 | 10843.3784 | 5546.7156 | 8728.2314 | 0 | 0 | 0 | 771194.6252
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 36803.0312 | -1684.3864 | -7915.4201 | -3454.3308 | -108084.273 | -9307.7652 | -3532.4085 | -6048.3784 | -3093.7156 | -8728.2314 |  |  |  | -115045.8782
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -1.2
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -41.1953 | -0.97911 | -0.97912 | -0.97911 | -0.97911 | -0.97912 | -0.97911 | 0 | 0 | 0 |  |  |  | -47.07
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -4930.9435 | -358.5613 | -368.2844 | -389.4513 | -399.6396 | -423.4506 | -425.9379 | -435.039 | -450.1292 | -454.0988 |  |  |  | -8635.5356
4.3 | Total Adjustment | -4973.3388 | -359.5404 | -369.2635 | -390.4305 | -400.6187 | -424.4297 | -426.9171 | -435.039 | -450.1292 | -454.0988 | 0 | 0 | 0 | -8683.8056
5 | Gross Profit (Item 3.0-4.3) | 41776.37 | -1324.846 | -7546.1566 | -3063.9004 | -107683.6543 | -8883.3355 | -3105.4915 | -5613.3393 | -2643.5864 | -8274.1327 |  |  |  | -106362.0726
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 19088.5472 | 86.61 | 0 | 33.42 | 40.38 | 172.74 | 158.82 | 285.78 | 147.18 | 0 |  |  |  | 20013.4772
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 22687.8228 | -1411.456 | -7546.1566 | -3097.3204 | -107724.0343 | -9056.0755 | -3264.3115 | -5899.1193 | -2790.7664 | -8274.1327 |  |  |  | -126375.5498
(=Item5.0 - 6.0 + 6.2)

## Accrual
CW-KL JV
Print Date: 2026-01-20
Project Code: | 1069
Project Name: | Contract No. DC/2022/01 - Drainage Improvement Works in Tsim Sha Tsui
Report Date: | 2025-12-31
Start Date: | 2022-08-19 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-11-10 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-11-10 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 385985.968 | 16552 | 15268 | 19907 | 11795 | 13601 | 10805 | 12832 | 52993 | 24915 |  |  |  | 564653.968
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 2141.44 | 32 | 33 | 32 | 113 | 32 | 33 | 32 | 33 | 56 |  |  |  | 2537.44
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | -750.8 | 0 | 0 | 0 |  |  |  | -750.8
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 388143.408 | 16584 | 15301 | 19939 | 11908 | 13633 | 10087.2 | 12864 | 53026 | 24971 | 0 | 0 | 0 | 566456.608
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 48306.0322 | 1515.17 | 1690.9108 | 1486.9152 | 1492.6812 | 1574.6665 | 1565.4596 | 1609.663 | 1517.2176 | 1823.6369 |  |  |  | 62582.353
2.1.13 | -Manpower (HO-Consultant) | 1212.76 | 22.58 | 46.2006 | 55.494 | 53.8447 | 58.8254 | 90.7553 | 45.7871 | -77.2811 | 139.4 |  |  |  | 1648.366
2.1.2 | -Manpower (RE) | 1983.5877 | 95.63 | 108.7791 | 142.0101 | 117.7894 | 126.082 | 125.7492 | 117.77 | 137.1037 | 132.09 |  |  |  | 3086.5912
2.1.3 | -Manpower (Labour) | 6225.2644 | 333.17 | 335.0202 | 364.9512 | 400.2488 | 372.9771 | 448.0612 | 472.1585 | 438.5697 | 491.9614 |  |  |  | 9882.3826
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 12821.904 | 293.319 | 0 | 124.082 | 232.26 | 0 | 109.774 | 91.785 | 124.17 | 355.062 |  |  |  | 14152.356
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 31439.7396 | 2906.5687 | 1822.4841 | 1011.9035 | 150.7899 | 804.3533 | 616.0622 | 1650.7503 | 969.5797 | 494.8196 |  |  |  | 41867.0509
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1.2
2.1.7 | -Adm. Cost Messing | 167.2238 | 8.338 | 18.975 | 18.7226 | 4.291 | 2.558 | 6.568 | -3.3426 | 7.509 | 5.587 |  |  |  | 236.4298
2.1.8 | -DSC | 17961.98 | 546.245 | 1729 | 153.25 | 1166.1 | 310.105 | 0 | 296.95 | 1205.78 | 0 |  |  |  | 23369.41
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 6566.603 | 1960.6183 | 1137.3904 | 278.232 | 810.7728 | -571.3436 | 31.5019 | 234.4019 | 345.3475 | 45.1767 |  |  |  | 10838.7009
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 2312.8405 | 6.63 | 41.893 | 0 | 149.983 | 4.75 | 0 | 141.1075 | 51.55 | 0 |  |  |  | 2708.754
2.2.2 | -Reinforcement | 460.8571 | 2.4 | 0 | 1298.2363 | 91.2 | 62.15 | 0 | 19.8013 | 0 | 0 |  |  |  | 1934.6447
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 3599.5971 | 910.0816 | 883.7682 | 130.5774 | 156.3131 | 51.4128 | 0 | 1100.8433 | 1520.5395 | 0 |  |  |  | 8353.1329
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 414.3206 | 47.5045 | 8.8 | 1.475 | 53.95 | 10.67 | 0 | 0 | 0 | 0 |  |  |  | 536.7201
2.2.14 | -Deposit | 3870.3996 | -119.4969 | -1462.2062 | 0 | -8.865 | 0 | 17.444 | 2.0655 | 7.2975 | -339.949 |  |  |  | 1966.6895
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1473.058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1473.058
2.3.2 | -Plant, Equipments & Tools (external hire) | 2985.8944 | 339.255 | 299.102 | 0.8 | 311.05 | 0 | 0 | 467.303 | 1.2 | 0 |  |  |  | 4404.6044
2.3.3 | -Diesel & Lubricant | 143.2265 | 29.5756 | 17.0668 | 10.3725 | 10.1273 | 12.5405 | 0 | 48.6927 | 25.9611 | 0 |  |  |  | 297.563
2.3.4 | -Repairing | 137.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 137.7688
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 41.1953 | 0.97911 | 0.97912 | 0.97911 | 0.97911 | 0.97912 | 0.97911 | 0 | 0 | 0 |  |  |  | 47.07
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 138142.147 | 9078.92 | 4478.2576 | 8126.8591 | 5501.134 | 674.8956 | 0 | 48545.2674 | 2245.7661 | 0 |  |  |  | 216793.2468
2.4.2 | -Variation | 17855.5209 | 3228.6262 | 1009.925 | 2070.0885 | 841.3112 | 474.012 | 0 | 5957.6885 | 41.8 | 0 |  |  |  | 31478.9722
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 8757.801 | 1054.2341 | -846.3555 | -3010.9462 | -192.3073 | -206.5255 | 0 | -4447.1875 | 97.1545 | 0 |  |  |  | 1205.8676
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.609 | 0 | 0 |  |  |  | 255.609
2.5 | Manpower (Labour) for Works | 5290.0835 | 189.02 | 418.3824 | 654.802 | 798.454 | 741.7951 | 638.2621 | 594.7951 | 579.0479 | 618.272 |  |  |  | 10522.9141
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 5939.9388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5939.9388
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 318110.9437 | 22449.3684 | 11738.3727 | 12918.8044 | 12142.1071 | 4504.9033 | 3650.6165 | 57201.9089 | 9238.3126 | 3766.0566 | 0 | 0 | 0 | 455721.3943
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 70032.4643 | -5865.3684 | 3562.6273 | 7020.1956 | -234.1071 | 9128.0967 | 6436.5835 | -44337.9089 | 43787.6874 | 21204.9434 |  |  |  | 110735.2137
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -1.2
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -41.1953 | -0.97911 | -0.97912 | -0.97911 | -0.97911 | -0.97912 | -0.97911 | 0 | 0 | 0 |  |  |  | -47.07
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -4930.9435 | -358.5613 | -368.2844 | -389.4513 | -399.6396 | -423.4506 | -425.9379 | -435.039 | -450.1292 | -454.0988 |  |  |  | -8635.5356
4.3 | Total Adjustment | -4973.3388 | -359.5404 | -369.2635 | -390.4305 | -400.6187 | -424.4297 | -426.9171 | -435.039 | -450.1292 | -454.0988 | 0 | 0 | 0 | -8683.8056
5 | Gross Profit (Item 3.0-4.3) | 75005.8031 | -5505.828 | 3931.8908 | 7410.6261 | 166.5115 | 9552.5264 | 6863.5005 | -43902.8699 | 44237.8166 | 21659.0421 |  |  |  | 119419.0193
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 11580.059 | 496.56 | 458.04 | 597.21 | 707.7 | 816.06 | 603.252 | 769.92 | 3179.58 | 1494.9 |  |  |  | 20703.281
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 63425.7441 | -6002.388 | 3473.8508 | 6813.4161 | -541.1885 | 8736.4664 | 6260.2485 | -44672.7899 | 41058.2366 | 20164.1421 |  |  |  | 98715.7383
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
CW-KL JV
Print Date: 2026-01-20
Project Code: | 1069
Project Name: | Contract No. DC/2022/01 - Drainage Improvement Works in Tsim Sha Tsui
Report Date: | 2025-12-31
Start Date: | 2022-08-19 |  |  |  |  | Monthly Financial Report
Complete Date: | 2026-11-10 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-11-10 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 380962.4746 | 15618.62 | 16103.0205 | 16361 | 17249.7496 | 12090.5168 | 12294.3276 | 11158.159 | 12691.3648 | 59430.464 |  |  |  | 553959.6969
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0.01667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.01667
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | -3704.0587 | -156.55 | -165.5194 | -153 | -199.0717 | -117.9419 | -136.0127 | -107.0312 | -128.284 | -529.9242 |  |  |  | -5397.3938
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 377258.4326 | 15462.07 | 15937.5011 | 16208 | 17050.6779 | 11972.5749 | 12158.3149 | 11051.1278 | 12563.0808 | 58900.5398 | 0 | 0 | 0 | 548562.3198
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 48306.029 | 1515.17 | 1690.9108 | 1486.9152 | 1492.6812 | 1574.6665 | 1565.4596 | 1609.663 | 1517.2176 | 1823.6369 |  |  |  | 62582.3498
2.1.13 | -Manpower (HO-Consultant) | 1212.76 | 22.58 | 46.2006 | 55.494 | 53.8447 | 58.8254 | 90.7553 | 45.7871 | -77.2811 | 139.4 |  |  |  | 1648.366
2.1.2 | -Manpower (RE) | 1983.3177 | 95.63 | 108.7791 | 142.0101 | 117.7894 | 126.082 | 125.7492 | 118.0475 | 137.1037 | 132.09 |  |  |  | 3086.5987
2.1.3 | -Manpower (Labour) | 6225.3012 | 333.17 | 335.0202 | 364.9512 | 400.2488 | 372.9771 | 448.0612 | 472.1585 | 438.5697 | 491.9614 |  |  |  | 9882.4193
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 12821.904 | 293.319 | 0 | 124.082 | 232.26 | 0 | 109.774 | 91.785 | 67.883 | 411.349 |  |  |  | 14152.356
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 29751.5908 | 538.1026 | 881.8992 | 1332.8835 | 2065.1813 | 609.8341 | 1235.5316 | 1001.6418 | 1137.0229 | 936.4552 |  |  |  | 39490.143
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1.2
2.1.7 | -Adm. Cost Messing | 158.3448 | 7.297 | 0 | 9.6996 | 5.53 | 7.559 | 31.958 | 0.1234 | 10.331 | 5.587 |  |  |  | 236.4298
2.1.8 | -DSC | 17005.68 | 258.7 | 257.7 | 895.845 | 1819.3 | 77 | 77 | 637.5 | 107.405 | 781.7 |  |  |  | 21917.83
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 5715.8138 | 236.0876 | 120.749 | 663.8018 | 259.7452 | 126.0193 | 186.5964 | 99.6693 | 214.7481 | 1343.7236 |  |  |  | 8966.9542
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 2310.7205 | 0 | 6.63 | 0 | 41.893 | 0 | 73.865 | 103.1005 | 43.02 | 122.655 |  |  |  | 2701.884
2.2.2 | -Reinforcement | 460.8571 | 0 | 0 | 0 | 0 | 0 | 2.49 | 588.0043 | 797.7543 | 85.539 |  |  |  | 1934.6447
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 2834.603 | 54.18 | 1012.6249 | 377.4563 | 97.433 | 167.5142 | 522.6649 | 306.9462 | 335.3877 | 1887.8921 |  |  |  | 7596.7022
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 309.1815 | 3.802 | 40.326 | 7.4845 | 8.8 | 0 | 50.75 | 10.67 | 1.475 | 3.2 |  |  |  | 435.689
2.2.14 | -Deposit | 3644.2352 | -119.4969 | -1462.2062 | 0 | -8.865 | 0 | 17.444 | 2.0655 | 7.2975 | -339.949 |  |  |  | 1740.5251
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1473.058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1473.058
2.3.2 | -Plant, Equipments & Tools (external hire) | 2121.1554 | 143.124 | 87.292 | 508.684 | 411.719 | 33.774 | 4.86 | 38.935 | 6.37 | 532.646 |  |  |  | 3888.5594
2.3.3 | -Diesel & Lubricant | 137.5591 | 0 | 1.0877 | 0 | 1.455 | 0 | 27.2756 | 11.966 | 43.6984 | 74.5212 |  |  |  | 297.563
2.3.4 | -Repairing | 137.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 137.7688
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 41.1953 | 0.97911 | 0.97912 | 0.97911 | 0.97911 | 0.97912 | 0.97911 | 0 | 0 | 0 |  |  |  | 47.07
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 128540.8758 | 4779.2835 | 6529.0805 | 3932.4695 | 5841.9925 | 1701.9127 | 6074.1254 | 1175.6429 | 2889.4057 | 49762.061 |  |  |  | 211226.8496
2.4.2 | -Variation | 15689.3998 | 2576.4242 | 961.4609 | 971.9195 | 812.2638 | 535.12 | 1618.6514 | 1066.7637 | 1032.4806 | 4096.2977 |  |  |  | 29360.7816
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 7548.8198 | -1508.2062 | 2984.585 | -57.6369 | 74.8508 | -47.9151 | -1038.1815 | 407.9651 | -448.5629 | -6175.8391 |  |  |  | 1739.8791
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | -8733.158 | -488.8985 | -536.1305 | -460.8901 | -554.6658 | -145.9447 | -607.7899 | -9.1031 | -217.6809 | -1869.2539 |  |  |  | -13623.5153
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.609 | 0 | 0 |  |  |  | 255.609
2.5 | Manpower (Labour) for Works | 5290.082 | 189.02 | 418.3824 | 654.802 | 798.454 | 741.7951 | 638.2621 | 594.7951 | 579.0479 | 618.272 |  |  |  | 10522.9126
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 5939.9388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5939.9388
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 290928.2332 | 8930.2675 | 13485.3707 | 11010.9504 | 13972.8901 | 5940.1987 | 11256.2815 | 8629.7359 | 8622.6932 | 54863.9451 | 0 | 0 | 0 | 427640.5663
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 86330.1993 | 6531.8025 | 2452.1304 | 5197.0496 | 3077.7878 | 6032.3762 | 902.0334 | 2421.3919 | 3940.3876 | 4036.5948 |  |  |  | 120921.7535
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -1.2
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -41.1953 | -0.97911 | -0.97912 | -0.97911 | -0.97911 | -0.97912 | -0.97911 | 0 | 0 | 0 |  |  |  | -47.07
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -4930.9435 | -358.5613 | -368.2844 | -389.4513 | -399.6396 | -423.4506 | -425.9379 | -435.039 | -450.1292 | -454.0988 |  |  |  | -8635.5356
4.3 | Total Adjustment | -4973.3388 | -359.5404 | -369.2635 | -390.4305 | -400.6187 | -424.4297 | -426.9171 | -435.039 | -450.1292 | -454.0988 | 0 | 0 | 0 | -8683.8056
5 | Gross Profit (Item 3.0-4.3) | 91303.5382 | 6891.3429 | 2821.3939 | 5587.48 | 3478.4065 | 6456.8059 | 1328.9505 | 2856.4309 | 4390.5168 | 4490.6935 |  |  |  | 129605.5591
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 11317.753 | 463.8621 | 478.125 | 486.24 | 1023.0407 | 718.3545 | 729.4989 | 663.0677 | 753.7848 | 3534.0324 |  |  |  | 20167.7591
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F |  | 79985.7852 | 86413.266 | 88756.5348 | 93857.7749 | 96313.1407 | 102051.5921 | 102651.0437 | 104844.4069 | 108481.1389
7 | Acc. Net Profit/(Loss) | 79985.7852 | 86413.266 | 88756.5348 | 93857.7749 | 96313.1407 | 102051.5921 | 102651.0437 | 104844.4069 | 108481.1389 | 109437.8 |  |  |  | 109437.8
(=Item5.0 - 6.0 + 6.2)