## Financial Status
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-14
Project Code: | 1090
Project Name: | Contract No. DC/2023/08 Construction of Trunk Sewage Rising Main in Cheung Sha Wan
Report Date: | 2025-12-31
Start Date: | 2023-08-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2027-08-22 Time Consumed (%): | 58.97% | [12 empty] | Confidential
Target Complete Date: | 2027-11-30 Target Completed (%): | 55.19%
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 353000 | 353000 | 0 | 353000 | 353000 | 353000 | 0 | 353000 | 256817 | 72.75% | 96183 | 256817.1326 | 247760.0206 | 96.47% | 9056.9794
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 9028 | 38500 | 0 | 38500 | 50609 | 225352 | 0 | 225352 | 14112 | 36.65% | 24388 | 0 | 0 | 0% | 14112
1.2.2 | -Fee of C.E. | 0 | 9625 | 0 | 9625 | 12402 | 53633 | 0 | 53633 | 3454 | 35.89% | 6171 | 0 | 0 | 0% | 3454
1.3 | Provisional Sum | 8778 | 5180 | 0 | 5180 | 5180 | 5180 | 0 | 5180 | 1459 | 28.17% | 3721 | 1459 | 0 | 0% | 1459
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | -3598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 28225 | 28225 | 0 | 28225 | 28225 | 2040 | 0 | 2040 | 0 | 0% | 28225 | 0 | 0 | 0% | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.2 | -Pain Gain Sharing | 16809 | 21467 | 0 | 21467 | 22211 | 31836 | 0 | 31836 | 0 | 0% | 21467 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2568 | 0% | 2568 | 0 | -2531.7345 | 98.59% | -36.2655
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -0.01 | 0% | 0.01
| Total Income | 412242 | 455997 | 0 | 455997 | 471627 | 671041 | 0 | 671041 | 273274 | 59.93% | 182723 | 258276.1326 | 245228.2761 | 89.74% | 28045.7239
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 43112.805 | 51154.666 | 0 | 51154.666 | 55551 | 68034 | 9880 | 77914 | 42740.5032 | 83.55% | 8414.1628 | 42740.5032 | 42740.4998 | 100% | 0.00346
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1150 | 678.0648 | 0% | -678.0648 | 678.0648 | 678.0686 | 100% | -0.00371
2.1.2 | -Manpower (RE) | 4396 | 4396 | 0 | 4396 | 0 | 4396 | 0 | 4396 | 739.8139 | 16.83% | 3656.1861 | 739.8143 | 739.814 | 100% | -0.0001
2.1.3 | -Manpower (Labour) | 0 | 0 | 0 | 0 | 20223 | 14570 | 4826 | 19396 | 10350.6341 | 0% | -10350.6341 | 10350.6366 | 10350.6401 | 100% | -0.00601
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 10992.816 | 10992.816 | 0 | 10992.816 | 10661 | 9241 | 0 | 9241 | 9053.066 | 82.35% | 1939.75 | 9053.066 | 9053.066 | 100% | -3.638e-12
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 18574.133 | 18574.133 | 0 | 18574.133 | 26692 | 32119 | -1920 | 30199 | 27353.7055 | 147.3% | -8779.5725 | 18342.264 | 17063.4055 | 62.38% | 10290.3
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.7 | -Adm. Cost Messing | 251.534 | 251.534 | 0 | 251.534 | 0 | 100 | 20 | 120 | 112.4866 | 44.72% | 139.0473 | 112.4866 | 112.4866 | 100% | 0
2.1.8 | -DSC | 18851.672 | 21853.672 | 0 | 21853.672 | 14810 | 14810 | 1670 | 16480 | 16463.383 | 75.33% | 5390.289 | 10828.513 | 9828.522 | 59.7% | 6634.861
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 7473.248 | 7473.248 | 0 | 7473.248 | 6225 | 9875 | 8450 | 18325 | 17347.2249 | 232.1% | -9873.9769 | 13143.5206 | 9917.4564 | 57.17% | 7429.7685
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 0 | 5220 | -50 | 5170 | 729.7815 | 0% | -729.7815 | 728.2815 | 710.5523 | 97.37% | 19.2292
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 0 | 5490 | -60 | 5430 | 421.0265 | 0% | -421.0265 | 262.153 | 235.0213 | 55.82% | 186.0053
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 43500 | -4025 | 39475 | 39318.2367 | 0% | -39318.2367 | 25332.5311 | 24756.0231 | 62.96% | 14562.2136
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 0 | 25547 | -950 | 24597 | 23971.9204 | 0% | -23971.9204 | 5997.6724 | 4993.2414 | 20.83% | 18978.679
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 21373.5579 | 21724.1579 | 0% | -21724.1579
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1443.642 | 1443.642 | 0 | 1443.642 | 0 | 610 | 0 | 610 | 593.732 | 41.13% | 849.91 | 593.732 | 593.732 | 100% | 0
2.3.2 | -Plant, Equipments & Tools (external hire) | 5155 | 5155 | 0 | 5155 | 0 | 1130 | 36320 | 37450 | 37078.922 | 719.3% | -31923.922 | 20518.0068 | 13271.9362 | 35.79% | 23806.9858
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 0 | 610 | 1160 | 1770 | 1766.6708 | 0% | -1766.6708 | 1631.3141 | 1094.2571 | 61.94% | 672.4138
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.5 | -Resale | -433.094 | -433.094 | 0 | -433.094 | 0 | 0 | 0 | 0 | 0 | 0% | -433.094 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 3.3177 | 0% | -3.3177 | 3.3177 | 3.3177 | 100% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 1089.724 | 1089.724 | 0% | -1089.724
2.4 | Subcontractor
2.4.1 | -Contract Works | 291233.256 | 281349.653 | 0 | 281349.653 | 290166 | 366468 | -26825 | 339643 | 121479.811 | 43.18% | 159869.842 | 53186.8556 | 35220.1709 | 28.99% | 86259.6401
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 0 | 3950 | 700 | 4650 | 4563.3293 | 0% | -4563.3293 | 4257.1582 | 3816.0982 | 83.63% | 747.2311
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | -896.9541 | 691.9108 | 0% | -691.9108
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3233.1616 | 0% | 3233.1616
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 2158.65 | 20223.193 | 0 | 20223.193 | 0 | 5544 | 6050 | 11594 | 9269.4964 | 45.84% | 10953.6966 | 9269.4998 | 9269.4927 | 100% | 0.0037
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | -18216.09 | 3877.771 | 0 | 3877.771 | 0 | 0 | 0 | 0 | 0 | 0% | 3877.771 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 1040 | 1040 | -1040 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 1040 | 3056.048 | 0 | 3056.048 | 2016 | 2016 | 1140 | 3156 | 3056.0483 | 100% | -0.00031 | 3056.0483 | 3056.0483 | 100% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | -32620 | -36501 | -69121 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 386033.572 | 429368.282 | 0 | 429368.282 | 427384 | 581650 | 0 | 581650 | 367091.1747 | 85.5% | 62277.1073 | 252391.7675 | 217776.4812 | 59.32% | 149314.6936
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 26208.428 | 26628.718 | 0 | 26628.718 | 44243 | 89391 | 0 | 89391 | -93817.1747 | -352.3% | 120445.8927 | 5884.3651 | 27451.7949 | -29.26% | -121268.9696
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | 0 |  |  | -5 | -3.3177 |  |  | -3.3177 | -3.3177 | 100% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | 0 |  |  | -1377.8847 | -1377.8847 | 0% | 1377.8847 | -1377.8847 | -1395.0362 | 101.2% | 17.1515
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | 0 |  |  | -1382.8847 | -1381.2024 | 0% | 1381.2024 | -1381.2024 | -1398.3539 | 101.2% | 17.1515
5 | Gross Profit (Item 3.0-4.3) | 26208.428 | 26628.718 | 0 | 26628.718 | 44243 |  |  | 90773.8847 | -92435.9724 | -347.1% | 119064.6904 | 7265.5675 | 28850.1488 | -31.21% | -121286.1211
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | #VALUE!
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 24207.84 | 27049.02 | 0 | 27049.02 | 27986.82 |  |  | 21554.82 | 11175.48 | 41.32% | 15873.54 | 10406.704 | 9727.9706 | 87.05% | 1447.5094
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 2000.588 | -420.302 | 0 | -420.302 | 16256.18 |  |  | 69219.0647 | -103611.4524 | 24652% | 103191.1504 | -3141.1365 | 19122.1781 | -18.46% | -122733.6305
(=Item5.0 - 6.0 + 6.2)

## Projection
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-14
Project Code: | 1090
Project Name: | Contract No. DC/2023/08 Construction of Trunk Sewage Rising Main in Cheung Sha Wan
Report Date: | 2025-12-31
Start Date: | 2023-08-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2027-08-22 Time Consumed (%): | 58.97% | [11 empty] | Confidential
Target Complete Date: | 2027-11-30 Target Completed (%): | 55.19%
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 353000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 353000
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 163000 | 7552 | 0 | 0 | 0 | 0 | 0 | 0 | 54800 | 0 |  |  |  | 225352
1.2.2 | -Fee of C.E. | 40750 | 1888 | 0 | 0 | 0 | 0 | 0 | 0 | 10995 | 0 |  |  |  | 53633
1.3 | Provisional Sum | 5180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5180
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 28225 | -10322 | 0 | 0 | 0 | 0 | 0 | 0 | -15863 | 0 |  |  |  | 2040
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 29135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701 | 0 |  |  |  | 31836
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 619290 | -882 | 0 | 0 | 0 | 0 | 0 | 0 | 52633 | 0 | 0 | 0 | 0 | 671041
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 56914 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 |  |  |  | 77914
2.1.13 | -Manpower (HO-Consultant) | 500 | 50 | 20 | 50 | 30 | 200 | 250 | 50 | 0 | 0 |  |  |  | 1150
2.1.2 | -Manpower (RE) | 4396 | 0 | 0 | -50 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4396
2.1.3 | -Manpower (Labour) | 14900 | -1180 | 5756 | 0 | -80 | 0 | 0 | 0 | 0 | 0 |  |  |  | 19396
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 9241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9241
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 30799 | 0 | 1320 | 0 | -400 | 0 | 0 | -1520 | 0 | 0 |  |  |  | 30199
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 |  |  |  | 120
2.1.8 | -DSC | 14810 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 1400 | 200 |  |  |  | 16480
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 7875 | 1000 | 1000 | 150 | 350 | 150 | 6100 | 200 | 200 | 1300 |  |  |  | 18325
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 220 | 0 | 5000 | -50 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5170
2.2.2 | -Reinforcement | 200 | 200 | 5090 | 0 | 0 | 0 | 0 | -60 | 0 | 0 |  |  |  | 5430
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 33500 | 0 | 10000 | 0 | -1550 | -3555 | 500 | 6500 | -3920 | -2000 |  |  |  | 39475
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 5597 | 1300 | 18650 | 0 | 0 | 0 | -2400 | 150 | 600 | 700 |  |  |  | 24597
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | -1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 610
2.3.2 | -Plant, Equipments & Tools (external hire) | 13050 | 3000 | 2000 | 4000 | 1200 | 1600 | 8800 | 1000 | 1450 | 1350 |  |  |  | 37450
2.3.3 | -Diesel & Lubricant | 310 | 50 | 250 | 50 | 400 | 0 | 200 | 400 | 110 | 0 |  |  |  | 1770
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 |  |  |  | 5
2.3.8 | -Potential Savings (Plants) | -7510 | -4000 | 11510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 390348 | 0 | -73255 | -4200 | -3000 | 1600 | -1550 | -7050 | 41600 | -4850 |  |  |  | 339643
2.4.2 | -Variation | 1950 | 0 | 2000 | 0 | 0 | 0 | 0 | 250 | 150 | 300 |  |  |  | 4650
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | -22860 | -400 | 23260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 4600 | 444 | 500 | 50 | 3000 | 0 | 0 | 0 | 0 | 3000 |  |  |  | 11594
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 3156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3156
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | -32576 | -44 | -24601 | 0 | 0 | 0 | -11900 | 0 | 0 | 0 |  |  |  | -69121
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 530130 | -1080 | 0 | 0 | 0 | 0 | 0 | 0 | 52600 | 0 | 0 | 0 | 0 | 581650
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 89160 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 |  |  |  | 89391
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | -5 | 0 | 0 | 0 | 0 |  |  |  | -5
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -511.3751 | -104.6525 | -95.8152 | -115.1168 | -122.6948 | -153.8642 | -51.7493 | -64.9169 | -97.589 | -60.1109 |  |  |  | -1377.8847
4.3 | Total Adjustment | -511.3751 | -104.6525 | -95.8152 | -115.1168 | -122.6948 | -158.8642 | -51.7493 | -64.9169 | -97.589 | -60.1109 | 0 | 0 | 0 | -1382.8847
5 | Gross Profit (Item 3.0-4.3) | 89671.3751 | 302.6525 | 95.8152 | 115.1168 | 122.6948 | 158.8642 | 51.7493 | 64.9169 | 130.589 | 60.1109 |  |  |  | 90773.8847
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 18423.3 | -26.46 | 0 | 0 | 0 | 0 | 0 | 0 | 3157.98 | 0 |  |  |  | 21554.82
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 71248.0751 | 329.1125 | 95.8152 | 115.1168 | 122.6948 | 158.8642 | 51.7493 | 64.9169 | -3027.391 | 60.1109 |  |  |  | 69219.0647
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-14
Project Code: | 1090
Project Name: | Contract No. DC/2023/08 Construction of Trunk Sewage Rising Main in Cheung Sha Wan
Report Date: | 2025-12-31
Start Date: | 2023-08-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2027-08-22 Time Consumed (%): | 58.97% | [11 empty] | Confidential
Target Complete Date: | 2027-11-30 Target Completed (%): | 55.19%
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 142551 | 10241 | 5121 | 8831 | 9697 | 12714 | 18409 | 13931 | 14173 | 21149 |  |  |  | 256817
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 4208 | 473 | 148 | 0 | 2066 | 0 | 1031 | 2960 | 2304 | 922 |  |  |  | 14112
1.2.2 | -Fee of C.E. | 1053 | 118 | 37 | 0 | 517 | 0 | 182 | 740 | 576 | 231 |  |  |  | 3454
1.3 | Provisional Sum | 1037 | 51 | 0 | 25 | 25 | 220 | 25 | 26 | 25 | 25 |  |  |  | 1459
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | -1425 | -127 | -32 | -83 | 0 | -229 | -179 | -139 | -142 | -212 |  |  |  | -2568
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 147424 | 10756 | 5274 | 8773 | 12305 | 12705 | 19468 | 17518 | 16936 | 22115 | 0 | 0 | 0 | 273274
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 31213.0635 | 1234.6131 | 1512.1007 | 1052.7822 | 1258.2699 | 1181.2382 | 1288.7363 | 1344.4479 | 1408.278 | 1246.9734 |  |  |  | 42740.5032
2.1.13 | -Manpower (HO-Consultant) | 495.7589 | 34.76 | 36.2257 | 51.867 | 25.8985 | 182.4984 | 266.9821 | 33 | -474.8655 | 25.9397 |  |  |  | 678.0648
2.1.2 | -Manpower (RE) | 61.3367 | 59.4666 | 62.3078 | 62.4666 | 82.3778 | 81.0729 | 79.4 | 79.4 | 79.5852 | 92.4003 |  |  |  | 739.8139
2.1.3 | -Manpower (Labour) | 8300.375 | -115.4 | 387.4988 | 963.2628 | 143.682 | 140.3815 | 114.5935 | 173.2087 | 190.7529 | 52.2789 |  |  |  | 10350.6341
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 8271.754 | 65.907 | 43.487 | 63.348 | 43.081 | 69.14 | 82.121 | 86.453 | 159.314 | 168.461 |  |  |  | 9053.066
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 12710.2113 | 1172.3601 | 524.9856 | 1978.9018 | 534.0261 | 274.186 | 3087.0099 | 658.0511 | 5742.4145 | 671.5591 |  |  |  | 27353.7055
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 66.895 | 2.8895 | 0 | 4.9604 | 1.841 | 9.5077 | 5.042 | 16.3444 | 3.6386 | 1.368 |  |  |  | 112.4866
2.1.8 | -DSC | 12570.383 | 0 | 32 | 0 | 0 | 1530 | 681 | 2 | 98 | 1550 |  |  |  | 16463.383
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 7695.9744 | 889.4518 | 176.452 | 557.229 | 768.957 | 259.3604 | 5905.148 | 621.0433 | 82.805 | 390.804 |  |  |  | 17347.2249
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 138.9724 | 8.525 | 0 | 23.49 | 50.0455 | 61.256 | 308.8274 | 81.827 | 39.109 | 17.7292 |  |  |  | 729.7815
2.2.2 | -Reinforcement | 170.4854 | 107.2869 | 0 | 89.9289 | 0 | 0 | 53.3253 | 0 | 0 | 0 |  |  |  | 421.0265
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 31914.3338 | 588.6871 | 459.7905 | 690.0462 | 847.21 | 64.8123 | 135.6207 | 4539.8081 | 0 | 77.928 |  |  |  | 39318.2367
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 5554.4684 | 1261.186 | 0 | 194.39 | 81.124 | 15223.06 | 800.802 | 168.75 | 495.49 | 192.65 |  |  |  | 23971.9204
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 593.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 593.732
2.3.2 | -Plant, Equipments & Tools (external hire) | 12950.5161 | 1614.9805 | 1558.444 | 3969.8797 | 1863.8 | 2400.971 | 8459.84 | 1282.928 | 1939.15 | 1038.4128 |  |  |  | 37078.922
2.3.3 | -Diesel & Lubricant | 302.3308 | 54.0608 | 0 | 137.3119 | 375.0958 | 189.9075 | 182.9828 | 251.8633 | 141.8364 | 131.2815 |  |  |  | 1766.6708
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 1.1059 | 1.1059 | 1.1059 | 0 | 0 | 0 |  |  |  | 3.3177
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 49920.557 | 0 | 2724.324 | 824.9 | 67 | 10580.86 | 4364.49 | 8046.48 | 3078.45 | 41872.75 |  |  |  | 121479.811
2.4.2 | -Variation | 4220.2899 | 0 | 98.3985 | 218.99 | 0 | 0 | 25.6509 | 0 | 0 | 0 |  |  |  | 4563.3293
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 4592.714 | 324.77 | 320.7591 | 306.019 | 771.72 | 611.2547 | 566.46 | 505.49 | 456.6244 | 813.6852 |  |  |  | 9269.4964
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 3056.0483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3056.0483
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 194800.1999 | 7303.5444 | 7936.7738 | 11189.7734 | 6915.2345 | 32860.6125 | 26409.1377 | 17891.0949 | 13440.5825 | 48344.2211 | 0 | 0 | 0 | 367091.1747
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -47376.1999 | 3452.4556 | -2662.7738 | -2416.7734 | 5389.7655 | -20155.6125 | -6941.1377 | -373.0949 | 3495.4175 | -26229.2211 |  |  |  | -93817.1747
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | -1.1059 | -1.1059 | -1.1059 | 0 | 0 | 0 |  |  |  | -3.3177
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -511.3751 | -104.6525 | -95.8152 | -115.1168 | -122.6948 | -153.8642 | -51.7493 | -64.9169 | -97.589 | -60.1109 |  |  |  | -1377.8847
4.3 | Total Adjustment | -511.3751 | -104.6525 | -95.8152 | -115.1168 | -123.8007 | -154.9701 | -52.8552 | -64.9169 | -97.589 | -60.1109 | 0 | 0 | 0 | -1381.2024
5 | Gross Profit (Item 3.0-4.3) | -46864.8247 | 3557.108 | -2566.9586 | -2301.6566 | 5513.5662 | -20000.6425 | -6888.2825 | -308.178 | 3593.0064 | -26169.1103 |  |  |  | -92435.9724
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 4391.61 | 321.15 | 158.22 | 262.44 | 736.8 | 749.1 | 1166.58 | 1049.52 | 1014.66 | 1325.4 |  |  |  | 11175.48
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -51256.4347 | 3235.958 | -2725.1786 | -2564.0966 | 4776.7662 | -20749.7425 | -8054.8625 | -1357.698 | 2578.3464 | -27494.5103 |  |  |  | -103611.4524
(=Item5.0 - 6.0 + 6.2)

## Accrual
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-14
Project Code: | 1090
Project Name: | Contract No. DC/2023/08 Construction of Trunk Sewage Rising Main in Cheung Sha Wan
Report Date: | 2025-12-31
Start Date: | 2023-08-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2027-08-22 Time Consumed (%): | 58.97% | [11 empty] | Confidential
Target Complete Date: | 2027-11-30 Target Completed (%): | 55.19%
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 142550.1326 | 10681 | 5178 | 8335 | 9697 | 11894 | 19229 | 13931 | 14174 | 21148 |  |  |  | 256817.1326
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 1037 | 51 | 0 | 25 | 25 | 220 | 25 | 26 | 25 | 25 |  |  |  | 1459
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 143587.1326 | 10732 | 5178 | 8360 | 9722 | 12114 | 19254 | 13957 | 14199 | 21173 | 0 | 0 | 0 | 258276.1326
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 31213.0635 | 1234.6131 | 1512.1007 | 1052.7822 | 1258.2699 | 1181.2382 | 1288.7363 | 1344.4479 | 1408.278 | 1246.9734 |  |  |  | 42740.5032
2.1.13 | -Manpower (HO-Consultant) | 495.7589 | 34.76 | 36.2257 | 51.867 | 25.8985 | 182.4984 | 266.9821 | 33 | -474.8655 | 25.9397 |  |  |  | 678.0648
2.1.2 | -Manpower (RE) | 61.3371 | 59.4666 | 62.3078 | 62.4667 | 82.3778 | 81.0729 | 79.4 | 79.4 | 79.5852 | 92.4003 |  |  |  | 739.8143
2.1.3 | -Manpower (Labour) | 8300.3775 | -115.4 | 387.4988 | 963.2628 | 143.682 | 140.3815 | 114.5935 | 173.2087 | 190.7529 | 52.2789 |  |  |  | 10350.6366
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 8271.754 | 65.907 | 43.487 | 63.348 | 43.081 | 69.14 | 82.121 | 86.453 | 159.314 | 168.461 |  |  |  | 9053.066
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 8806.4872 | 1687.4805 | 645.3216 | 1871.4353 | 919.91 | 275.263 | 2912.5783 | 964.3133 | -165.9229 | 425.3976 |  |  |  | 18342.264
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 66.895 | 2.8895 | 0 | 4.9604 | 1.841 | 9.5077 | 5.042 | 16.3444 | 3.6386 | 1.368 |  |  |  | 112.4866
2.1.8 | -DSC | 6280.76 | 272.112 | 194.168 | 621.252 | 768.556 | 939.46 | 0 | 1386.985 | 365.22 | 0 |  |  |  | 10828.513
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 2141.7398 | 937.1421 | 56.073 | 922.292 | 268.078 | 370.1344 | 5391.267 | 2527.5543 | 523.62 | 5.62 |  |  |  | 13143.5206
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 138.9724 | 24.145 | 6.37 | 111.3015 | 0 | 284.3874 | 0 | 145.376 | 17.7292 | 0 |  |  |  | 728.2815
2.2.2 | -Reinforcement | 13.1654 | 105.7333 | 61.5972 | 1.2 | 53.3253 | 0 | 0 | 27.1317 | 0 | 0 |  |  |  | 262.153
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 10550.972 | 5753.3366 | 3695.4121 | 4101.7635 | 530.1926 | 80.3724 | 18.4 | 602.082 | 0 | 0 |  |  |  | 25332.5311
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 3069.7854 | 435.502 | 0 | 1463.51 | 0 | 27.6462 | 325 | 138.7992 | 537.4296 | 0 |  |  |  | 5997.6724
2.2.14 | -Deposit | 16567.6423 | 1688.4 | -1233.1552 | -24.5 | -298.752 | 0 | -3354.8962 | 4109.087 | -143.227 | 4062.959 |  |  |  | 21373.5579
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 593.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 593.732
2.3.2 | -Plant, Equipments & Tools (external hire) | 3220.9927 | 879.8285 | 759.089 | 2575.2851 | 2609.138 | 753.7229 | 6560.166 | 2599.9048 | 559.8798 | 0 |  |  |  | 20518.0068
2.3.3 | -Diesel & Lubricant | 264.9021 | 87.4143 | 137.0519 | 359.5683 | 15.7875 | 189.9075 | 0 | 434.8461 | 141.8364 | 0 |  |  |  | 1631.3141
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 1.1059 | 1.1059 | 1.1059 | 0 | 0 | 0 |  |  |  | 3.3177
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.8655 | 597.8585 |  |  |  | 1089.724
2.4 | Subcontractor
2.4.1 | -Contract Works | 16917.6316 | 5765.9028 | 1076.5718 | 7396.68 | 2130.995 | 2492.0588 | 0 | 12696.3556 | 4690.66 | 20 |  |  |  | 53186.8556
2.4.2 | -Variation | 1794.4459 | 837.084 | 327.82 | 39.1 | 278.6043 | 17.364 | 0 | 745.12 | 217.62 | 0 |  |  |  | 4257.1582
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 21.258 | -77.869 | -34.4444 | -31.25 | 99.9604 | 268.5854 | 0 | -1149.0845 | 5.89 | 0 |  |  |  | -896.9541
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 4592.7174 | 324.77 | 320.7591 | 306.019 | 771.72 | 611.2547 | 566.46 | 505.49 | 456.6244 | 813.6852 |  |  |  | 9269.4998
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 3056.0483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3056.0483
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 126440.4384 | 20003.2184 | 8054.2541 | 21912.3438 | 9703.7712 | 7975.1013 | 14256.9559 | 27466.8147 | 9065.9282 | 7512.9416 | 0 | 0 | 0 | 252391.7675
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 17146.6942 | -9271.2184 | -2876.2541 | -13552.3438 | 18.2288 | 4138.8987 | 4997.0441 | -13509.8147 | 5133.0718 | 13660.0584 |  |  |  | 5884.3651
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | -1.1059 | -1.1059 | -1.1059 | 0 | 0 | 0 |  |  |  | -3.3177
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -511.3751 | -104.6525 | -95.8152 | -115.1168 | -122.6948 | -153.8642 | -51.7493 | -64.9169 | -97.589 | -60.1109 |  |  |  | -1377.8847
4.3 | Total Adjustment | -511.3751 | -104.6525 | -95.8152 | -115.1168 | -123.8007 | -154.9701 | -52.8552 | -64.9169 | -97.589 | -60.1109 | 0 | 0 | 0 | -1381.2024
5 | Gross Profit (Item 3.0-4.3) | 17658.0693 | -9166.5659 | -2780.4388 | -13437.2269 | 142.0295 | 4293.8688 | 5049.8993 | -13444.8978 | 5230.6607 | 13720.1693 |  |  |  | 7265.5675
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 4276.504 | 320.43 | 155.34 | 250.05 | 581.82 | 713.64 | 1153.74 | 835.86 | 850.44 | 1268.88 |  |  |  | 10406.704
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 13381.5654 | -9486.9959 | -2935.7788 | -13687.2769 | -439.7905 | 3580.2288 | 3896.1593 | -14280.7578 | 4380.2207 | 12451.2893 |  |  |  | -3141.1365
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-14
Project Code: | 1090
Project Name: | Contract No. DC/2023/08 Construction of Trunk Sewage Rising Main in Cheung Sha Wan
Report Date: | 2025-12-31
Start Date: | 2023-08-23 |  |  |  |  | Monthly Financial Report
Complete Date: | 2027-08-22 Time Consumed (%): | 58.97% | [11 empty] | Confidential
Target Complete Date: | 2027-11-30 Target Completed (%): | 55.19%
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 141076.66 | 13247 | 2587 | 10921 | 10379 | 12840.116 | 8947.7229 | 15997 | 21177.5217 | 10587 |  |  |  | 247760.0206
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | -1400.9207 | -131 | -25.8651 | -83 | -129 | -126.1995 | -89.2256 | -229 | -211.5236 | -106 |  |  |  | -2531.7345
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -0.01
| Total Income | 139675.7293 | 13116 | 2561.1349 | 10838 | 10250 | 12713.9165 | 8858.4973 | 15768 | 20965.9982 | 10481 | 0 | 0 | 0 | 245228.2761
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 31213.06 | 1234.6131 | 1512.1007 | 1052.7822 | 1258.2699 | 1181.2382 | 1288.7363 | 1344.4479 | 1408.278 | 1246.9734 |  |  |  | 42740.4998
2.1.13 | -Manpower (HO-Consultant) | 495.724 | 34.7949 | 36.2257 | 51.867 | 25.8985 | 182.4984 | 266.9821 | 33 | -474.8655 | 25.9434 |  |  |  | 678.0686
2.1.2 | -Manpower (RE) | 61.3371 | 59.4666 | 62.3078 | 62.4666 | 82.3778 | 81.0729 | 79.4 | 79.4 | 79.5852 | 92.4 |  |  |  | 739.814
2.1.3 | -Manpower (Labour) | 8300.3811 | -115.4 | 387.4988 | 963.2628 | 143.682 | 140.3815 | 114.5935 | 173.2087 | 190.7529 | 52.2788 |  |  |  | 10350.6401
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 8244.101 | 93.56 | 43.487 | 63.348 | 43.081 | 51.549 | 99.712 | 86.453 | 120.477 | 207.298 |  |  |  | 9053.066
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 7387.2852 | 1420.2978 | 353.0324 | 504.0391 | 798.2283 | 501.8288 | 3000.4229 | 410.5566 | 382.9602 | 2304.7541 |  |  |  | 17063.4055
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 65.637 | 1.258 | 0 | 2.8895 | 0 | 6.8014 | 0 | 20.9891 | 9.905 | 5.0066 |  |  |  | 112.4866
2.1.8 | -DSC | 5945.184 | 193.232 | 245.9 | 123.656 | 64.9 | 185.616 | 1602.352 | 471.052 | 883.63 | 113 |  |  |  | 9828.522
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 1761.9558 | 38.975 | 119.8268 | 51.7309 | 496.655 | 301.0986 | 5682.4548 | 102.661 | 381.5304 | 980.5681 |  |  |  | 9917.4564
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 124.4824 | 9.175 | 13.84 | 0 | 42.1355 | 8.79 | 81.456 | 371.2624 | 36.972 | 22.439 |  |  |  | 710.5523
2.2.2 | -Reinforcement | 13.1654 | 0 | 105.7333 | 0 | 61.5972 | 0 | 0 | 53.3253 | 0 | 1.2 |  |  |  | 235.0213
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 7809.29 | 0 | 2027.7381 | 198.0667 | 905.0014 | 0 | 11864.6743 | 871.8039 | 390.5627 | 688.886 |  |  |  | 24756.0231
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 1933.9454 | 0 | 3.2 | 6.4 | 1195.996 | 0 | 523.34 | 0 | 0 | 1330.36 |  |  |  | 4993.2414
2.2.14 | -Deposit | 16918.2423 | 1688.4 | -1233.1552 | -24.5 | -298.752 | 0 | -3354.8962 | 4109.087 | -143.227 | 4062.959 |  |  |  | 21724.1579
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 593.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 593.732
2.3.2 | -Plant, Equipments & Tools (external hire) | 2124.1211 | 778.198 | 0 | 70.1 | 288.4583 | 182.0166 | 6863.2865 | 31.9 | 1692.5 | 1241.3557 |  |  |  | 13271.9362
2.3.3 | -Diesel & Lubricant | 232.471 | 0 | 0.78 | 1.132 | 63.8727 | 0 | 289.4267 | 13.245 | 290.9924 | 202.3373 |  |  |  | 1094.2571
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 1.1059 | 1.1059 | 1.1059 | 0 | 0 | 0 |  |  |  | 3.3177
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491.8655 | 597.8585 |  |  |  | 1089.724
2.4 | Subcontractor
2.4.1 | -Contract Works | 16331.2666 | 381.245 | 403.9928 | 1909.964 | 1626.375 | 864.3068 | 4573.161 | 2947.5979 | 6162.2618 | 20 |  |  |  | 35220.1709
2.4.2 | -Variation | 1322.9927 | 422.0035 | 86.5336 | 800 | 320.12 | 28.3 | 171.7043 | 89.58 | 390.134 | 184.73 |  |  |  | 3816.0982
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 61.608 | -36.25 | 233.347 | -77.05 | 270.7208 | 271.5854 | -472.1208 | 214.1804 | 225.89 | 0 |  |  |  | 691.9108
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | -1452.1265 | -62.1952 | -13.2564 | -89.8834 | -228.9395 | -5.2057 | -252.7262 | -215.8028 | -545.2948 | -367.7311 |  |  |  | -3233.1616
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 4592.714 | 324.77 | 320.7591 | 306.019 | 771.72 | 611.2547 | 566.46 | 505.49 | 456.6244 | 813.6815 |  |  |  | 9269.4927
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 3056.0483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3056.0483
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 117136.6179 | 6466.1437 | 4709.8916 | 5976.2904 | 7932.5038 | 4594.2386 | 32989.5249 | 11713.4376 | 12431.5343 | 13826.2982 | 0 | 0 | 0 | 217776.4812
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 22539.1114 | 6649.8563 | -2148.7567 | 4861.7096 | 2317.4962 | 8119.6778 | -24131.0277 | 4054.5624 | 8534.4639 | -3345.2982 |  |  |  | 27451.7949
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | -1.1059 | -1.1059 | -1.1059 | 0 | 0 | 0 |  |  |  | -3.3177
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -511.3751 | -104.6525 | -95.8152 | -115.1168 | -122.6948 | -153.8642 | -51.7493 | -64.9169 | -95.5062 | -79.3451 |  |  |  | -1395.0362
4.3 | Total Adjustment | -511.3751 | -104.6525 | -95.8152 | -115.1168 | -123.8007 | -154.9701 | -52.8552 | -64.9169 | -95.5062 | -79.3451 | 0 | 0 | 0 | -1398.3539
5 | Gross Profit (Item 3.0-4.3) | 23050.4865 | 6754.5088 | -2052.9415 | 4976.8264 | 2441.2969 | 8274.6479 | -24078.1725 | 4119.4793 | 8629.9701 | -3265.9531 |  |  |  | 28850.1488
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 4190.2719 | 393.48 | 76.834 | 325.14 | 615 | 762.835 | 531.5098 | 946.08 | 1257.9599 | 628.86 |  |  |  | 9727.9706
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F |  | 18860.2147 | 25221.2434 | 23091.4678 | 27743.1542 | 29569.4511 | 37081.264 | 12471.5817 | 15644.9811 | 23016.9912
7 | Acc. Net Profit/(Loss) | 18860.2147 | 25221.2434 | 23091.4678 | 27743.1542 | 29569.4511 | 37081.264 | 12471.5817 | 15644.9811 | 23016.9912 | 19122.1781 |  |  |  | 19122.1781
(=Item5.0 - 6.0 + 6.2)