## Financial Status
KL-CW JV
Print Date: 2026-01-15
Project Code: | 1130
Project Name: | Contract No. DC/2023/11 Construction and Rehabilitation of Sewage Rising Mains in Southern District
Report Date: | 2025-12-31
Start Date: | 2025-01-03 |  |  |  |  | Monthly Financial Report
Complete Date: | 2029-06-04 Time Consumed (%): | 22.44% | [12 empty] | Confidential
Target Complete Date: | Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 0 | 0 | 0 | 0 | 630000 | 630000 | 0 | 630000 | 630000 | 0% | -630000 | 132145 | 101532.5266 | 16.12% | 528467.4734
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 115776 | 115776 | 0 | 115776 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 28944 | 28944 | 0 | 28944 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 6910 | 6910 | 0 | 6910 | 352 | 0% | -352 | 352 | 0 | 0% | 352
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 43296 | 43296 | 0 | 43296 | -1138 | 0% | 1138 | 0 | 0 | 0% | -1138
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 40901 | 40901 | 0 | 40901 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1117.0532 | 0% | 1117.0532
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 12600 | 0% | -12600
| Total Income | 0 | 0 | 0 | 0 | 865827 | 865827 | 0 | 865827 | 629214 | 0% | -629214 | 132497 | 113015.4734 | 17.96% | 516198.5266
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 0 | 0 | 0 | 0 | 55463 | 55463 | 0 | 55463 | 11147.383 | 0% | -11147.383 | 11147.383 | 11147.383 | 100% | 0
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 690 | 690 | 0 | 690 | 372.5559 | 0% | -372.5559 | 372.5559 | 372.5559 | 100% | 0
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 10573 | 10573 | 0 | 10573 | 769.7929 | 0% | -769.7929 | 769.7929 | 769.7929 | 100% | 0
2.1.3 | -Manpower (Labour) | 0 | 0 | 0 | 0 | 5686 | 5686 | 0 | 5686 | 634.6542 | 0% | -634.6542 | 634.6496 | 634.6496 | 100% | 0.0046
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 0 | 0 | 0 | 0 | 18975 | 18975 | 0 | 18975 | 6861.916 | 0% | -6861.916 | 6861.916 | 6859.332 | 99.96% | 2.584
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 0 | 0 | 0 | 0 | 11305 | 11305 | 4322 | 15627 | 11544.9112 | 0% | -11544.9112 | 10059.5754 | 5380.4462 | 46.6% | 6164.465
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0 | 0 | 877.82 | 877.82 | -0.005 | 877.815 | 25.419 | 0% | -25.419 | 25.419 | 22.347 | 87.91% | 3.072
2.1.8 | -DSC | 0 | 0 | 0 | 0 | 27147 | 27147 | 0 | 27147 | 3397.5 | 0% | -3397.5 | 2037.618 | 1193.118 | 35.12% | 2204.382
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 0 | 0 | 0 | 0 | 14553 | 14553 | -4322 | 10231 | 8147.6757 | 0% | -8147.6757 | 5444.7612 | 5120.7743 | 62.85% | 3026.9014
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 12987 | 12987 | 0 | 12987 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 7200 | 7200 | 0 | 7200 | 6840.12 | 0% | -6840.12 | 0 | 0 | 0% | 6840.12
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 800 | 800 | 100 | 900 | 825.7319 | 0% | -825.7319 | 774.7565 | 758.029 | 91.8% | 67.7029
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 4250.2875 | 4250.2875 | 0% | -4250.2875
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0 | 0 | 0 | 0 | 2855 | 2855 | 0 | 2855 | 961.5455 | 0% | -961.5455 | 961.5455 | 961.5455 | 100% | 0
2.3.2 | -Plant, Equipments & Tools (external hire) | 0 | 0 | 0 | 0 | 4984 | 4984 | 0 | 4984 | 1406.3078 | 0% | -1406.3078 | 702.5728 | 203.82 | 14.49% | 1202.4878
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 626 | 626 | 0 | 626 | 39.8269 | 0% | -39.8269 | 39.8269 | 39.8269 | 100% | 0
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 51.4051 | 51.4051 | 0% | -51.4051
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 0 | 0 | 0 | 528341 | 528341 | -100 | 528241 | 307799.496 | 0% | -307799.496 | 48937.7918 | 16902.8463 | 5.492% | 290896.6496
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 115776 | 115776 | 0 | 115776 | 1201.8143 | 0% | -1201.8143 | 1134.418 | 586.2726 | 48.78% | 615.5417
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 22.232 | 0 | 0% | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1640.0378 | 0% | 1640.0378
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -18642 | -18642 | 0 | -18642 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 4953 | 4953 | 0 | 4953 | 3952.1987 | 0% | -3952.1987 | 3952.1987 | 3952.1987 | 100% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 0 | 0 | 0 | 0 | 805149.82 | 805149.82 | -0.005 | 805149.815 | 365928.8489 | 0% | -365928.8489 | 98180.7058 | 57566.5926 | 15.73% | 308362.2563
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 0 | 0 | 0 | 0 | 60677.18 | 60677.18 | 0.005 | 60677.185 | 263285.1511 | 0% | -263285.1511 | 34316.2942 | 55448.8807 | 21.06% | 207836.2703
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | 0 |  |  | -1146.1662 | -1146.1662 | 0% | 1146.1662 | -1146.1662 | -1145.7944 | 99.97% | -0.3718
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | 0 |  |  | -1146.1662 | -1146.1662 | 0% | 1146.1662 | -1146.1662 | -1145.7944 | 99.97% | -0.3718
5 | Gross Profit (Item 3.0-4.3) | 0 | 0 | 0 | 0 | 60677.18 |  |  | 61823.3512 | 264431.3173 | 0% | -264431.3173 | 35462.4604 | 56594.6751 | 21.4% | 207836.6421
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | #VALUE!
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 51535.02 |  |  | 13135.02 | -54.78 | 0% | 54.78 | 5189.7 | 5194.5986 | -9483% | -5249.3786
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 0 | 0 | 0 | 0 | 9142.16 |  |  | 48688.3312 | 264486.0973 | 0% | -264486.0973 | 30272.7604 | 51400.0765 | 19.43% | 213086.0207
(=Item5.0 - 6.0 + 6.2)

## Projection
KL-CW JV
Print Date: 2026-01-15
Project Code: | 1130
Project Name: | Contract No. DC/2023/11 Construction and Rehabilitation of Sewage Rising Mains in Southern District
Report Date: | 2025-12-31
Start Date: | 2025-01-03 |  |  |  |  | Monthly Financial Report
Complete Date: | 2029-06-04 Time Consumed (%): | 22.44% | [11 empty] | Confidential
Target Complete Date: | Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 0 | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 630000
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 115776 | 0 | 0 | 0 | 0 |  |  |  | 115776
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 28944 | 0 | 0 | 0 | 0 |  |  |  | 28944
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 6910 | 0 | 0 | 0 | 0 |  |  |  | 6910
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 10000 | 0 | 0 | 0 | 33296 | 0 | 0 | 0 | 0 |  |  |  | 43296
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 40901 | 0 | 0 | 0 | 0 |  |  |  | 40901
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 0 | 640000 | 0 | 0 | 0 | 225827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 865827
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 0 | 39798 | 0 | 0 | 0 | 15665 | 0 | 0 | 0 | 0 |  |  |  | 55463
2.1.13 | -Manpower (HO-Consultant) | 0 | 594 | 0 | 0 | 0 | -404 | 500 | 0 | 0 | 0 |  |  |  | 690
2.1.2 | -Manpower (RE) | 0 | 5940 | 0 | 0 | 0 | 4633 | 0 | 0 | 0 | 0 |  |  |  | 10573
2.1.3 | -Manpower (Labour) | 0 | 5940 | 0 | 0 | 0 | -254 | 0 | 0 | 0 | 0 |  |  |  | 5686
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 0 | 5940 | 0 | 6560 | 0 | 6475 | 0 | 0 | 0 | 0 |  |  |  | 18975
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 0 | 5940 | -141 | 0 | 1500 | 4006 | 0 | 0 | 0 | 4322 |  |  |  | 15627
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0.815 | 40 | 0 | 837 | 0 | 0 | 0 | 0 |  |  |  | 877.815
2.1.8 | -DSC | 0 | 29700 | 0 | -6600 | -3600 | 8147 | -500 | 0 | 0 | 0 |  |  |  | 27147
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 0 | 5940 | 0 | 0 | 1500 | 7113 | 0 | 0 | 0 | -4322 |  |  |  | 10231
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 12987 | 0 | 0 | 0 | 0 |  |  |  | 12987
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 100 | 100 | 7000 | 0 | 0 | 0 |  |  |  | 7200
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 0 | 0 | 140 | 0 | 500 | 60 | 100 | 0 | 0 | 100 |  |  |  | 900
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0 | 2970 | 0 | 0 | 0 | -115 | 0 | 0 | 0 | 0 |  |  |  | 2855
2.3.2 | -Plant, Equipments & Tools (external hire) | 0 | 2970 | 0 | 0 | 0 | 2014 | 0 | 0 | 0 | 0 |  |  |  | 4984
2.3.3 | -Diesel & Lubricant | 0 | 2970 | 0 | 0 | 0 | -2344 | 0 | 0 | 0 | 0 |  |  |  | 626
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 5940 | 0 | 0 | 0 | -5940 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 475200 | 0 | 0 | 0 | 60241 | -7100 | 0 | 0 | -100 |  |  |  | 528241
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 0 | 115776 | 0 | 0 | 0 | 0 |  |  |  | 115776
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | -18642 | 0 | 0 | 0 | 0 |  |  |  | -18642
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 4158 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 |  |  |  | 4953
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 0 | 594000 | -0.185 | 0 | 0 | 211150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805149.815
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 0 | 46000 | 0.185 | 0 | 0 | 14677 | 0 | 0 | 0 | 0 |  |  |  | 60677.185
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -80.0698 | -42.0746 | -41.7117 | -69.9932 | -100.1714 | -120.3857 | -140.6545 | -153.6139 | -183.965 | -213.5264 |  |  |  | -1146.1662
4.3 | Total Adjustment | -80.0698 | -42.0746 | -41.7117 | -69.9932 | -100.1714 | -120.3857 | -140.6545 | -153.6139 | -183.965 | -213.5264 | 0 | 0 | 0 | -1146.1662
5 | Gross Profit (Item 3.0-4.3) | 80.0698 | 46042.0746 | 41.8967 | 69.9932 | 100.1714 | 14797.3857 | 140.6545 | 153.6139 | 183.965 | 213.5264 |  |  |  | 61823.3512
6 | Overhead
6.1 | HO Overhead Rate % | 0 | 0 | 0 | 0 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 13135.02 | 0 | 0 | 0 | 0 |  |  |  | 13135.02
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 80.0698 | 46042.0746 | 41.8967 | 69.9932 | 100.1714 | 1662.3657 | 140.6545 | 153.6139 | 183.965 | 213.5264 |  |  |  | 48688.3312
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
KL-CW JV
Print Date: 2026-01-15
Project Code: | 1130
Project Name: | Contract No. DC/2023/11 Construction and Rehabilitation of Sewage Rising Mains in Southern District
Report Date: | 2025-12-31
Start Date: | 2025-01-03 |  |  |  |  | Monthly Financial Report
Complete Date: | 2029-06-04 Time Consumed (%): | 22.44% | [11 empty] | Confidential
Target Complete Date: | Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 630000
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 49 | 26 | 25 | 25 | 100 | 26 | 25 | 25 | 26 | 25 |  |  |  | 352
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | -33 | -4 | -37 | -151 | -245 | -293 | -226 | -19 | -43 | -87 |  |  |  | -1138
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 630016 | 22 | -12 | -126 | -145 | -267 | -201 | 6 | -17 | -62 | 0 | 0 | 0 | 629214
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 528.63 | 935.4141 | 1171.2907 | 1056.1077 | 745.018 | 1230.5106 | 1208.5597 | 1452.7088 | 1268.4378 | 1550.7056 |  |  |  | 11147.383
2.1.13 | -Manpower (HO-Consultant) | 0 | 18.754 | 20.5273 | 29.6386 | 58.72 | 79.0616 | 63.7791 | 13.527 | 29.3756 | 59.1727 |  |  |  | 372.5559
2.1.2 | -Manpower (RE) | 3.51 | 0 | 39.0325 | 27.1945 | 55.67 | 76.5574 | 107.3345 | 108.9948 | 182.8263 | 168.6729 |  |  |  | 769.7929
2.1.3 | -Manpower (Labour) | 0 | 0.799 | 0.798 | 37.93 | 46 | 65.26 | 97.5666 | 150.55 | 112.7334 | 123.0172 |  |  |  | 634.6542
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 0 | 66.78 | 2.912 | 6111.465 | 6.754 | 84.784 | 144.424 | 109.081 | 136.864 | 198.852 |  |  |  | 6861.916
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 340.529 | 1024.9248 | 1035.2026 | 787.259 | 4176.2017 | 242.4468 | 685.8909 | 1353.5615 | 1014.189 | 884.7058 |  |  |  | 11544.9112
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 1.913 | 11.914 | 0 | 2.126 | 2.824 | 3.57 | 3.072 | 0 |  |  |  | 25.419
2.1.8 | -DSC | 834 | 1134.5 | 1175 | 250 | 0 | 0 | 0 | 2 | 2 | 0 |  |  |  | 3397.5
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 58.03 | 38.7 | 122.019 | 166.8626 | 6945.138 | 159.7178 | 141.727 | 45.8709 | 232.947 | 236.6634 |  |  |  | 8147.6757
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 58.8 | 0 | 6781.32 | 0 | 0 | 0 |  |  |  | 6840.12
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 139.2 | 8 | 468.893 | 130.611 | 7.2 | 11.325 | 60.5029 |  |  |  | 825.7319
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 178.634 | 399.2781 | 3.4 | 0 | 3.4 | 70.8594 | 5 | 300.974 | 0 | 0 |  |  |  | 961.5455
2.3.2 | -Plant, Equipments & Tools (external hire) | 0 | 0 | 0 | 100 | 119.396 | 23.864 | 103.7535 | 210.25 | 14.69 | 834.3543 |  |  |  | 1406.3078
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 7.3903 | 0 | 0 | 32.4366 | 0 | 0 |  |  |  | 39.8269
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 133 | 287680.616 | 14420.96 | 1420.88 | 0 | 1164.04 | 0 | 2980 | 0 | 0 |  |  |  | 307799.496
2.4.2 | -Variation | 66.5514 | 1085.3629 | 49.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1201.8143
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 3952.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3952.1987
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 6095.083 | 292385.1289 | 18042.9551 | 10138.4513 | 12230.488 | 3668.1206 | 9472.7903 | 6770.7246 | 3008.4601 | 4116.6468 | 0 | 0 | 0 | 365928.8489
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 623920.917 | -292363.1289 | -18054.9551 | -10264.4513 | -12375.488 | -3935.1206 | -9673.7903 | -6764.7246 | -3025.4601 | -4178.6468 |  |  |  | 263285.1511
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -80.0698 | -42.0746 | -41.7117 | -69.9932 | -100.1714 | -120.3857 | -140.6545 | -153.6139 | -183.965 | -213.5264 |  |  |  | -1146.1662
4.3 | Total Adjustment | -80.0698 | -42.0746 | -41.7117 | -69.9932 | -100.1714 | -120.3857 | -140.6545 | -153.6139 | -183.965 | -213.5264 | 0 | 0 | 0 | -1146.1662
5 | Gross Profit (Item 3.0-4.3) | 624000.9867 | -292321.0543 | -18013.2434 | -10194.4581 | -12275.3166 | -3814.7348 | -9533.1359 | -6611.1107 | -2841.4952 | -3965.1205 |  |  |  | 264431.3173
6 | Overhead
6.1 | HO Overhead Rate % | 0 | 0 | 0 | 0 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | -14.7 | -17.58 | -13.56 | -1.14 | -2.58 | -5.22 |  |  |  | -54.78
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 624000.9867 | -292321.0543 | -18013.2434 | -10194.4581 | -12260.6166 | -3797.1548 | -9519.5759 | -6609.9707 | -2838.9152 | -3959.9005 |  |  |  | 264486.0973
(=Item5.0 - 6.0 + 6.2)

## Accrual
KL-CW JV
Print Date: 2026-01-15
Project Code: | 1130
Project Name: | Contract No. DC/2023/11 Construction and Rehabilitation of Sewage Rising Mains in Southern District
Report Date: | 2025-12-31
Start Date: | 2025-01-03 |  |  |  |  | Monthly Financial Report
Complete Date: | 2029-06-04 Time Consumed (%): | 22.44% | [11 empty] | Confidential
Target Complete Date: | Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 4041 | 1262 | 8575 | 19172 | 10926 | 17893 | 15228 | 18118 | 16491 | 20439 |  |  |  | 132145
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 49 | 26 | 25 | 25 | 100 | 26 | 25 | 25 | 26 | 25 |  |  |  | 352
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 12600 | 0 | 0 | 0 | -2100 | -2100 | -2100 | -2100 | -2100 | -2100 |  |  |  | 0
| Total Income | 16690 | 1288 | 8600 | 19197 | 8926 | 15819 | 13153 | 16043 | 14417 | 18364 | 0 | 0 | 0 | 132497
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 528.63 | 935.4141 | 1171.2907 | 1056.1077 | 745.018 | 1230.5106 | 1208.5597 | 1452.7088 | 1268.4378 | 1550.7056 |  |  |  | 11147.383
2.1.13 | -Manpower (HO-Consultant) | 0 | 18.754 | 20.5273 | 29.6386 | 58.72 | 79.0616 | 63.7791 | 13.527 | 29.3756 | 59.1727 |  |  |  | 372.5559
2.1.2 | -Manpower (RE) | 3.51 | 0 | 39.0325 | 27.1945 | 55.67 | 76.5574 | 107.3345 | 108.9948 | 182.8263 | 168.6729 |  |  |  | 769.7929
2.1.3 | -Manpower (Labour) | 0 | 0.799 | 0.798 | 37.93 | 46 | 65.2554 | 97.5666 | 150.55 | 112.7334 | 123.0172 |  |  |  | 634.6496
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 0 | 66.78 | 2.912 | 6111.465 | 6.754 | 84.784 | 144.424 | 109.081 | 136.864 | 198.852 |  |  |  | 6861.916
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 307.599 | 1024.9248 | 521.9658 | 825.287 | 963.2947 | 221.9968 | 530.9609 | 4598.1832 | 669.0994 | 396.2638 |  |  |  | 10059.5754
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 1.913 | 11.914 | 0 | 2.126 | 2.824 | 3.57 | 3.072 | 0 |  |  |  | 25.419
2.1.8 | -DSC | 0 | 0 | 303.014 | 230.213 | 245.671 | 0 | 0 | 1256.72 | 2 | 0 |  |  |  | 2037.618
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 0 | 96.73 | 12.739 | 4696.9966 | 152.133 | 71.0628 | 0.878 | 210.2199 | 204.002 | 0 |  |  |  | 5444.7612
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 139.2 | 8 | 599.504 | 0 | 16.7275 | 11.325 | 0 |  |  |  | 774.7565
2.2.14 | -Deposit | 467.6775 | 165.5 | 45 | 2.5 | 0 | 244.75 | 6 | 0 | 3394.86 | -76 |  |  |  | 4250.2875
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 178.634 | 402.6781 | 0 | 0 | 0.8594 | 70 | 5 | 304.374 | 0 | 0 |  |  |  | 961.5455
2.3.2 | -Plant, Equipments & Tools (external hire) | 0 | 0 | 0 | 104.11 | 0 | 1.914 | 88 | 464.5173 | 44.0315 | 0 |  |  |  | 702.5728
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 7.3903 | 0 | 0 | 32.4366 | 0 | 0 |  |  |  | 39.8269
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7025 | 25.7025 |  |  |  | 51.4051
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 2853.2845 | 7084.8357 | 6886.2059 | 6250.5301 | 0 | 54.339 | 22161.8645 | 3642.732 | 4 |  |  |  | 48937.7918
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 38.2616 | 0 | 0 | 1096.1564 | 0 | 0 |  |  |  | 1134.418
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.232 | 0 | 0 |  |  |  | 22.232
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 3952.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3952.1987
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 5438.2492 | 5564.8645 | 9204.028 | 20158.7623 | 8578.3022 | 2747.5226 | 2309.6658 | 32001.8629 | 9727.0616 | 2450.3868 | 0 | 0 | 0 | 98180.7058
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 11251.7508 | -4276.8645 | -604.028 | -961.7623 | 347.6978 | 13071.4774 | 10843.3342 | -15958.8629 | 4689.9384 | 15913.6132 |  |  |  | 34316.2942
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -80.0698 | -42.0746 | -41.7117 | -69.9932 | -100.1714 | -120.3857 | -140.6545 | -153.6139 | -183.965 | -213.5264 |  |  |  | -1146.1662
4.3 | Total Adjustment | -80.0698 | -42.0746 | -41.7117 | -69.9932 | -100.1714 | -120.3857 | -140.6545 | -153.6139 | -183.965 | -213.5264 | 0 | 0 | 0 | -1146.1662
5 | Gross Profit (Item 3.0-4.3) | 11331.8206 | -4234.7899 | -562.3163 | -891.7691 | 447.8693 | 13191.8632 | 10983.9886 | -15805.249 | 4873.9034 | 16127.1396 |  |  |  | 35462.4604
6 | Overhead
6.1 | HO Overhead Rate % | 0 | 0 | 0 | 0 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 529.56 | 947.58 | 787.68 | 961.08 | 863.46 | 1100.34 |  |  |  | 5189.7
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 11331.8206 | -4234.7899 | -562.3163 | -891.7691 | -81.6907 | 12244.2832 | 10196.3086 | -16766.329 | 4010.4434 | 15026.7996 |  |  |  | 30272.7604
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
KL-CW JV
Print Date: 2026-01-15
Project Code: | 1130
Project Name: | Contract No. DC/2023/11 Construction and Rehabilitation of Sewage Rising Mains in Southern District
Report Date: | 2025-12-31
Start Date: | 2025-01-03 |  |  |  |  | Monthly Financial Report
Complete Date: | 2029-06-04 Time Consumed (%): | 22.44% | [11 empty] | Confidential
Target Complete Date: | Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 0 | 4090.44 | 1287.03 | 8600.14 | 19197.8 | 8925.87 | 15818.72 | 13153.14 | 16043.0335 | 14416.3531 |  |  |  | 101532.5266
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | -40.41 | -12.62 | -85.75 | -191.72 | -109.26 | -178.93 | -152.2774 | -181.1763 | -164.9095 |  |  |  | -1117.0532
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12600
| Total Income | 12600 | 4050.03 | 1274.41 | 8514.39 | 19006.08 | 8816.61 | 15639.79 | 13000.8626 | 15861.8572 | 14251.4436 | 0 | 0 | 0 | 113015.4734
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 528.63 | 935.4141 | 1171.2907 | 1056.1077 | 745.018 | 1230.5106 | 1208.5597 | 1452.7088 | 1268.4378 | 1550.7056 |  |  |  | 11147.383
2.1.13 | -Manpower (HO-Consultant) | 0 | 18.754 | 20.5273 | 29.6386 | 58.72 | 79.0616 | 63.7791 | 13.527 | 29.3756 | 59.1727 |  |  |  | 372.5559
2.1.2 | -Manpower (RE) | 3.51 | 0 | 39.0325 | 27.1945 | 55.67 | 76.5574 | 107.3345 | 108.9948 | 182.8263 | 168.6729 |  |  |  | 769.7929
2.1.3 | -Manpower (Labour) | 0 | 0.799 | 0.798 | 37.93 | 46 | 65.2554 | 97.5666 | 150.55 | 112.7334 | 123.0172 |  |  |  | 634.6496
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 0 | 66.78 | 0 | 24.377 | 6.754 | 84.784 | 6234.424 | 46.729 | 106.349 | 289.135 |  |  |  | 6859.332
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 306.419 | 7.874 | 108.4319 | 336.782 | 844.4466 | 184.5941 | 1006.7404 | 978.719 | 335.9545 | 1270.4848 |  |  |  | 5380.4462
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0 | 12.1275 | 0 | 0.6015 | 0 | 6.048 | 3.57 | 0 |  |  |  | 22.347
2.1.8 | -DSC | 0 | 0 | 0 | 0 | 289.69 | 173.544 | 294.067 | 240.097 | 20.896 | 174.824 |  |  |  | 1193.118
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 0 | 0 | 18.5 | 2.689 | 4667.249 | 17.2018 | 129.2337 | 182.3998 | 59.1619 | 44.339 |  |  |  | 5120.7743
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 139.2 | 8 | 0 | 468.893 | 130.611 | 0 | 11.325 |  |  |  | 758.029
2.2.14 | -Deposit | 467.6775 | 165.5 | 45 | 2.5 | 0 | 244.75 | 6 | 0 | 3394.86 | -76 |  |  |  | 4250.2875
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0 | 178.634 | 0 | 0 | 402.6781 | 70 | 5 | 0.8594 | 3.4 | 300.974 |  |  |  | 961.5455
2.3.2 | -Plant, Equipments & Tools (external hire) | 0 | 0 | 0 | 100 | 0 | 0 | 88 | 1.914 | 7.826 | 6.08 |  |  |  | 203.82
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 0 | 0 | 5.6423 | 11.9648 | 10.6989 | 11.5209 |  |  |  | 39.8269
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7025 | 25.7025 |  |  |  | 51.4051
2.4 | Subcontractor
2.4.1 | -Contract Works | 0 | 0 | 0 | 0 | 3958.573 | 1462.2238 | 283.92 | 6508.4101 | 2118.0511 | 2571.6684 |  |  |  | 16902.8463
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.2616 | 342.918 | 205.093 |  |  |  | 586.2726
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | -389.8641 | -152.7354 | -41.867 | -620.5978 | -213.5451 | -221.4283 |  |  |  | -1640.0378
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 3952.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3952.1987
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 5258.4352 | 1373.7551 | 1403.5804 | 1768.5463 | 10692.9346 | 3536.3488 | 9957.2933 | 9251.1964 | 7809.216 | 6515.2866 | 0 | 0 | 0 | 57566.5926
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 7341.5648 | 2676.2749 | -129.1704 | 6745.8437 | 8313.1454 | 5280.2612 | 5682.4967 | 3749.6661 | 8052.6412 | 7736.157 |  |  |  | 55448.8807
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -80.0698 | -42.0746 | -41.7117 | -69.9932 | -100.1714 | -120.3857 | -140.6545 | -153.6139 | -183.8412 | -213.2783 |  |  |  | -1145.7944
4.3 | Total Adjustment | -80.0698 | -42.0746 | -41.7117 | -69.9932 | -100.1714 | -120.3857 | -140.6545 | -153.6139 | -183.8412 | -213.2783 | 0 | 0 | 0 | -1145.7944
5 | Gross Profit (Item 3.0-4.3) | 7421.6346 | 2718.3495 | -87.4586 | 6815.8369 | 8413.3168 | 5400.647 | 5823.1511 | 3903.2801 | 8236.4824 | 7949.4353 |  |  |  | 56594.6751
6 | Overhead
6.1 | HO Overhead Rate % | 0 | 0 | 0 | 0 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 1140.3648 | 528.9966 | 938.3874 | 780.0518 | 951.7114 | 855.0866 |  |  |  | 5194.5986
6.1.2 | BU Overhead (0.0000% of Total Income excl. PC & Provisional Sum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
6.2 | Acc. Profit/(Loss) ~ B/F |  | 7421.6346 | 10139.9841 | 10052.5255 | 16868.3624 | 24141.3145 | 29012.9648 | 33897.7286 | 37020.9569 | 44305.7279
7 | Acc. Net Profit/(Loss) | 7421.6346 | 10139.9841 | 10052.5255 | 16868.3624 | 24141.3145 | 29012.9648 | 33897.7286 | 37020.9569 | 44305.7279 | 51400.0765 |  |  |  | 51400.0765
(=Item5.0 - 6.0 + 6.2)