## Financial Status
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 951
Project Name: | Subcontract for the Engineering, Procurement and construction of SENT Landfill Extension
Report Date: | 2025-12-31
Start Date: | 2018-04-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-07-07 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2021-11-20 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 518634.3 | 504711.24 | 8472 | 513183.24 | 481117.5269 | 481117.5269 | 0 | 481117.5269 | 481117.5269 | 93.75% | 32065.7131 | 481118.29 | 481117.47 | 100% | 0.05688
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 9036.8 | 12556.74 | 21593.54 | -8249.6517 | -8249.6517 | 0 | -8249.6517 | -8249.6517 | -38.2% | 29843.1917 | -8250.47 | -8249.65 | 100% | -0.00169
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 176364 | 190287.06 | -8472 | 181815.06 | 176364 | 176364 | 0 | 176364 | 176364 | 97% | 5451.06 | 176364 | 176363.65 | 100% | 0.35
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 10431.09 | 10431.09 | 0 | 0 | 0 | 0 | 0 | 0% | 10431.09 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 0 | 58464.95 | -37076.8 | 21388.15 | -8231.8752 | -8231.8752 | 0 | -8231.8752 | -8231.8752 | -38.49% | 29620.0252 | -8231.94 | -8231.87 | 100% | -0.00519
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0.01 | 0% | -0.01
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Income | 694998.3 | 762500.05 | -14088.97 | 748411.08 | 641000 | 641000 | 0 | 641000 | 641000 | 85.65% | 107411.08 | 640999.88 | 640999.61 | 100% | 0.39
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 48314.4967 | 54377.5737 | -0.01041 | 54377.5633 | 52690 | 52690 | 0 | 52690 | 52639.8124 | 96.8% | 1737.7509 | 52639.8124 | 52639.8124 | 100% | 0
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.3 | -Manpower (Labour) | 2670.2697 | 5956.7144 | 0 | 5956.7144 | 8370 | 8370 | 0.3 | 8370.3 | 8368.5605 | 140.5% | -2411.8461 | 8368.5605 | 8368.5605 | 100% | 0
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 12548.4553 | 7382.063 | -5559.96 | 1822.103 | 2337 | 2337 | 0 | 2337 | 2208.4897 | 121.2% | -386.3867 | 2208.4897 | 2207.8671 | 99.97% | 0.62264
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 24425.7154 | 21679.8764 | -4401.3388 | 17278.5377 | 28334 | 28334 | 0 | 28334 | 28333.6187 | 164% | -11055.0811 | 26617.5219 | 26629.9714 | 93.99% | 1703.6473
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0.28 | 0% | -0.28 | 0.28 | 0.28 | 100% | 0
2.1.7 | -Adm. Cost Messing | 63.434 | 67.2644 | -1.4893 | 65.775 | 120 | 120 | 0 | 120 | 119.79 | 182.1% | -54.0149 | 119.79 | 119.79 | 100% | 0
2.1.8 | -DSC | 22329.9785 | 24182.4013 | -3581.5086 | 20600.8927 | 16540 | 16540 | 0 | 16540 | 16534.4123 | 80.26% | 4066.4803 | 15901.6113 | 15901.6113 | 96.17% | 632.801
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 1186.3539 | 1257.99 | 0 | 1257.99 | 2883 | 2883 | 0 | 2883 | 2882.8011 | 229.2% | -1624.8112 | 2639.7991 | 2632.1292 | 91.3% | 250.672
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 3521 | 3521 | 5435 | 5435 | 0 | 5435 | 5434.7893 | 154.4% | -1913.7893 | 5434.7533 | 5434.7533 | 100% | 0.036
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 8102 | 8102 | 0 | 8102 | 5990.7384 | 0% | -5990.7384 | 5990.7384 | 5990.7384 | 100% | 0
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 197 | 197 | 0 | 197 | 196.225 | 0% | -196.225 | 196.225 | 196.225 | 100% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3 | 2.2553 | 0% | -2.2553 | 2.2553 | 2.2553 | 100% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 66.08 | 66.08 | 2068 | 2068 | 0 | 2068 | 2047.7388 | 3099% | -1981.6588 | 1671.3938 | 1671.3938 | 81.62% | 376.345
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 15 | 15 | 0% | -15
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | -8511 | -8511 | 0 | -8511 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0 | 2118 | 700 | 2818 | 1817 | 1817 | 0 | 1817 | 1816.682 | 64.47% | 1001.318 | 1182.24 | 1182.24 | 65.08% | 634.442
2.3.2 | -Plant, Equipments & Tools (external hire) | 7510.2997 | 8981.2773 | -736.6 | 8244.6773 | 11061 | 11061 | 0 | 11061 | 11060.3069 | 134.2% | -2815.6296 | 9848.9503 | 9727.831 | 87.95% | 1332.4759
2.3.3 | -Diesel & Lubricant | 0 | 0 | 726.6 | 726.6 | 3510 | 3510 | 0 | 3510 | 3509.0748 | 482.9% | -2782.4748 | 3509.0748 | 3509.0748 | 100% | 0
2.3.4 | -Repairing | 0 | 0 | 10 | 10 | 42 | 42 | 0 | 42 | 41.8948 | 418.9% | -31.8948 | 41.8948 | 41.8948 | 100% | 0
2.3.5 | -Resale | 0 | 0 | -700 | -700 | -741 | -741 | 0 | -741 | -340.7105 | 48.67% | -359.2895 | -340.7105 | -340.7105 | 100% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 520 | 520 | 0 | 520 | 519.8684 | 0% | -519.8684 | 519.8684 | 519.8684 | 100% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | -1214 | -1214 | 0 | -1214 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 540835.9538 | 593846.8789 | -4131.7402 | 589715.1387 | 512357 | 512357 | -0.3 | 512356.7 | 496866.685 | 84.26% | 92848.4536 | 487206.5945 | 484867.018 | 97.58% | 11999.6671
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 91833 | 91833 | 0 | 91833 | 75400.242 | 0% | -75400.242 | 74647.0488 | 74250.359 | 98.47% | 1149.883
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | -13872.9825 | -10321.101 | 0% | 10321.101
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5389.7347 | 0% | 5389.7347
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -53344 | -53344 | 0 | -53344 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 659884.9572 | 719850.0394 | -14088.9674 | 705761.072 | 684410 | 684410 | 0 | 684410 | 713633.555 | 101.1% | -7872.483 | 684548.2094 | 679857.1274 | 95.27% | 33776.4276
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 35113.3428 | 42650.0106 | -0.00262 | 42650.008 | -43410 | -43410 | 0 | -43410 | -72633.555 | -170.3% | 115283.563 | -43548.3294 | -38857.5174 | 53.5% | -33776.0376
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | -1 |  |  | -1 | -0.28 | 0% |  | -0.28 | -0.28 | 100% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | -520 |  |  | -520 | -519.8684 | 0% |  | -519.8684 | -519.8684 | 100% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | -760 |  |  | 6632.8266 | 6632.8266 | 0% | -6632.8266 | 6632.8266 | 7202.3606 | 108.6% | -569.534
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | -1281 |  |  | 6111.8266 | 6112.6782 | 0% | -6112.6782 | 6112.6782 | 6682.2122 | 109.3% | -569.534
5 | Gross Profit (Item 3.0-4.3) | 35113.3428 | 42650.0106 | -0.00262 | 42650.008 | -42129 |  |  | -49521.8266 | -78746.2332 | -184.6% | 121396.2412 | -49661.0076 | -45539.7296 | 57.83% | -33206.5036
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 31118.058 | 34332.7794 | -337.0182 | 33995.7612 | 27878.16 |  |  | 13939.08 | 13939.08 | 41% | 20056.6812 | 13939.0764 | 13939.0788 | 100% | 0.0012
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 10372.686 | 11444.2598 | -112.3394 | 11331.9204 | 9292.72 |  |  | 9292.72 | 9292.72 | 82% | 2039.2004 | 9292.7176 | 9292.7192 | 100% | 0.0008
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -6377.4012 | -3127.0286 | 449.355 | -2677.6736 | -79299.88 |  |  | -72753.6266 | -101978.0332 | 3808% | 99300.3596 | -72892.8016 | -68771.5276 | 67.44% | -33206.5056
(=Item5.0 - 6.0 + 6.2)

## Projection
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 951
Project Name: | Subcontract for the Engineering, Procurement and construction of SENT Landfill Extension
Report Date: | 2025-12-31
Start Date: | 2018-04-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-07-07 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2021-11-20 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 481117.5269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 481117.5269
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | -8249.6517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8249.6517
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 176364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 176364
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | -8231.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8231.8752
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 641000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641000
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 52690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 52690
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 8370.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8370.3
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 2337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2337
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 28334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 28334
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1
2.1.7 | -Adm. Cost Messing | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 120
2.1.8 | -DSC | 16540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16540
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2883
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 5435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5435
2.2.2 | -Reinforcement | 8102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8102
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 197
2.2.8 | -Ironmongery | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 2068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2068
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | -8511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8511
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1817
2.3.2 | -Plant, Equipments & Tools (external hire) | 11061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11061
2.3.3 | -Diesel & Lubricant | 3510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3510
2.3.4 | -Repairing | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 42
2.3.5 | -Resale | -741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -741
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 520
2.3.8 | -Potential Savings (Plants) | -1214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -1214
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 512356.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 512356.7
2.4.2 | -Variation | 91833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 91833
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | -53344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -53344
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 684410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684410
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -43410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -43410
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -1
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -520
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 4837.1119 | 239.1148 | 242.1894 | 247.4402 | 250.5545 | 251.5985 | 281.8216 | 282.9958 | 0 | 0 |  |  |  | 6632.8266
4.3 | Total Adjustment | 4316.1119 | 239.1148 | 242.1894 | 247.4402 | 250.5545 | 251.5985 | 281.8216 | 282.9958 | 0 | 0 | 0 | 0 | 0 | 6111.8266
5 | Gross Profit (Item 3.0-4.3) | -47726.1119 | -239.1148 | -242.1894 | -247.4402 | -250.5545 | -251.5985 | -281.8216 | -282.9958 | 0 | 0 |  |  |  | -49521.8266
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 13939.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13939.08
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 9292.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9292.72
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -70957.9119 | -239.1148 | -242.1894 | -247.4402 | -250.5545 | -251.5985 | -281.8216 | -282.9958 | 0 | 0 |  |  |  | -72753.6266
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 951
Project Name: | Subcontract for the Engineering, Procurement and construction of SENT Landfill Extension
Report Date: | 2025-12-31
Start Date: | 2018-04-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-07-07 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2021-11-20 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 481117.5269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 481117.5269
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | -8249.6517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8249.6517
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 176364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 176364
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | -8231.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8231.8752
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 641000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641000
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 52639.8124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 52639.8124
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 8369.7805 | 0 | -1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8368.5605
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 2208.4897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2208.4897
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 28333.6187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 28333.6187
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.28
2.1.7 | -Adm. Cost Messing | 119.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 119.79
2.1.8 | -DSC | 16534.4123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16534.4123
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 2882.8011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2882.8011
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 5434.7893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5434.7893
2.2.2 | -Reinforcement | 5990.7384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5990.7384
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 196.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 196.225
2.2.8 | -Ironmongery | 2.2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2.2553
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 2047.7388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2047.7388
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1816.682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1816.682
2.3.2 | -Plant, Equipments & Tools (external hire) | 11060.3069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11060.3069
2.3.3 | -Diesel & Lubricant | 3509.0748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3509.0748
2.3.4 | -Repairing | 41.8948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 41.8948
2.3.5 | -Resale | -340.7105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -340.7105
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 519.8684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 519.8684
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 496866.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 496866.685
2.4.2 | -Variation | 75400.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75400.242
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 713634.775 | 0 | -1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713633.555
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -72634.775 | 0 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -72633.555
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -0.28
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -519.8684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -519.8684
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 4837.1119 | 239.1148 | 242.1894 | 247.4402 | 250.5545 | 251.5985 | 281.8216 | 282.9958 | 0 | 0 |  |  |  | 6632.8266
4.3 | Total Adjustment | 4316.9635 | 239.1148 | 242.1894 | 247.4402 | 250.5545 | 251.5985 | 281.8216 | 282.9958 | 0 | 0 | 0 | 0 | 0 | 6112.6782
5 | Gross Profit (Item 3.0-4.3) | -76951.7385 | -239.1148 | -240.9694 | -247.4402 | -250.5545 | -251.5985 | -281.8216 | -282.9958 | 0 | 0 |  |  |  | -78746.2332
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 13939.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13939.08
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 9292.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9292.72
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -100183.5385 | -239.1148 | -240.9694 | -247.4402 | -250.5545 | -251.5985 | -281.8216 | -282.9958 | 0 | 0 |  |  |  | -101978.0332
(=Item5.0 - 6.0 + 6.2)

## Accrual
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 951
Project Name: | Subcontract for the Engineering, Procurement and construction of SENT Landfill Extension
Report Date: | 2025-12-31
Start Date: | 2018-04-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-07-07 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2021-11-20 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 481118.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 481118.29
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | -8250.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8250.47
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 176364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 176364
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | -8231.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8231.94
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 640999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640999.88
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 52639.8124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 52639.8124
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 8369.7805 | 0 | -1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8368.5605
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 2208.4897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2208.4897
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 26617.5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 26617.5219
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.28
2.1.7 | -Adm. Cost Messing | 119.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 119.79
2.1.8 | -DSC | 15901.6113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15901.6113
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 2639.7991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2639.7991
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 5434.7533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5434.7533
2.2.2 | -Reinforcement | 5990.7384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5990.7384
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 196.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 196.225
2.2.8 | -Ironmongery | 2.2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2.2553
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 1671.3938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1671.3938
2.2.14 | -Deposit | 45 | 0 | 0 | -30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1182.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1182.24
2.3.2 | -Plant, Equipments & Tools (external hire) | 9848.9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9848.9503
2.3.3 | -Diesel & Lubricant | 3509.0748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3509.0748
2.3.4 | -Repairing | 41.8948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 41.8948
2.3.5 | -Resale | -340.7105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -340.7105
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 519.8684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 519.8684
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 487206.5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 487206.5945
2.4.2 | -Variation | 74647.0488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 74647.0488
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | -13872.9825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -13872.9825
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 684579.4294 | 0 | -1.22 | -30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684548.2094
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -43579.5494 | 0 | 1.22 | 30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -43548.3294
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -0.28
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -519.8684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -519.8684
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 4837.1119 | 239.1148 | 242.1894 | 247.4402 | 250.5545 | 251.5985 | 281.8216 | 282.9958 | 0 | 0 |  |  |  | 6632.8266
4.3 | Total Adjustment | 4316.9635 | 239.1148 | 242.1894 | 247.4402 | 250.5545 | 251.5985 | 281.8216 | 282.9958 | 0 | 0 | 0 | 0 | 0 | 6112.6782
5 | Gross Profit (Item 3.0-4.3) | -47896.5129 | -239.1148 | -240.9694 | -217.4402 | -250.5545 | -251.5985 | -281.8216 | -282.9958 | 0 | 0 |  |  |  | -49661.0076
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 13939.0764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13939.0764
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 9292.7176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9292.7176
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -71128.3069 | -239.1148 | -240.9694 | -217.4402 | -250.5545 | -251.5985 | -281.8216 | -282.9958 | 0 | 0 |  |  |  | -72892.8016
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 951
Project Name: | Subcontract for the Engineering, Procurement and construction of SENT Landfill Extension
Report Date: | 2025-12-31
Start Date: | 2018-04-30 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-07-07 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2021-11-20 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 481117.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 481117.47
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | -8249.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8249.65
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 176363.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 176363.65
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | -8231.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -8231.87
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.01
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 640999.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640999.61
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 52639.8124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 52639.8124
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 8369.7805 | 0 | -1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8368.5605
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 2207.8671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2207.8671
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 26628.4714 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 |  |  |  | 26629.9714
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.28
2.1.7 | -Adm. Cost Messing | 119.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 119.79
2.1.8 | -DSC | 15901.6113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15901.6113
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 2632.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2632.1292
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 5434.7533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5434.7533
2.2.2 | -Reinforcement | 5990.7384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5990.7384
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 196.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 196.225
2.2.8 | -Ironmongery | 2.2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2.2553
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 1671.3938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1671.3938
2.2.14 | -Deposit | 45 | 0 | 0 | -30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1182.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1182.24
2.3.2 | -Plant, Equipments & Tools (external hire) | 9711.5504 | 0 | 0 | 16.2806 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9727.831
2.3.3 | -Diesel & Lubricant | 3509.0748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3509.0748
2.3.4 | -Repairing | 41.8948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 41.8948
2.3.5 | -Resale | -340.7105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -340.7105
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 519.8684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 519.8684
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 483175.2728 | 252.4973 | 252.4973 | 252.4973 | 252.4973 | 0 | 681.7561 | 0 | 0 | 0 |  |  |  | 484867.018
2.4.2 | -Variation | 76343.9743 | 166.135 | 166.135 | 166.135 | 166.135 | 0 | -2758.1552 | 0 | 0 | 0 |  |  |  | 74250.359
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | -10866.2691 | 81.3677 | 81.3677 | 81.3677 | 81.3677 | 0 | 219.6972 | 0 | 0 | 0 |  |  |  | -10321.101
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | -14778.603 | 0 | 0 | 531.7228 | 0 | 0 | 8857.1455 | 0 | 0 | 0 |  |  |  | -5389.7347
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 670338.4004 | 500 | 498.78 | 1018.0033 | 500 | 0 | 7001.9436 | 0 | 0 | 0 | 0 | 0 | 0 | 679857.1274
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -29338.7904 | -500 | -498.78 | -1018.0033 | -500 | 0 | -7001.9436 | 0 | 0 | 0 |  |  |  | -38857.5174
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -0.28
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -519.8684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -519.8684
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 4837.1119 | 239.1148 | 242.1894 | 247.4402 | 250.5545 | 251.5985 | 281.8216 | 282.9958 | 284.175 | 285.359 |  |  |  | 7202.3606
4.3 | Total Adjustment | 4316.9635 | 239.1148 | 242.1894 | 247.4402 | 250.5545 | 251.5985 | 281.8216 | 282.9958 | 284.175 | 285.359 | 0 | 0 | 0 | 6682.2122
5 | Gross Profit (Item 3.0-4.3) | -33655.7539 | -739.1148 | -740.9694 | -1265.4435 | -750.5545 | -251.5985 | -7283.7652 | -282.9958 | -284.175 | -285.359 |  |  |  | -45539.7296
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 13939.0788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13939.0788
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 9292.7192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9292.7192
6.2 | Acc. Profit/(Loss) ~ B/F |  | -56887.5519 | -57626.6667 | -58367.6361 | -59633.0796 | -60383.6341 | -60635.2326 | -67918.9978 | -68201.9936 | -68486.1686
7 | Acc. Net Profit/(Loss) | -56887.5519 | -57626.6667 | -58367.6361 | -59633.0796 | -60383.6341 | -60635.2326 | -67918.9978 | -68201.9936 | -68486.1686 | -68771.5276 |  |  |  | -68771.5276
(=Item5.0 - 6.0 + 6.2)