## Financial Status
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-13
Project Code: | 968
Project Name: | Contract No. DC/2018/09 Rehabilitation of Trunk Sewers in Tuen Mun
Report Date: | 2025-12-31
Start Date: | 2018-12-28 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-03-31 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2023-12-01 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 205000 | 205000 | 0 | 205000 | 205000 | 205000 | 0 | 205000 | 205000 | 100% | 0 | 428279.8308 | 428280.1646 | 208.9% | -223280.1646
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 5476.51 | 25383.56 | 0 | 25383.56 | 126723.3988 | 126723.3988 | 0 | 126723.3988 | 71713.6 | 282.5% | -46330.04 | 0 | 0 | 0% | 71713.6
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 25480.08 | 25480.08 | 0 | 25480.08 | 14311.16 | 0% | -14311.16 | 0 | 0 | 0% | 14311.16
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 6124.68 | 13371.87 | 0 | 13371.87 | 52516.54 | 52516.54 | 0 | 52516.54 | 52429.896 | 392.1% | -39058.026 | 0 | 0 | 0% | 52429.896
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0.008 | 0% | -0.008
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 12333 | 12089.6 | 0 | 12089.6 | 3067.819 | 3067.819 | 0 | 3067.819 | 2966.76 | 24.54% | 9122.84 | -0.14 | -0.038 | -0.001281% | 2966.798
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 15492.6 | 15492.6 | 0 | 15492.6 | -48534.7856 | 0% | 48534.7856 | 0.19949 | -0.20051 | 0.0004131% | -48534.5851
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -0.24791 | 0% | 0.24791
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Income | 228934.19 | 255845.03 | 0 | 255845.03 | 428280.4378 | 428280.4378 | 0 | 428280.4378 | 297886.6304 | 116.4% | -42041.6004 | 428279.8903 | 428279.6862 | 143.8% | -130393.0557
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 19623.397 | 29952.64 | 0 | 29952.64 | 80028.454 | 80028.454 | 0 | 80028.454 | 79994.2226 | 267.1% | -50041.5826 | 79994.0344 | 79994.6344 | 100% | -0.41179
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 25 | 25 | 170 | 195 | 191.6396 | 0% | -191.6396 | 191.6396 | 191.2796 | 99.81% | 0.36
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 250 | 122.512 | 0% | -122.512 | 122.512 | 122.512 | 100% | 0
2.1.3 | -Manpower (Labour) | 0 | 7622.083 | 0 | 7622.083 | 15643 | 15643 | 0 | 15643 | 15420.888 | 202.3% | -7798.805 | 15420.8831 | 15420.8831 | 100% | 0.00492
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 1561.889 | 3702.16 | 0 | 3702.16 | 3541 | 3541 | 580 | 4121 | 4106.6833 | 110.9% | -404.5233 | 4106.6833 | 4108.6133 | 100% | -1.93
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 7686.756 | 28236.281 | 0 | 28236.281 | 38720 | 38720 | 0 | 38720 | 36097.8692 | 127.8% | -7861.5882 | 31951.6511 | 31635.0651 | 87.64% | 4462.804
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.7 | -Adm. Cost Messing | 1252.803 | 4602.007 | 0 | 4602.007 | 2500 | 2500 | 0 | 2500 | 2213.6186 | 48.1% | 2388.3884 | 2007.1258 | 2001.6898 | 90.43% | 211.9288
2.1.8 | -DSC | 1245.4 | 2528.73 | 0 | 2528.73 | 8956.305 | 8956.305 | 0 | 8956.305 | 8912.4318 | 352.4% | -6383.7018 | 7940.6962 | 7847.9462 | 88.06% | 1064.4856
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 1926.021 | 5668.525 | 0 | 5668.525 | 16197 | 16197 | 0 | 16197 | 11803.1916 | 208.2% | -6134.6666 | 10984.3897 | 9861.1062 | 83.55% | 1942.0854
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 0 | 0 | 0 | 6350 | 6350 | 1000 | 7350 | 7303.688 | 0% | -7303.688 | 6640.6271 | 6243.4321 | 85.48% | 1060.2559
2.2.2 | -Reinforcement | 0 | 0 | 0 | 0 | 2155 | 2155 | 0 | 2155 | 2149.2644 | 0% | -2149.2644 | 1124.4223 | 1124.4223 | 52.32% | 1024.8421
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 6154 | 6154 | -0.06 | 6153.94 | 5995.4202 | 0% | -5995.4202 | 4951.3909 | 4863.1909 | 81.12% | 1132.2294
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 78018.3 | 49000 | 0 | 49000 | 98849.671 | 98849.671 | 0 | 98849.671 | 98119.7489 | 200.2% | -49119.7489 | 67248.8264 | 63804.4837 | 65.03% | 34315.2652
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 3031.8132 | 8385.6287 | 0% | -8385.6287
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | -56690 | -56690 | -8971 | -65661 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 0 | 1149 | 0 | 1149 | 6000 | 6000 | 0 | 6000 | 5046.279 | 439.2% | -3897.279 | 5046.279 | 597.279 | 11.84% | 4449
2.3.2 | -Plant, Equipments & Tools (external hire) | 3220 | 6777 | 0 | 6777 | 44250 | 44250 | 150 | 44400 | 36821.7454 | 543.3% | -30044.7454 | 19882.8557 | 17926.2388 | 48.68% | 18895.5066
2.3.3 | -Diesel & Lubricant | 0 | 189.5 | 0 | 189.5 | 924 | 924 | 2 | 926 | 925.0493 | 488.2% | -735.5493 | 917.9067 | 914.7267 | 98.88% | 10.3225
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 990 | 990 | 16 | 1006 | 1005.0599 | 0% | -1005.0599 | 1005.0599 | 1005.0599 | 100% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | -24803 | -24803 | -210 | -25013 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 99817.041 | 101834.527 | 0 | 101834.527 | 190240.714 | 190240.714 | 0 | 190240.714 | 180211.9341 | 177% | -78377.407 | 143859.7818 | 138399.3517 | 76.8% | 41812.5824
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 34000 | 34000 | 7473 | 41473 | 41435.4798 | 0% | -41435.4798 | 36397.1627 | 32867.684 | 79.32% | 8567.7958
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | -278.3088 | 1417.0262 | 0% | -1417.0262
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 243 | 0% | -243
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -7187.7382 | 0% | 7187.7382
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -53990 | -53990 | -210 | -54200 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 214351.607 | 241262.453 | 0 | 241262.453 | 420291.144 | 420291.144 | -0.06 | 420291.084 | 537876.7258 | 222.9% | -296614.2728 | 442547.4322 | 421787.5157 | 78.42% | 116089.2101
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 14582.583 | 14582.577 | 0 | 14582.577 | 7989.2938 | 7989.2938 | 0.06 | 7989.3538 | -239990.0953 | -1646% | 254572.6723 | -14267.542 | 6492.1705 | -2.705% | -246482.2658
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | 0 |  |  | 0 | 0 | 0% |  | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | -990 |  |  | -1006 | -1005.0599 | 0% |  | -1005.0599 | -1005.0599 | 100% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | 0 |  |  | 2862.9433 | 2862.9433 | 0% | -2862.9433 | 2862.9433 | 2862.9433 | 100% | 1.7531e-09
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | -990 |  |  | 1856.9433 | 1857.8834 | 0% | -1857.8834 | 1857.8834 | 1857.8834 | 100% | 1.7531e-09
5 | Gross Profit (Item 3.0-4.3) | 14582.583 | 14582.577 | 0 | 14582.577 | 8979.2938 |  |  | 6132.4105 | -241847.9787 | -1658% | 256430.5557 | -16125.4254 | 4634.2871 | -1.916% | -246482.2658
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 13736.0514 | 15350.7018 | 0 | 15350.7018 | 25696.8263 |  |  | 12848.4131 | 8936.5989 | 58.22% | 6414.1029 | 12920.0667 | 12920.0606 | 144.6% | -3983.4617
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 4578.6838 | 5116.9006 | 0 | 5116.9006 | 8565.6088 |  |  | 8565.6088 | 5957.7326 | 116.4% | -840.832 | 8565.5978 | 8565.5937 | 143.8% | -2607.8611
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -3732.1522 | -5885.0254 | 0 | -5885.0254 | -25283.1412 |  |  | -15281.6114 | -256742.3103 | 4363% | 250857.2849 | -37611.0899 | -16851.3672 | 6.564% | -239890.943
(=Item5.0 - 6.0 + 6.2)

## Projection
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-13
Project Code: | 968
Project Name: | Contract No. DC/2018/09 Rehabilitation of Trunk Sewers in Tuen Mun
Report Date: | 2025-12-31
Start Date: | 2018-12-28 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-03-31 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2023-12-01 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 205000
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 126723.3988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 126723.3988
1.2.2 | -Fee of C.E. | 25480.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 25480.08
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 52516.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 52516.54
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 3067.819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3067.819
1.12.2 | -Pain Gain Sharing | 15492.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15492.6
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 428280.4378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428280.4378
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 80028.454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 80028.454
2.1.13 | -Manpower (HO-Consultant) | 25 | 0 | 0 | 0 | 20 | 30 | 30 | 0 | 0 | 90 |  |  |  | 195
2.1.2 | -Manpower (RE) | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 250
2.1.3 | -Manpower (Labour) | 15643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15643
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 3191 | 300 | 50 | 50 | 0 | 0 | 30 | 500 | 0 | 0 |  |  |  | 4121
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 38620 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 38720
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2500
2.1.8 | -DSC | 8956.305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8956.305
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 16197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16197
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 6150 | 200 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 |  |  |  | 7350
2.2.2 | -Reinforcement | 2155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2155
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 6153.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6153.94
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 98849.671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 98849.671
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | -56040 | -550 | -100 | 0 | -20 | 0 | 0 | -8861 | 0 | -90 |  |  |  | -65661
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6000
2.3.2 | -Plant, Equipments & Tools (external hire) | 44250 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 |  |  |  | 44400
2.3.3 | -Diesel & Lubricant | 904 | 0 | 20 | 0 | 0 | 0 | 1 | 1 | 0 | 0 |  |  |  | 926
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 990 | 0 | 0 | 0 | 0 | 13 | 3 | 0 | 0 | 0 |  |  |  | 1006
2.3.8 | -Potential Savings (Plants) | -24783 | 0 | -20 | -50 | 0 | -160 | 0 | 0 | 0 | 0 |  |  |  | -25013
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 190240.714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 190240.714
2.4.2 | -Variation | 33600 | 0 | 400 | 0 | 0 | 7100 | 223 | 0 | 0 | 150 |  |  |  | 41473
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | -53590 | 0 | -400 | 0 | 0 | -60 | 0 | 0 | 0 | -150 |  |  |  | -54200
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 420291.084 | 0 | 0 | 0 | 0 | 7073 | 287 | -7360 | 0 | 0 | 0 | 0 | 0 | 420291.084
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 7989.3538 | 0 | 0 | 0 | 0 | -7073 | -287 | 7360 | 0 | 0 |  |  |  | 7989.3538
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -990 | 0 | 0 | 0 | 0 | -13 | -3 | 0 | 0 | 0 |  |  |  | -1006
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 2058.4372 | 97.206 | 100.3693 | 103.6212 | 108.6088 | 109.3285 | 69.7645 | 71.2922 | 74.3929 | 69.9227 |  |  |  | 2862.9433
4.3 | Total Adjustment | 1068.4372 | 97.206 | 100.3693 | 103.6212 | 108.6088 | 96.3285 | 66.7645 | 71.2922 | 74.3929 | 69.9227 | 0 | 0 | 0 | 1856.9433
5 | Gross Profit (Item 3.0-4.3) | 6920.9166 | -97.206 | -100.3693 | -103.6212 | -108.6088 | -7169.3285 | -353.7645 | 7288.7078 | -74.3929 | -69.9227 |  |  |  | 6132.4105
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 12848.4131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12848.4131
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 8565.6088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8565.6088
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -14493.1053 | -97.206 | -100.3693 | -103.6212 | -108.6088 | -7169.3285 | -353.7645 | 7288.7078 | -74.3929 | -69.9227 |  |  |  | -15281.6114
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-13
Project Code: | 968
Project Name: | Contract No. DC/2018/09 Rehabilitation of Trunk Sewers in Tuen Mun
Report Date: | 2025-12-31
Start Date: | 2018-12-28 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-03-31 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2023-12-01 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 205000
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 71713.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 71713.6
1.2.2 | -Fee of C.E. | 14311.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14311.16
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 52429.896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 52429.896
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 2966.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2966.76
1.12.2 | -Pain Gain Sharing | -48534.7856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -48534.7856
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 297886.6304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297886.6304
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 79994.2226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 79994.2226
2.1.13 | -Manpower (HO-Consultant) | 22.112 | -3 | 3.94 | 0 | 12.69 | 37.3476 | 29.81 | -3.27 | 3.94 | 88.07 |  |  |  | 191.6396
2.1.2 | -Manpower (RE) | 122.512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 122.512
2.1.3 | -Manpower (Labour) | 15420.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15420.888
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 3092.8627 | 431.9645 | 47.604 | 46.529 | 0 | 0 | 0 | 46.104 | 441.6191 | 0 |  |  |  | 4106.6833
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 38610.2732 | 42.3779 | 47.103 | 26.5115 | -43.2763 | -66.278 | -2672.6373 | 9.5483 | 136.666 | 7.5809 |  |  |  | 36097.8692
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 2213.6186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2213.6186
2.1.8 | -DSC | 8912.4318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8912.4318
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 16158.1916 | 0 | 0 | 0 | 0 | 0 | -4355 | 0 | 0 | 0 |  |  |  | 11803.1916
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 6146.0105 | 142.632 | 0 | 60.885 | 0 | 0 | 0 | 0 | 954.1605 | 0 |  |  |  | 7303.688
2.2.2 | -Reinforcement | 2149.2644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2149.2644
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 6013.8202 | 0 | 0 | 0 | 0 | 0 | -18.4 | 0 | 0 | 0 |  |  |  | 5995.4202
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 98363.1989 | 16.762 | 0 | 3.09 | 61.698 | 0 | -325 | 0 | 0 | 0 |  |  |  | 98119.7489
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 5046.279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5046.279
2.3.2 | -Plant, Equipments & Tools (external hire) | 43880.2114 | 91.3 | 18 | 71.75 | 163.8 | 55.6 | -7463.416 | 0 | 4.5 | 0 |  |  |  | 36821.7454
2.3.3 | -Diesel & Lubricant | 896.6581 | 6.0984 | 4.2624 | 4.653 | 7.7729 | 0 | 4.0272 | 1.5772 | 0 | 0 |  |  |  | 925.0493
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 985.2858 | 3.8487 | 3.8486 | 3.8486 | 2.7428 | 2.7428 | 2.7428 | 0 | 0 | 0 |  |  |  | 1005.0599
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 180211.9341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 180211.9341
2.4.2 | -Variation | 41435.4798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 41435.4798
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 549675.2547 | 731.9834 | 124.758 | 217.2671 | 205.4274 | 29.4124 | -14797.8733 | 53.9595 | 1540.8856 | 95.6509 | 0 | 0 | 0 | 537876.7258
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -251788.6243 | -731.9834 | -124.758 | -217.2671 | -205.4274 | -29.4124 | 14797.8733 | -53.9595 | -1540.8856 | -95.6509 |  |  |  | -239990.0953
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -985.2858 | -3.8487 | -3.8486 | -3.8486 | -2.7428 | -2.7428 | -2.7428 | 0 | 0 | 0 |  |  |  | -1005.0599
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 2058.4372 | 97.206 | 100.3693 | 103.6212 | 108.6088 | 109.3285 | 69.7645 | 71.2922 | 74.3929 | 69.9227 |  |  |  | 2862.9433
4.3 | Total Adjustment | 1073.1514 | 93.3573 | 96.5207 | 99.7726 | 105.8661 | 106.5858 | 67.0217 | 71.2922 | 74.3929 | 69.9227 | 0 | 0 | 0 | 1857.8834
5 | Gross Profit (Item 3.0-4.3) | -252861.7757 | -825.3407 | -221.2787 | -317.0397 | -311.2935 | -135.9981 | 14730.8516 | -125.2517 | -1615.2785 | -165.5736 |  |  |  | -241847.9787
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 8936.5989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8936.5989
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 5957.7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5957.7326
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -267756.1072 | -825.3407 | -221.2787 | -317.0397 | -311.2935 | -135.9981 | 14730.8516 | -125.2517 | -1615.2785 | -165.5736 |  |  |  | -256742.3103
(=Item5.0 - 6.0 + 6.2)

## Accrual
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-13
Project Code: | 968
Project Name: | Contract No. DC/2018/09 Rehabilitation of Trunk Sewers in Tuen Mun
Report Date: | 2025-12-31
Start Date: | 2018-12-28 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-03-31 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2023-12-01 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 425890.8308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2389 |  |  |  | 428279.8308
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | -0.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -0.14
1.12.2 | -Pain Gain Sharing | 0.19949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.19949
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 425890.8903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2389 | 0 | 0 | 0 | 428279.8903
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 79994.0344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 79994.0344
2.1.13 | -Manpower (HO-Consultant) | 22.112 | -3 | 3.94 | 0 | 12.69 | 37.3476 | 29.81 | -3.27 | 3.94 | 88.07 |  |  |  | 191.6396
2.1.2 | -Manpower (RE) | 122.512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 122.512
2.1.3 | -Manpower (Labour) | 15420.8831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15420.8831
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 3092.8627 | 431.9645 | 47.604 | 46.529 | 0 | 0 | 0 | 46.104 | 441.6191 | 0 |  |  |  | 4106.6833
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 34664.2705 | 6.8535 | 16.438 | 26.5115 | -43.2763 | -66.278 | -2672.6373 | 11.4033 | 0.785 | 7.5809 |  |  |  | 31951.6511
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 2007.1258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2007.1258
2.1.8 | -DSC | 7940.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7940.6962
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 15145.2207 | 2.471 | -1.037 | 5.345 | 0.735 | -63.135 | -4355 | 249.79 | 0 | 0 |  |  |  | 10984.3897
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 5482.9496 | 159.6075 | 43.9095 | 0 | 0 | 0 | 0 | 954.1605 | 0 | 0 |  |  |  | 6640.6271
2.2.2 | -Reinforcement | 1124.4223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1124.4223
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 4969.7909 | 0 | 0 | 0 | 0 | 0 | -18.4 | 0 | 0 | 0 |  |  |  | 4951.3909
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 67552.2764 | 16.762 | 3.09 | 61.698 | 0 | -60 | -325 | 0 | 0 | 0 |  |  |  | 67248.8264
2.2.14 | -Deposit | 3323.7332 | 0 | 0 | 0 | 0 | -58 | 0 | -233.92 | 0 | 0 |  |  |  | 3031.8132
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 5046.279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5046.279
2.3.2 | -Plant, Equipments & Tools (external hire) | 26452.3204 | 238.122 | 344.9 | 27.84 | 296.62 | 10.6 | -7594.666 | 107.1193 | 0 | 0 |  |  |  | 19882.8557
2.3.3 | -Diesel & Lubricant | 889.5156 | 10.3608 | 4.653 | 0 | 7.7729 | 0 | 0 | 5.6044 | 0 | 0 |  |  |  | 917.9067
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 985.2858 | 3.8487 | 3.8486 | 3.8486 | 2.7428 | 2.7428 | 2.7428 | 0 | 0 | 0 |  |  |  | 1005.0599
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 143484.3474 | 0 | 0 | 345.9468 | 0 | 0 | 0 | 0 | 29.4876 | 0 |  |  |  | 143859.7818
2.4.2 | -Variation | 27185.863 | 772.6563 | 0 | 0 | 0 | 8325.6602 | 0 | 0 | 112.9833 | 0 |  |  |  | 36397.1627
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 727.9307 | -449.7736 | 0 | 0 | 0 | -549.8325 | -6.6334 | 0 | 0 | 0 |  |  |  | -278.3088
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 445634.4316 | 1189.8726 | 467.3461 | 517.7189 | 277.2844 | 7579.1051 | -14939.7839 | 1136.9915 | 588.815 | 95.6509 | 0 | 0 | 0 | 442547.4322
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -19743.5413 | -1189.8726 | -467.3461 | -517.7189 | -277.2844 | -7579.1051 | 14939.7839 | -1136.9915 | -588.815 | 2293.3491 |  |  |  | -14267.542
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -985.2858 | -3.8487 | -3.8486 | -3.8486 | -2.7428 | -2.7428 | -2.7428 | 0 | 0 | 0 |  |  |  | -1005.0599
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 2058.4372 | 97.206 | 100.3693 | 103.6212 | 108.6088 | 109.3285 | 69.7645 | 71.2922 | 74.3929 | 69.9227 |  |  |  | 2862.9433
4.3 | Total Adjustment | 1073.1514 | 93.3573 | 96.5207 | 99.7726 | 105.8661 | 106.5858 | 67.0217 | 71.2922 | 74.3929 | 69.9227 | 0 | 0 | 0 | 1857.8834
5 | Gross Profit (Item 3.0-4.3) | -20816.6928 | -1283.2299 | -563.8668 | -617.4915 | -383.1505 | -7685.6908 | 14872.7622 | -1208.2838 | -663.2079 | 2223.4264 |  |  |  | -16125.4254
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 12776.7267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.34 |  |  |  | 12920.0667
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 8517.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.78 |  |  |  | 8565.5978
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -42111.2373 | -1283.2299 | -563.8668 | -617.4915 | -383.1505 | -7685.6908 | 14872.7622 | -1208.2838 | -663.2079 | 2032.3064 |  |  |  | -37611.0899
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-13
Project Code: | 968
Project Name: | Contract No. DC/2018/09 Rehabilitation of Trunk Sewers in Tuen Mun
Report Date: | 2025-12-31
Start Date: | 2018-12-28 |  |  |  |  | Monthly Financial Report
Complete Date: | 2023-03-31 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2023-12-01 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 427975.1646 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 428280.1646
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.008
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 2223.962 | 0 | -2224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -0.038
1.12.2 | -Pain Gain Sharing | -1980.2005 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -0.20051
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | -2328.2479 | 0 | -61 | 0 | 0 | 0 | 0 | 0 | 0 | 2389 |  |  |  | -0.24791
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 425890.6862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2389 | 0 | 0 | 0 | 428279.6862
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 79994.6344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 79994.6344
2.1.13 | -Manpower (HO-Consultant) | 21.752 | -3 | 3.94 | 0 | 12.69 | 37.3476 | 29.81 | -3.27 | 3.94 | 88.07 |  |  |  | 191.2796
2.1.2 | -Manpower (RE) | 122.512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 122.512
2.1.3 | -Manpower (Labour) | 15420.8831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15420.8831
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 3065.4097 | 0 | 1.5 | 29.808 | 478.0685 | 0 | 0 | 46.104 | 441.6191 | 46.104 |  |  |  | 4108.6133
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 34220.1738 | 23.2669 | 57.7887 | 24.5195 | -11.3968 | -48.0771 | -2672.6373 | 4.5993 | 35.98 | 0.848 |  |  |  | 31635.0651
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 2001.6898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2001.6898
2.1.8 | -DSC | 7847.9462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7847.9462
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 13771.0522 | 3.66 | 13.169 | 51.125 | 52.64 | 71.15 | -4352.215 | 250.525 | 0 | 0 |  |  |  | 9861.1062
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 5395.3157 | 0 | 142.632 | 57.4779 | 60.885 | 0 | 0 | 0 | 0 | 587.1215 |  |  |  | 6243.4321
2.2.2 | -Reinforcement | 1081.1319 | 0 | 43.2904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1124.4223
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 4862.8309 | 0 | 0 | 18.76 | 0 | 0 | -18.4 | 0 | 0 | 0 |  |  |  | 4863.1909
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 63954.7375 | 47.215 | 16.762 | 12.9832 | 3.09 | 61.698 | -325 | 32.998 | 0 | 0 |  |  |  | 63804.4837
2.2.14 | -Deposit | 8677.5487 | 0 | 0 | 0 | 0 | -58 | 0 | -233.92 | 0 | 0 |  |  |  | 8385.6287
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 597.279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 597.279
2.3.2 | -Plant, Equipments & Tools (external hire) | 23929.4726 | 327.51 | 0 | 122.1742 | 492.77 | 0 | -7594.666 | 133.694 | 186.8 | 328.484 |  |  |  | 17926.2388
2.3.3 | -Diesel & Lubricant | 867.6684 | 12.3564 | 6.8484 | 0 | 4.653 | 0 | 7.7729 | 10.8836 | 4.5439 | 0 |  |  |  | 914.7267
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 985.2858 | 3.8487 | 3.8486 | 3.8486 | 2.7428 | 2.7428 | 2.7428 | 0 | 0 | 0 |  |  |  | 1005.0599
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 138399.3517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 138399.3517
2.4.2 | -Variation | 26374.747 | 0 | 376.073 | 333.3773 | 0 | 0 | 5783.4867 | 0 | 0 | 0 |  |  |  | 32867.684
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 1869.6477 | 0 | 0 | 0 | 0 | 0 | -452.6215 | 0 | 0 | 0 |  |  |  | 1417.0262
2.4.5 | -Down Payment | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 243
2.4.6 | -Retention | -7262.6488 | 0 | 0 | 29.8614 | 0 | 0 | -10.2265 | 55.2757 | 0 | 0 |  |  |  | -7187.7382
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 426441.4213 | 414.857 | 665.8522 | 683.9352 | 1096.1425 | 66.8613 | -9601.9539 | 296.8896 | 672.883 | 1050.6275 | 0 | 0 | 0 | 421787.5157
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -550.7351 | -414.857 | -665.8522 | -683.9352 | -1096.1425 | -66.8613 | 9601.9539 | -296.8896 | -672.883 | 1338.3725 |  |  |  | 6492.1705
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -985.2858 | -3.8487 | -3.8486 | -3.8486 | -2.7428 | -2.7428 | -2.7428 | 0 | 0 | 0 |  |  |  | -1005.0599
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 2058.4372 | 97.206 | 100.3693 | 103.6212 | 108.6088 | 109.3285 | 69.7645 | 71.2922 | 74.3929 | 69.9227 |  |  |  | 2862.9433
4.3 | Total Adjustment | 1073.1514 | 93.3573 | 96.5207 | 99.7726 | 105.8661 | 106.5858 | 67.0217 | 71.2922 | 74.3929 | 69.9227 | 0 | 0 | 0 | 1857.8834
5 | Gross Profit (Item 3.0-4.3) | -1623.8866 | -508.2143 | -762.3729 | -783.7078 | -1202.0085 | -173.4471 | 9534.9322 | -368.1818 | -747.276 | 1268.4498 |  |  |  | 4634.2871
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 12776.7206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.34 |  |  |  | 12920.0606
6.1.2 | BU Overhead (2.0000% of Total Income excl. PC & Provisional Sum) | 8517.8137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.78 |  |  |  | 8565.5937
6.2 | Acc. Profit/(Loss) ~ B/F |  | -22918.4209 | -23426.6351 | -24189.008 | -24972.7158 | -26174.7243 | -26348.1714 | -16813.2392 | -17181.4211 | -17928.697
7 | Acc. Net Profit/(Loss) | -22918.4209 | -23426.6351 | -24189.008 | -24972.7158 | -26174.7243 | -26348.1714 | -16813.2392 | -17181.4211 | -17928.697 | -16851.3672 |  |  |  | -16851.3672
(=Item5.0 - 6.0 + 6.2)