## Financial Status
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 985
Project Name: | Hong Kong Disneyland - Arendelle Completion Package
Report Date: | 2025-12-31
Start Date: | 2019-06-15 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-05-18 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2023-09-30 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 1011828 | 1063800 | -51972 | 1011828 | 1011828 | 1011828 | 0 | 1011828 | 1011828 | 100% | 0 | 1011827.91 | 1011828.14 | 100% | -0.14
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 415996.196 | -342245.2 | 73750.996 | 7946.34 | 7946.34 | 0 | 7946.34 | 7946.34 | 10.77% | 65804.656 | 7936.28 | 3870 | 48.7% | 4076.34
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 203433 | 203433 | 201138.66 | 201138.66 | 0 | 201138.66 | 201138.66 | 98.87% | 2294.34 | 201139.3 | 201138.68 | 100% | -0.02
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 51972 | 0 | -77 | -77 | 0 | 0 | 0 | 0 | 0 | 0% | -77 | 0 | 0 | 0% | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 18856 | 18856 | 513407 | 513407 | 10 | 513417 | 513416 | 2723% | -494560 | 513416 | 517550 | 100.8% | -4134
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -0.24714 | 0% | 0.24714
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Income | 1063800 | 1479796.196 | -172005.2 | 1307790.996 | 1734320 | 1734320 | 10 | 1734330 | 1734329 | 132.6% | -426538.004 | 1734319.49 | 1734386.5729 | 100% | -57.5729
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 69516.706 | 108112.514 | 0 | 108112.514 | 162553 | 162553 | 121 | 162674 | 162633.254 | 150.4% | -54520.74 | 162633.254 | 162633.254 | 100% | 0
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 0 | 0 | 411 | 411 | 402.1855 | 0% | -402.1855 | 402.1855 | 402.1872 | 100% | -0.0017
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.3 | -Manpower (Labour) | 0 | 0 | 0 | 0 | 35187 | 35187 | -2 | 35185 | 35172.995 | 0% | -35172.995 | 35172.995 | 35172.8051 | 100% | 0.19
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 10415 | 13376.714 | 0 | 13376.714 | 13053 | 13053 | 200 | 13253 | 12885.6432 | 96.33% | 491.0708 | 12885.6432 | 12885.6432 | 100% | 0
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 15794.527 | 19123.118 | 0 | 19123.118 | 26081 | 26081 | 4320 | 30401 | 30382.3247 | 158.9% | -11259.2067 | 29787.1285 | 29190.8164 | 96.08% | 1191.5083
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 88 | 88 | 0 | 88 | 82.6073 | 0% | -82.6073 | 82.6073 | 82.6073 | 100% | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0 | 0 | 309 | 309 | 7 | 316 | 315.2727 | 0% | -315.2727 | 315.2727 | 315.2727 | 100% | 0
2.1.8 | -DSC | 17976.578 | 41582.906 | 0 | 41582.906 | 37663 | 37663 | 987 | 38650 | 36704.5799 | 88.27% | 4878.3261 | 35791.7579 | 35791.7579 | 97.51% | 912.822
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 567.645 | 2907.8115 | 0 | 2907.8115 | 5381 | 5381 | -25 | 5356 | 5352.1653 | 184.1% | -2444.3538 | 5166.9871 | 5156.4721 | 96.34% | 195.6932
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 0 | 495 | 0 | 495 | 8156.5 | 8156.5 | 0 | 8156.5 | 8150.0817 | 1646% | -7655.0817 | 7136.7761 | 7086.4842 | 86.95% | 1063.5975
2.2.2 | -Reinforcement | 0 | 15016.1928 | 0 | 15016.1928 | 14923.88 | 14923.88 | -8 | 14915.88 | 14906.0452 | 99.27% | 110.1476 | 13000.6825 | 13000.6825 | 87.22% | 1905.3627
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 485 | 485 | -15 | 470 | 468.598 | 0% | -468.598 | 468.598 | 468.598 | 100% | 0
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 82100.399 | 426716.729 | 0 | 426716.729 | 12190.62 | 12190.62 | 0 | 12190.62 | 12188.1831 | 2.856% | 414528.5459 | 11471.5706 | 10391.9015 | 85.26% | 1796.2816
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 2858.7931 | 3805.2893 | 0% | -3805.2893
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | -2023 | -2023 | -8000 | -10023 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1519.448 | 2638.348 | 0 | 2638.348 | 738 | 738 | 0 | 738 | 679.078 | 25.74% | 1959.27 | 552.478 | 712.478 | 104.9% | -33.4
2.3.2 | -Plant, Equipments & Tools (external hire) | 16570.813 | 20305.413 | 0 | 20305.413 | 35140 | 35140 | 1950 | 37090 | 37081.6173 | 182.6% | -16776.2043 | 30452.3022 | 30428.2497 | 82.06% | 6653.3676
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 3409 | 3409 | -115 | 3294 | 3205.142 | 0% | -3205.142 | 3205.142 | 3205.142 | 100% | 0
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 140 | 140 | 0 | 140 | 94.2699 | 0% | -94.2699 | 90.6699 | 90.6699 | 96.18% | 3.6
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -139.3974 | 0% | 139.3974 | -139.3974 | -139.3974 | 100% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 150 | 150 | -0.45 | 149.55 | 123.7793 | 0% | -123.7793 | 123.7793 | 123.7793 | 100% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 786532.358 | 767517.4237 | 0 | 767517.4237 | 877251.34 | 877251.34 | 16506 | 893757.34 | 893338.9201 | 116.4% | -125821.4964 | 882009.265 | 866821.7295 | 97.03% | 26517.1906
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 261122.5 | 261122.5 | 38264 | 299386.5 | 285226.5351 | 0% | -285226.5351 | 292865.1258 | 288001.7918 | 101% | -2775.2567
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 18557.6108 | 18901.086 | 0% | -18901.086
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 66000 | 66000 | -14350 | 51650 | 7874.6351 | 0% | -7874.6351 | 7394.7178 | 51649.6864 | 655.9% | -43775.0513
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -33029.1876 | 0% | 33029.1876
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -77646 | -77646 | -40180 | -117826 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 175717.66 | 175717.66 | 0 | 175717.66 | 175716.9067 | 0% | -175716.9067 | 175716.9067 | 175716.9068 | 100% | -0.00014
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 1000993.474 | 1417792.17 | 0 | 1417792.17 | 1656070.5 | 1656070.5 | 70.55 | 1656141.05 | 1722845.4219 | 121.5% | -305053.2519 | 1728002.8515 | 1718866.7057 | 99.77% | 3978.7162
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 62806.526 | 62004.026 | -172005.2 | -110001.174 | 78249.5 | 78249.5 | -60.55 | 78188.95 | 11483.5781 | -10.44% | -121484.7521 | 6316.6385 | 15519.8672 | 135.1% | -4036.2891
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | -88 |  |  | -88 | -82.6073 | 0% |  | -82.6073 | -82.6073 | 100% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | -150 |  |  | -149.55 | -123.7793 | 0% |  | -123.7793 | -123.7793 | 100% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | 0 |  |  | 1234.0081 | 1234.0081 | 0% | -1234.0081 | 1234.0081 | 1234.0081 | 100% | -2.9927e-09
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | -238 |  |  | 996.4581 | 1027.6215 | 0% | -1027.6215 | 1027.6215 | 1027.6215 | 100% | -2.9927e-09
5 | Gross Profit (Item 3.0-4.3) | 62806.526 | 62004.026 | -172005.2 | -110001.174 | 78487.5 |  |  | 77192.4919 | 10455.9566 | -9.505% | -120457.1306 | 5289.017 | 14492.2457 | 138.6% | -4036.2891
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 63828 | 88787.7718 | -22526.292 | 66261.4798 | 91990.8804 |  |  | 45995.7402 | 45995.7102 | 69.42% | 20265.7696 | 45995.4057 | 45997.4368 | 100% | -1.7266
6.1.2 | BU Overhead (1.1000% of Total Income excl. PC & Provisional Sum) | 11701.8 | 16277.7582 | -4129.8202 | 12147.938 | 16864.9947 |  |  | 16865.1047 | 16865.0937 | 138.8% | -4717.1558 | 16864.9821 | 16865.7268 | 100% | -0.63308
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -12723.274 | -43061.5039 | -145349.0878 | -188410.5917 | -30368.3751 |  |  | 14331.647 | -52404.8473 | 27.81% | -136005.7444 | -57571.3708 | -48370.9179 | 92.3% | -4033.9294
(=Item5.0 - 6.0 + 6.2)

## Projection
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 985
Project Name: | Hong Kong Disneyland - Arendelle Completion Package
Report Date: | 2025-12-31
Start Date: | 2019-06-15 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-05-18 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2023-09-30 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 1011828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1011828
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 7946.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7946.34
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 201138.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 201138.66
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 513417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 513417
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 1734330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1734330
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 162674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 162674
2.1.13 | -Manpower (HO-Consultant) | 176 | 0 | 40 | 0 | 35 | 50 | 30 | 10 | 30 | 40 |  |  |  | 411
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 35185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 35185
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 13253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13253
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 29158 | 210 | 180 | 8 | 40 | 115 | 35 | 350 | 155 | 150 |  |  |  | 30401
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 88
2.1.7 | -Adm. Cost Messing | 311 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  |  |  | 316
2.1.8 | -DSC | 39645 | 0 | 0 | 0 | -75 | -120 | -70 | -360 | -180 | -190 |  |  |  | 38650
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 5356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5356
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 8156.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8156.5
2.2.2 | -Reinforcement | 14923.88 | 0 | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14915.88
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 470
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 12190.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12190.62
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | -10023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -10023
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 738
2.3.2 | -Plant, Equipments & Tools (external hire) | 37090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 37090
2.3.3 | -Diesel & Lubricant | 3294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3294
2.3.4 | -Repairing | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 140
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 149.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 149.55
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 893757.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 893757.34
2.4.2 | -Variation | 299816.5 | -210 | -220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 299386.5
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 51650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 51650
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | -117826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -117826
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 175717.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 175717.66
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 1656091.05 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1656141.05
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 78238.95 | 0 | 0 | 0 | 0 | -45 | 0 | 0 | -5 | 0 |  |  |  | 78188.95
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -88
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -149.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -149.55
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -74.8589 | 94.349 | 117.3044 | 123.3884 | 126.6977 | 127.1345 | 155.2441 | 177.1929 | 186.8469 | 200.7092 |  |  |  | 1234.0081
4.3 | Total Adjustment | -312.4089 | 94.349 | 117.3044 | 123.3884 | 126.6977 | 127.1345 | 155.2441 | 177.1929 | 186.8469 | 200.7092 | 0 | 0 | 0 | 996.4581
5 | Gross Profit (Item 3.0-4.3) | 78551.3589 | -94.349 | -117.3044 | -123.3884 | -126.6977 | -172.1345 | -155.2441 | -177.1929 | -191.8469 | -200.7092 |  |  |  | 77192.4919
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 45995.7402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 45995.7402
6.1.2 | BU Overhead (1.1000% of Total Income excl. PC & Provisional Sum) | 16865.1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16865.1047
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 15690.5139 | -94.349 | -117.3044 | -123.3884 | -126.6977 | -172.1345 | -155.2441 | -177.1929 | -191.8469 | -200.7092 |  |  |  | 14331.647
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 985
Project Name: | Hong Kong Disneyland - Arendelle Completion Package
Report Date: | 2025-12-31
Start Date: | 2019-06-15 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-05-18 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2023-09-30 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 1011828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1011828
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 7946.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7946.34
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 201138.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 201138.66
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 513416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 513416
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 1734329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1734329
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 162672.694 | -39.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 162633.254
2.1.13 | -Manpower (HO-Consultant) | 154.72 | 10.42 | 45.79 | 0 | 37.6 | 49.57 | 31.27 | 9.6855 | 31 | 32.13 |  |  |  | 402.1855
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 35180.035 | -2.54 | 0 | 0 | 0 | 0 | 0 | -4.5 | 0 | 0 |  |  |  | 35172.995
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 13226.6513 | -194.2581 | 0 | 0 | 0 | -139.1 | 0 | -7.65 | 0 | 0 |  |  |  | 12885.6432
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 29152.8657 | 213.0015 | 55.5783 | 133.7362 | 34.245 | 67.679 | 85.715 | 58.7666 | 262.7561 | 317.9813 |  |  |  | 30382.3247
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 82.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 82.6073
2.1.7 | -Adm. Cost Messing | 310.2328 | 0 | 0 | 0 | 0 | 0 | 5.04 | 0 | 0 | 0 |  |  |  | 315.2727
2.1.8 | -DSC | 36704.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36704.5799
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 5352.1653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5352.1653
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 8150.0817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8150.0817
2.2.2 | -Reinforcement | 14906.0452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14906.0452
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 468.598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 468.598
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 12188.1831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12188.1831
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 679.078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 679.078
2.3.2 | -Plant, Equipments & Tools (external hire) | 37081.6173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 37081.6173
2.3.3 | -Diesel & Lubricant | 3205.142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3205.142
2.3.4 | -Repairing | 94.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 94.2699
2.3.5 | -Resale | -139.3974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -139.3974
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 123.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 123.7793
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 893338.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 893338.9201
2.4.2 | -Variation | 285226.5351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 285226.5351
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 7874.6351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7874.6351
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 175716.9067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 175716.9067
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 1721750.9455 | -12.8166 | 101.3683 | 133.7362 | 71.845 | -21.851 | 122.025 | 56.3021 | 293.7561 | 350.1113 | 0 | 0 | 0 | 1722845.4219
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 12578.0545 | 12.8166 | -101.3683 | -133.7362 | -71.845 | 21.851 | -122.025 | -56.3021 | -293.7561 | -350.1113 |  |  |  | 11483.5781
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -82.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -82.6073
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -123.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -123.7793
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -74.8589 | 94.349 | 117.3044 | 123.3884 | 126.6977 | 127.1345 | 155.2441 | 177.1929 | 186.8469 | 200.7092 |  |  |  | 1234.0081
4.3 | Total Adjustment | -281.2455 | 94.349 | 117.3044 | 123.3884 | 126.6977 | 127.1345 | 155.2441 | 177.1929 | 186.8469 | 200.7092 | 0 | 0 | 0 | 1027.6215
5 | Gross Profit (Item 3.0-4.3) | 12859.3 | -81.5324 | -218.6726 | -257.1246 | -198.5427 | -105.2835 | -277.2691 | -233.495 | -480.603 | -550.8205 |  |  |  | 10455.9566
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 45995.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 45995.7102
6.1.2 | BU Overhead (1.1000% of Total Income excl. PC & Provisional Sum) | 16865.0937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16865.0937
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -50001.504 | -81.5324 | -218.6726 | -257.1246 | -198.5427 | -105.2835 | -277.2691 | -233.495 | -480.603 | -550.8205 |  |  |  | -52404.8473
(=Item5.0 - 6.0 + 6.2)

## Accrual
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 985
Project Name: | Hong Kong Disneyland - Arendelle Completion Package
Report Date: | 2025-12-31
Start Date: | 2019-06-15 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-05-18 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2023-09-30 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 1011827.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1011827.91
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 7936.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7936.28
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 201139.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 201139.3
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 513416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 513416
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 1734319.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1734319.49
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 162672.694 | -39.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 162633.254
2.1.13 | -Manpower (HO-Consultant) | 154.72 | 10.42 | 45.79 | 0 | 37.6 | 49.57 | 31.27 | 9.6855 | 31 | 32.13 |  |  |  | 402.1855
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 35180.035 | -2.54 | 0 | 0 | 0 | 0 | 0 | -4.5 | 0 | 0 |  |  |  | 35172.995
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 13226.6513 | -194.2581 | 0 | 0 | 0 | -139.1 | 0 | -7.65 | 0 | 0 |  |  |  | 12885.6432
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 28557.6695 | 213.0015 | 55.5783 | 133.7362 | 34.245 | 67.679 | 85.715 | 58.7666 | 262.7561 | 317.9813 |  |  |  | 29787.1285
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 82.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 82.6073
2.1.7 | -Adm. Cost Messing | 310.2328 | 0 | 0 | 0 | 0 | 0 | 5.04 | 0 | 0 | 0 |  |  |  | 315.2727
2.1.8 | -DSC | 35791.7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 35791.7579
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 5166.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5166.9871
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 7136.7761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7136.7761
2.2.2 | -Reinforcement | 13000.6825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13000.6825
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 468.598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 468.598
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 11471.5706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11471.5706
2.2.14 | -Deposit | 2878.7931 | 0 | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2858.7931
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 552.478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 552.478
2.3.2 | -Plant, Equipments & Tools (external hire) | 30452.3022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 30452.3022
2.3.3 | -Diesel & Lubricant | 3205.142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3205.142
2.3.4 | -Repairing | 90.6699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 90.6699
2.3.5 | -Resale | -139.3974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -139.3974
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 123.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 123.7793
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 881646.7549 | 0 | 151.196 | 0 | 211.3141 | 0 | 0 | 0 | 0 | 0 |  |  |  | 882009.265
2.4.2 | -Variation | 292578.1171 | 0 | 195.0086 | 0 | 92 | 0 | 0 | 0 | 0 | 0 |  |  |  | 292865.1258
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 18557.6108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18557.6108
2.4.5 | -Down Payment | 7394.7178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7394.7178
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 175716.9067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 175716.9067
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 1726278.8564 | -12.8166 | 447.5729 | 113.7362 | 375.159 | -21.851 | 122.025 | 56.3021 | 293.7561 | 350.1113 | 0 | 0 | 0 | 1728002.8515
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 8040.6336 | 12.8166 | -447.5729 | -113.7362 | -375.159 | 21.851 | -122.025 | -56.3021 | -293.7561 | -350.1113 |  |  |  | 6316.6385
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -82.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -82.6073
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -123.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -123.7793
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -74.8589 | 94.349 | 117.3044 | 123.3884 | 126.6977 | 127.1345 | 155.2441 | 177.1929 | 186.8469 | 200.7092 |  |  |  | 1234.0081
4.3 | Total Adjustment | -281.2455 | 94.349 | 117.3044 | 123.3884 | 126.6977 | 127.1345 | 155.2441 | 177.1929 | 186.8469 | 200.7092 | 0 | 0 | 0 | 1027.6215
5 | Gross Profit (Item 3.0-4.3) | 8321.8791 | -81.5324 | -564.8773 | -237.1246 | -501.8567 | -105.2835 | -277.2691 | -233.495 | -480.603 | -550.8205 |  |  |  | 5289.017
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 45995.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 45995.4057
6.1.2 | BU Overhead (1.1000% of Total Income excl. PC & Provisional Sum) | 16864.9821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16864.9821
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -54538.5087 | -81.5324 | -564.8773 | -237.1246 | -501.8567 | -105.2835 | -277.2691 | -233.495 | -480.603 | -550.8205 |  |  |  | -57571.3708
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
Chun Wo Construction & Engineering Company Limited
Print Date: 2026-01-09
Project Code: | 985
Project Name: | Hong Kong Disneyland - Arendelle Completion Package
Report Date: | 2025-12-31
Start Date: | 2019-06-15 |  |  |  |  | Monthly Financial Report
Complete Date: | 2021-05-18 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2023-09-30 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 1011828.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1011828.14
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 3870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3870
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 201138.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 201138.68
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 517550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 517550
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | -0.24714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -0.24714
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 1734386.5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1734386.5729
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 162672.694 | -39.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 162633.254
2.1.13 | -Manpower (HO-Consultant) | 154.72 | 10.42 | 45.79 | 0 | 37.6 | 49.57 | 31.2717 | 9.6855 | 31 | 32.13 |  |  |  | 402.1872
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.3 | -Manpower (Labour) | 35179.8451 | -2.54 | 0 | 0 | 0 | 0 | 0 | -4.5 | 0 | 0 |  |  |  | 35172.8051
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 13226.6513 | -194.2581 | 0 | 0 | 0 | -139.1 | 0 | -7.65 | 0 | 0 |  |  |  | 12885.6432
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 27929.7565 | 255.8015 | 55.5783 | 133.7362 | 35.1204 | 67.679 | 85.715 | 45.8166 | 263.6316 | 317.9813 |  |  |  | 29190.8164
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 82.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 82.6073
2.1.7 | -Adm. Cost Messing | 310.2328 | 0 | 0 | 0 | 0 | 0 | 0 | 5.04 | 0 | 0 |  |  |  | 315.2727
2.1.8 | -DSC | 35791.7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 35791.7579
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 5156.4721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5156.4721
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 7086.4842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7086.4842
2.2.2 | -Reinforcement | 13000.6825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13000.6825
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 468.598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 468.598
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 10388.7965 | 0 | 0 | 0 | 3.105 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10391.9015
2.2.14 | -Deposit | 3825.2893 | 0 | 0 | -20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3805.2893
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 712.478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 712.478
2.3.2 | -Plant, Equipments & Tools (external hire) | 30221.3097 | 0 | 0 | 206.94 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 30428.2497
2.3.3 | -Diesel & Lubricant | 3205.142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3205.142
2.3.4 | -Repairing | 90.6699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 90.6699
2.3.5 | -Resale | -139.3974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -139.3974
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 123.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 123.7793
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 857501.7556 | 200 | 305.8886 | 308.7736 | 242.5057 | 0 | 3221.403 | 3157.5132 | 362.2789 | 1521.6109 |  |  |  | 866821.7295
2.4.2 | -Variation | 278737.356 | -401.1168 | 1894.6611 | 383.989 | 340.9407 | 0 | 3494.7292 | 1963.1653 | 600 | 988.0673 |  |  |  | 288001.7918
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 18899.396 | 82.24 | -67.0905 | 176.11 | -17.0051 | 0 | -96.0989 | -55.8636 | -0.92379 | -19.6781 |  |  |  | 18901.086
2.4.5 | -Down Payment | 51649.6864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 51649.6864
2.4.6 | -Retention | -37816.7087 | 360.3372 | 3180.1196 | 153.3113 | 28.5739 | 0 | -117.8669 | -0.72351 | 883.7695 | 300 |  |  |  | -33029.1876
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 175456.1272 | 260.7796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 175716.9068
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 1693916.1814 | 532.2234 | 5414.947 | 1342.8601 | 670.8407 | -21.851 | 6619.1532 | 5112.4835 | 2139.7561 | 3140.1113 | 0 | 0 | 0 | 1718866.7057
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 40470.3915 | -532.2234 | -5414.947 | -1342.8601 | -670.8407 | 21.851 | -6619.1532 | -5112.4835 | -2139.7561 | -3140.1113 |  |  |  | 15519.8672
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | -82.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -82.6073
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | -123.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -123.7793
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -74.8589 | 94.349 | 117.3044 | 123.3884 | 126.6977 | 127.1345 | 155.2441 | 177.1929 | 186.8469 | 200.7092 |  |  |  | 1234.0081
4.3 | Total Adjustment | -281.2455 | 94.349 | 117.3044 | 123.3884 | 126.6977 | 127.1345 | 155.2441 | 177.1929 | 186.8469 | 200.7092 | 0 | 0 | 0 | 1027.6215
5 | Gross Profit (Item 3.0-4.3) | 40751.6369 | -626.5724 | -5532.2513 | -1466.2485 | -797.5383 | -105.2835 | -6774.3972 | -5289.6764 | -2326.603 | -3340.8205 |  |  |  | 14492.2457
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 45997.4368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 45997.4368
6.1.2 | BU Overhead (1.1000% of Total Income excl. PC & Provisional Sum) | 16865.7268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16865.7268
6.2 | Acc. Profit/(Loss) ~ B/F |  | -22111.5267 | -22738.0991 | -28270.3504 | -29736.5989 | -30534.1372 | -30639.4207 | -37413.818 | -42703.4944 | -45030.0974
7 | Acc. Net Profit/(Loss) | -22111.5267 | -22738.0991 | -28270.3504 | -29736.5989 | -30534.1372 | -30639.4207 | -37413.818 | -42703.4944 | -45030.0974 | -48370.9179 |  |  |  | -48370.9179
(=Item5.0 - 6.0 + 6.2)