## Financial Status
CW-KL JV
Print Date: 2026-01-16
Project Code: | 997
Project Name: | ND/2019/02 Kwu Tung North New Development Area, Phase 1, Roads and Drains between Kwu Tung North New Development Area and Shek Wu Hui
Report Date: | 2025-12-31
Start Date: | 2020-02-17 |  |  |  |  | Monthly Financial Report
Complete Date: | 2024-12-25 Time Consumed (%): | [13 empty] | Confidential
Target Complete Date: | 2026-05-31 Target Completed (%):
(HK$'000) | [5 empty] | Financial Status
Item | Trade | Budget |  |  |  | Business Plan | Audit Report (WIP) | Adjustment Cost / Variation | Projection | Committed Value / Cost |  |  | Accrual (Before Retention) | Cash Flow
|  | Tender | 1st Working Budget | Adjustment Cost/ variation | Revision as at | [8 empty] | Actual received & paid |  | Balance to
[9 empty] | as at | as at | % of time elapse | Balance | as at | as at | % of time elapse
|  | A | B | C | D=B+C |  | J | k=I-J | I | E | E1=E/D | F=D-E |  | G | G1=G/E | H=E-G
1 | Income
1.1 | Original Contract Works | 436982.6 | 436982.6 | 0 | 436982.6 | 450905 | 450905 | 0.2 | 450905.2 | 450904.637 | 103.2% | -13922.037 | 1078037.5694 | 1063076.8924 | 235.8% | -612172.2554
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 6465.1 | 16046.3 | 0 | 16046.3 | 439449 | 439449 | 48558.3 | 488007.3 | 372644.1987 | 2322% | -356597.8987 | 0 | 0 | 0% | 372644.1987
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 83495 | 83495 | 9248.5 | 92743.5 | 70704.0802 | 0% | -70704.0802 | 0 | 0 | 0% | 70704.0802
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 3887 | 3887 | 57.043 | 3944.043 | 2706.41 | 0% | -2706.41 | 2030.34 | 0 | 0% | 2706.41
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.8 | Price Fluctuation / CPF | 21901.67 | 21901.67 | 0 | 21901.67 | 175327 | 175327 | -494.33 | 174832.67 | 183109 | 836.1% | -161207.33 | 0 | 0 | 0% | 183109
1.9 | MPF Reimbursement | 14386.04 | 14386.04 | 0 | 14386.04 | 0 | 0 | 0 | 0 | 0 | 0% | 14386.04 | 0 | 0 | 0% | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0.4 | 0.4 | 0 | 0.4 | 0 | 0% | 0 | 0 | 0.0225 | 0% | -0.0225
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 22500 | 22500 | 0 | 22500 | 57 | 57 | 0 | 57 | 57 | 0.2533% | 22443 | 57 | 0 | 0% | 57
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 57370 | 57370 | -57370 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5769.9777 | 0% | 5769.9777
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Income | 502235.41 | 511816.61 | 0 | 511816.61 | 1210490.4 | 1210490.4 | -0.287 | 1210490.113 | 1080125.3259 | 211% | -568308.7159 | 1080124.9094 | 1057306.9372 | 97.89% | 22818.3887
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 20862.997 | 22485.964 | 0 | 22485.964 | 99672 | 99672 | -0.496 | 99671.504 | 97673.6223 | 434.4% | -75187.6583 | 97673.4923 | 97673.4923 | 100% | 0.13
2.1.13 | -Manpower (HO-Consultant) | 0 | 0 | 0 | 0 | 449 | 449 | 2090 | 2539 | 2538.6425 | 0% | -2538.6425 | 2538.6425 | 2538.9625 | 100% | -0.32
2.1.2 | -Manpower (RE) | 0 | 0 | 0 | 0 | 1921 | 1921 | -0.5 | 1920.5 | 1728.1621 | 0% | -1728.1621 | 1728.1621 | 1728.1621 | 100% | 0
2.1.3 | -Manpower (Labour) | 16115.684 | 16115.684 | 0 | 16115.684 | 128764 | 30445 | 7473.188 | 37918.188 | 28565.2742 | 177.3% | -12449.5902 | 28565.2778 | 28565.4378 | 100% | -0.16357
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 10565.4 | 10565.4 | 0 | 10565.4 | 19684 | 19684 | -99.548 | 19584.452 | 17383.127 | 164.5% | -6817.727 | 17383.127 | 17383.127 | 100% | 7.276e-12
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 17267.164 | 17517.164 | 0 | 17517.164 | 74088 | 74088 | 7647.578 | 81735.578 | 81334.0338 | 464.3% | -63816.8697 | 79328.1452 | 73707.3301 | 90.62% | 7626.7037
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.7 | -Adm. Cost Messing | 0 | 0 | 0 | 0 | 623 | 623 | -0.306 | 622.694 | 585.9739 | 0% | -585.9739 | 489.9739 | 448.0779 | 76.47% | 137.896
2.1.8 | -DSC | 21333.2479 | 21333.2479 | 0 | 21333.2479 | 37686.8 | 37686.8 | 10309 | 47995.8 | 47995.6756 | 225% | -26662.4277 | 35563.7916 | 31949.1953 | 66.57% | 16046.4803
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.10 | -Plant | 205 | 205 | 0 | 205 | 13509 | 13509 | 2108.94 | 15617.94 | 15572.6164 | 7596% | -15367.6164 | 14022.4986 | 11212.8315 | 72% | 4359.7849
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2 | Materials
2.2.1 | -Concrete | 10189.9665 | 10189.9665 | 0 | 10189.9665 | 14108 | 14108 | 752.478 | 14860.478 | 13307.94 | 130.6% | -3117.9735 | 13091.9525 | 12672.424 | 95.22% | 635.516
2.2.2 | -Reinforcement | 10017 | 10017 | 0 | 10017 | 10257 | 10257 | 2935 | 13192 | 12500.7096 | 124.8% | -2483.7096 | 9398.107 | 8302.6115 | 66.42% | 4198.0981
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 0 | 0 | 0 | 0 | 15538 | 15538 | 7801.55 | 23339.55 | 22559.3033 | 0% | -22559.3033 | 17979.6026 | 17307.2485 | 76.72% | 5252.0548
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.7 | -Sanitary Fitting | 0 | 0 | 0 | 0 | 1680 | 1680 | 3620 | 5300 | 5202.9112 | 0% | -5202.9112 | 1696.2472 | 1310.316 | 25.18% | 3892.5952
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.13 | -Others Material Cost | 0 | 0 | 0 | 0 | 12898 | 12898 | 9000.084 | 21898.084 | 16578.3324 | 0% | -16578.3324 | 12016.1894 | 9029.3112 | 54.46% | 7549.0212
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 7750.0982 | 9297.4302 | 0% | -9297.4302
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 4341.11 | 4341.11 | 0 | 4341.11 | 1592 | 1592 | -0.22 | 1591.78 | 1562.772 | 36% | 2778.338 | 1562.772 | 1562.772 | 100% | 0
2.3.2 | -Plant, Equipments & Tools (external hire) | 737.584 | 737.584 | 0 | 737.584 | 60250 | 60250 | 48969.5 | 109219.5 | 108246.0613 | 14676% | -107508.4773 | 76204.2021 | 54918.5294 | 50.73% | 53327.5319
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 359950.8814 | 367659.0114 | 0 | 367659.0114 | 681906.508 | 681906.508 | 54900 | 736806.508 | 736806.0077 | 200.4% | -369146.9963 | 556538.2062 | 485752.0861 | 65.93% | 251053.9216
2.4.2 | -Variation | 0 | 0 | 0 | 0 | 74804.75 | 74804.75 | 21566 | 96370.75 | 95125.8986 | 0% | -95125.8986 | 59250.9472 | 44414.8559 | 46.69% | 50711.0428
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 139262.6952 | 139090.9969 | 0% | -139090.9969
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 583.239 | 0% | -583.239
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -36380.193 | 0% | 36380.193
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | -147384 | -164924 | -148429.192 | -313353.192 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | -23711.9491 | -11551.2797 | 0% | 11551.2797
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.5 | Manpower (Labour) for Works | 0 | 0 | 0 | 0 | 8421 | 144314 | 3627 | 147941 | 147940.46 | 0% | -147940.46 | 147940.46 | 147940.8126 | 100% | -0.3525
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0.02 | 0.02 | 0 | 0.02 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
| Total Cost | 471586.0348 | 481167.1318 | 0 | 481167.1318 | 1110468.078 | 1130502.078 | 34270.056 | 1164772.134 | 1453207.5236 | 302% | -972040.3918 | 1296272.6413 | 1149457.7765 | 79.1% | 303749.7471
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 30649.3752 | 30649.4782 | 0 | 30649.4782 | 100022.322 | 79988.322 | -34270.343 | 45717.979 | -373082.1977 | -1217% | 403731.6759 | -216147.7319 | -92150.8393 | 24.7% | -280931.3584
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) |  |  |  |  | 0 |  |  | 0 | 0 | 0% |  | 0 | 0 | 0% | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) |  |  |  |  | 0 |  |  | 0 | 0 | 0% |  | 0 | 0 | 0% | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | 0 | 0 | 0 | 0 | -2052 |  |  | -2975.1883 | -2975.1883 | 0% | 2975.1883 | -2975.1883 | -2975.1883 | 100% | -5.9044e-09
4.3 | Total Adjustment | 0 | 0 | 0 | 0 | -2052 |  |  | -2975.1883 | -2975.1883 | 0% | 2975.1883 | -2975.1883 | -2975.1883 | 100% | -5.9044e-09
5 | Gross Profit (Item 3.0-4.3) | 30649.3752 | 30649.4782 | 0 | 30649.4782 | 102074.322 |  |  | 48693.1673 | -370107.0094 | -1208% | 400756.4876 | -213172.5436 | -89175.651 | 24.09% | -280931.3584
6 | Overhead
6.1 | HO Overhead Rate % | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0% | 0
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 30134.1246 | 30708.9966 | 0 | 30708.9966 | 72396.204 |  |  | 36389.3121 | 33913.4075 | 110.4% | -3204.4109 | 33953.9571 | 33300.2331 | 98.19% | 613.1744
6.1.2 | BU Overhead (0.6000% of Total Income excl. PC & Provisional Sum) | 3013.4125 | 3070.8997 | 0 | 3070.8997 | 7239.6204 |  |  | 7239.2764 | 6464.5135 | 210.5% | -3393.6138 | 6468.5674 | 6343.8416 | 98.13% | 120.6719
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -2498.1619 | -3130.4181 | 0 | -3130.4181 | 22438.4976 |  |  | 5064.5788 | -410484.9304 | 13113% | 407354.5123 | -253595.0681 | -128819.7257 | 31.38% | -281665.2047
(=Item5.0 - 6.0 + 6.2)

## Projection
CW-KL JV
Print Date: 2026-01-16
Project Code: | 997
Project Name: | ND/2019/02 Kwu Tung North New Development Area, Phase 1, Roads and Drains between Kwu Tung North New Development Area and Shek Wu Hui
Report Date: | 2025-12-31
Start Date: | 2020-02-17 |  |  |  |  | Monthly Financial Report
Complete Date: | 2024-12-25 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-05-31 Target Completed (%):
(HK$'000) | [5 empty] | Projection
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 450905.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 450905.2
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 501041.3 | -2169 | -4534 | -3511 | 2776 | -1007 | -976 | -3613 | 0 | 0 |  |  |  | 488007.3
1.2.2 | -Fee of C.E. | 95197.5 | -412 | -885 | -667 | 528 | -192 | -176 | -650 | 0 | 0 |  |  |  | 92743.5
1.3 | Provisional Sum | 3944.043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3944.043
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 152913.67 | 2581 | 5419 | 4178 | 3127 | 1199 | 1152 | 4263 | 0 | 0 |  |  |  | 174832.67
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.4
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 57
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 1204059.113 | 0 | 0 | 0 | 6431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210490.113
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 85684.504 | 1289 | 12698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 99671.504
2.1.13 | -Manpower (HO-Consultant) | 294 | 0 | 155 | 0 | 0 | 500 | 300 | 100 | 91 | 1099 |  |  |  | 2539
2.1.2 | -Manpower (RE) | 1412.5 | 0 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1920.5
2.1.3 | -Manpower (Labour) | 108137.188 | 4364 | 12506 | 0 | 2500 | -89589 | 0 | 0 | 0 | 0 |  |  |  | 37918.188
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 15991.452 | 530 | 3163 | 0 | 0 | -100 | 0 | 0 | 0 | 0 |  |  |  | 19584.452
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 67882.578 | 2763 | 13442 | 0 | 0 | -2352 | 0 | 0 | 0 | 0 |  |  |  | 81735.578
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 622.694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 622.694
2.1.8 | -DSC | 39207.8 | 0 | 5428 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 |  |  |  | 47995.8
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 12808.94 | 400 | 300 | 0 | 1150 | 300 | 70 | 200 | 371 | 18 |  |  |  | 15617.94
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 10681.478 | 600 | 2827 | 0 | 0 | 752 | 0 | 0 | 0 | 0 |  |  |  | 14860.478
2.2.2 | -Reinforcement | 8879 | 1210 | 3878 | 0 | 0 | -2775 | 0 | 2000 | 0 | 0 |  |  |  | 13192
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 22499.55 | 10 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 23339.55
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 4752 | 370 | 0 | 58 | 10 | 0 | 0 | 0 | 110 | 0 |  |  |  | 5300
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 13904.084 | 217 | 7777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 21898.084
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1591.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1591.78
2.3.2 | -Plant, Equipments & Tools (external hire) | 70734.5 | 11900 | 12924 | 0 | 2450 | 6703 | 1300 | 1000 | 988 | 1220 |  |  |  | 109219.5
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 685275.508 | 1400 | 0 | 0 | 0 | 0 | 18000 | 0 | 32000 | 131 |  |  |  | 736806.508
2.4.2 | -Variation | 68904.75 | 5061 | 1500 | 2655 | 1250 | 9000 | 2000 | 2000 | 4000 | 0 |  |  |  | 96370.75
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | -122028.192 | -29413 | -79782 | 4120 | 0 | 33034 | -27670 | -11300 | -70859 | -9455 |  |  |  | -313353.192
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 6801 | 550 | 595 | 475 | 600 | 115820 | 6000 | 6000 | 7473 | 3627 |  |  |  | 147941
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.02
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 1104037.134 | 1251 | -1251 | 7308 | 7960 | 71293 | 0 | 0 | -25826 | 0 | 0 | 0 | 0 | 1164772.134
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 100021.979 | -1251 | 1251 | -7308 | -1529 | -71293 | 0 | 0 | 25826 | 0 |  |  |  | 45717.979
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -5431.2522 | 56.0527 | 116.4859 | 146.768 | 198.1259 | 244.6499 | 303.2527 | 402.5844 | 453.6227 | 534.5217 |  |  |  | -2975.1883
4.3 | Total Adjustment | -5431.2522 | 56.0527 | 116.4859 | 146.768 | 198.1259 | 244.6499 | 303.2527 | 402.5844 | 453.6227 | 534.5217 | 0 | 0 | 0 | -2975.1883
5 | Gross Profit (Item 3.0-4.3) | 105453.2312 | -1307.0527 | 1134.5141 | -7454.768 | -1727.1259 | -71537.6499 | -303.2527 | -402.5844 | 25372.3773 | -534.5217 |  |  |  | 48693.1673
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 36003.4521 | 0 | 0 | 0 | 385.86 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36389.3121
6.1.2 | BU Overhead (0.6000% of Total Income excl. PC & Provisional Sum) | 7200.6904 | 0 | 0 | 0 | 38.586 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7239.2764
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | 62249.0887 | -1307.0527 | 1134.5141 | -7454.768 | -2151.5719 | -71537.6499 | -303.2527 | -402.5844 | 25372.3773 | -534.5217 |  |  |  | 5064.5788
(=Item5.0 - 6.0 + 6.2)

## Committed Cost
CW-KL JV
Print Date: 2026-01-16
Project Code: | 997
Project Name: | ND/2019/02 Kwu Tung North New Development Area, Phase 1, Roads and Drains between Kwu Tung North New Development Area and Shek Wu Hui
Report Date: | 2025-12-31
Start Date: | 2020-02-17 |  |  |  |  | Monthly Financial Report
Complete Date: | 2024-12-25 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-05-31 Target Completed (%):
(HK$'000) | [5 empty] | Committed Cost
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 450904.637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 450904.637
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 320650.1987 | 6463 | 6074 | 9954 | 3269 | 3831 | 0 | 6347 | 5892 | 10164 |  |  |  | 372644.1987
1.2.2 | -Fee of C.E. | 60923.0802 | 1228 | 1155 | 1891 | 621 | 688 | 0 | 1142 | 1125 | 1931 |  |  |  | 70704.0802
1.3 | Provisional Sum | 2030.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676 | 0 |  |  |  | 2706.41
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 152913 | 2581 | 5419 | 4178 | 3127 | 1200 | 828 | 4587 | 3322 | 4954 |  |  |  | 183109
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 57
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 987478.3259 | 10272 | 12648 | 16023 | 7017 | 5719 | 828 | 12076 | 11015 | 17049 | 0 | 0 | 0 | 1080125.3259
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 85440.0807 | 1532.99 | 1943.64 | 1491.28 | 1207.6 | 1315.36 | 1311.06 | 1234.6007 | 1065.6485 | 1131.3624 |  |  |  | 97673.6223
2.1.13 | -Manpower (HO-Consultant) | 292.99 | -28.94 | 49.06 | 58.86 | 69.4 | 474.7994 | 315.2212 | 92.5101 | 101.5516 | 1113.1901 |  |  |  | 2538.6425
2.1.2 | -Manpower (RE) | 1380.7975 | -54.58 | 12.98 | 26.67 | 14.3 | 69.05 | 80.74 | 53.499 | 72.2555 | 72.45 |  |  |  | 1728.1621
2.1.3 | -Manpower (Labour) | 108135.704 | 4137.02 | 511.5935 | 436.8661 | 1030.0734 | -82672.6552 | -3987.4524 | 388.0125 | 246.7586 | 339.3536 |  |  |  | 28565.2742
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 15986.7028 | 200.1065 | 1283.4614 | 121.338 | 58.697 | 83.2982 | -539.617 | 47.72 | 71.789 | 69.631 |  |  |  | 17383.127
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 67906.9448 | 2530.7844 | 946.5871 | 2481.582 | 424.0017 | 1067.602 | 1172.3247 | 1591.2665 | 1063.8962 | 2149.0442 |  |  |  | 81334.0338
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 538.7129 | 1.024 | 6.877 | 5.823 | 14.339 | 8.525 | 0.192 | 6.214 | 4.267 | 0 |  |  |  | 585.9739
2.1.8 | -DSC | 39207.0852 | 4478 | 950.5904 | 0 | 0 | 0 | 0 | 0 | 2 | 3358 |  |  |  | 47995.6756
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 12764.949 | 236.2048 | 240.6684 | 182.7507 | 828.9566 | 414.3852 | 297.0806 | 191.2416 | 128.7105 | 287.669 |  |  |  | 15572.6164
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 10681.3425 | 387.3805 | 389.026 | 475.2265 | 0 | 361.024 | 295.7485 | 178.459 | 227.097 | 312.636 |  |  |  | 13307.94
2.2.2 | -Reinforcement | 8926.8366 | 1352.1888 | 0 | 0 | 11.7442 | 0.14 | 0 | 0 | 2199.64 | 10.16 |  |  |  | 12500.7096
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 22463.9277 | 44.02 | 11.9996 | 0 | 39.356 | 0 | 0 | 0 | 0 | 0 |  |  |  | 22559.3033
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 4746.6072 | 0 | 368.25 | 0 | 22.104 | 52.75 | 0 | 0 | 0 | 13.2 |  |  |  | 5202.9112
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 13902.5341 | 127.7812 | 116.02 | 740.8251 | 1309.635 | -45.0647 | 59.531 | 91.096 | 222.5747 | 53.4 |  |  |  | 16578.3324
2.2.14 | -Deposit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1562.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1562.772
2.3.2 | -Plant, Equipments & Tools (external hire) | 70829.5119 | 9063.0604 | 14281.2627 | 1141.8657 | 1649.8137 | 1190.97 | 7048.807 | 1076.16 | 902.66 | 1061.95 |  |  |  | 108246.0613
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 685818.8708 | 0 | 0 | 366 | 0 | 0 | 16350.79 | 0 | 0 | 34270.347 |  |  |  | 736806.0077
2.4.2 | -Variation | 94610.8986 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95125.8986
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 6799.779 | 8137.6287 | 5527.9478 | 4887.9738 | 5141.2916 | 88516.5463 | 9999.7903 | 5739.7355 | 5962.5206 | 7227.2464 |  |  |  | 147940.46
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 1251997.0472 | 32659.6692 | 26639.9639 | 12417.0611 | 11821.3122 | 10836.7303 | 32404.2159 | 10690.5149 | 12271.3692 | 51469.6397 | 0 | 0 | 0 | 1453207.5236
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -264518.7213 | -22387.6692 | -13991.9639 | 3605.9389 | -4804.3122 | -5117.7303 | -31576.2159 | 1385.4851 | -1256.3692 | -34420.6397 |  |  |  | -373082.1977
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -5431.2522 | 56.0527 | 116.4859 | 146.768 | 198.1259 | 244.6499 | 303.2527 | 402.5844 | 453.6227 | 534.5217 |  |  |  | -2975.1883
4.3 | Total Adjustment | -5431.2522 | 56.0527 | 116.4859 | 146.768 | 198.1259 | 244.6499 | 303.2527 | 402.5844 | 453.6227 | 534.5217 | 0 | 0 | 0 | -2975.1883
5 | Gross Profit (Item 3.0-4.3) | -259087.4691 | -22443.722 | -14108.4498 | 3459.1709 | -5002.4381 | -5362.3801 | -31879.4686 | 982.9007 | -1709.9919 | -34955.1614 |  |  |  | -370107.0094
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 29563.4375 | 308.16 | 379.44 | 480.69 | 421.02 | 343.14 | 49.68 | 724.56 | 620.34 | 1022.94 |  |  |  | 33913.4075
6.1.2 | BU Overhead (0.6000% of Total Income excl. PC & Provisional Sum) | 5912.6875 | 61.632 | 75.888 | 96.138 | 42.102 | 34.314 | 4.968 | 72.456 | 62.034 | 102.294 |  |  |  | 6464.5135
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -294563.5941 | -22813.514 | -14563.7778 | 2882.3429 | -5465.5601 | -5739.8341 | -31934.1166 | 185.8847 | -2392.3659 | -36080.3954 |  |  |  | -410484.9304
(=Item5.0 - 6.0 + 6.2)

## Accrual
CW-KL JV
Print Date: 2026-01-16
Project Code: | 997
Project Name: | ND/2019/02 Kwu Tung North New Development Area, Phase 1, Roads and Drains between Kwu Tung North New Development Area and Shek Wu Hui
Report Date: | 2025-12-31
Start Date: | 2020-02-17 |  |  |  |  | Monthly Financial Report
Complete Date: | 2024-12-25 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-05-31 Target Completed (%):
(HK$'000) | [5 empty] | Accrual
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 985390.5694 | 10272 | 12648 | 16023 | 7017 | 5719 | 828 | 12076 | 11015 | 17049 |  |  |  | 1078037.5694
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 2030.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2030.34
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 57
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 987477.9094 | 10272 | 12648 | 16023 | 7017 | 5719 | 828 | 12076 | 11015 | 17049 | 0 | 0 | 0 | 1080124.9094
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 85439.9507 | 1532.99 | 1943.64 | 1491.28 | 1207.6 | 1315.36 | 1311.06 | 1234.6007 | 1065.6485 | 1131.3624 |  |  |  | 97673.4923
2.1.13 | -Manpower (HO-Consultant) | 292.99 | -28.94 | 49.06 | 58.86 | 69.4 | 474.7994 | 315.2212 | 92.5101 | 101.5516 | 1113.1901 |  |  |  | 2538.6425
2.1.2 | -Manpower (RE) | 1380.7975 | -54.58 | 12.98 | 26.67 | 14.3 | 69.05 | 80.74 | 53.499 | 72.2555 | 72.45 |  |  |  | 1728.1621
2.1.3 | -Manpower (Labour) | 108135.704 | 4137.0236 | 511.5935 | 436.8661 | 1030.0734 | -82672.6552 | -3987.4524 | 388.0125 | 246.7586 | 339.3536 |  |  |  | 28565.2778
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 15986.7028 | 200.1065 | 1283.4614 | 121.338 | 58.697 | 83.2982 | -539.617 | 47.72 | 71.789 | 69.631 |  |  |  | 17383.127
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 65992.2397 | 2867.8668 | 1319.2255 | 1714.3041 | 1208.5251 | 890.2745 | 449.582 | 3151.2467 | 1237.1498 | 497.7309 |  |  |  | 79328.1452
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 442.7129 | 1.024 | 6.877 | 5.823 | 14.339 | 8.525 | 0.192 | 6.214 | 4.267 | 0 |  |  |  | 489.9739
2.1.8 | -DSC | 29281.9193 | 1476.386 | 1372.7404 | 105.6982 | 1253 | 193.425 | 0 | 1879.1227 | 1.5 | 0 |  |  |  | 35563.7916
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 11199.8715 | 771.9981 | 87.982 | 888.9152 | 153.0234 | 289.7692 | 112.1556 | 296.0036 | 137.893 | 84.887 |  |  |  | 14022.4986
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 10469.815 | 1134.824 | 117.655 | 115.4615 | 327.1165 | 214.3385 | 0 | 539.926 | 172.816 | 0 |  |  |  | 13091.9525
2.2.2 | -Reinforcement | 7247.911 | 557.3828 | 33.5444 | 350.7946 | 52.4958 | 211.6767 | 0 | 537.7134 | 406.5883 | 0 |  |  |  | 9398.107
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 13109.874 | 430.3492 | 0 | 11.9996 | 240.3398 | 4187.04 | 0 | 0 | 0 | 0 |  |  |  | 17979.6026
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 1228.7227 | 74.3745 | 0 | 8 | 8 | 254.4 | 0 | 122.75 | 0 | 0 |  |  |  | 1696.2472
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 7020.2352 | 2742.6357 | 513.4281 | 83.6951 | 81.8366 | 261.7005 | 0 | 1064.6766 | 247.9816 | 0 |  |  |  | 12016.1894
2.2.14 | -Deposit | 15087.6501 | 1316.8935 | 180 | -158.1155 | -325.3487 | -8826.5376 | 0 | 0 | -671.2654 | 1146.8218 |  |  |  | 7750.0982
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1562.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1562.772
2.3.2 | -Plant, Equipments & Tools (external hire) | 49254.6294 | 12758.8888 | 2207.0817 | 2955.4432 | 2144.314 | 1440.8033 | 0 | 4060.1025 | 1382.939 | 0 |  |  |  | 76204.2021
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 499487.5287 | 18661.5642 | 256.3134 | 5062.3572 | 3938.11 | 6040.5661 | 0 | 17148.9795 | 5942.7871 | 0 |  |  |  | 556538.2062
2.4.2 | -Variation | 36157.6142 | 11228.0409 | 607.4336 | 5043.6876 | 215.6 | 1518.1752 | 0 | 3225.2558 | 1255.14 | 0 |  |  |  | 59250.9472
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 125515.7461 | 3920.6548 | 1143.3817 | 1555.6685 | 227.382 | 5699.3403 | 116.885 | 50.2206 | 1033.4163 | 0 |  |  |  | 139262.6952
2.4.5 | -Down Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.6 | -Retention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | -21693.8148 | -1407.1728 | 0 | 0 | -269.61 | 0 | 0 | -341.3514 | 0 | 0 |  |  |  | -23711.9491
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 6799.779 | 8137.6287 | 5527.9478 | 4887.9738 | 5141.2916 | 88516.5463 | 9999.7903 | 5739.7355 | 5962.5206 | 7227.2464 |  |  |  | 147940.46
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 1069401.3509 | 70459.9394 | 17174.3455 | 24766.7202 | 16790.4855 | 20169.8955 | 7858.5567 | 39296.9378 | 18671.7366 | 11682.6732 | 0 | 0 | 0 | 1296272.6413
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | -81923.4415 | -60187.9394 | -4526.3455 | -8743.7203 | -9773.4855 | -14450.8955 | -7030.5567 | -27220.9378 | -7656.7366 | 5366.3268 |  |  |  | -216147.7319
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -5431.2522 | 56.0527 | 116.4859 | 146.768 | 198.1259 | 244.6499 | 303.2527 | 402.5844 | 453.6227 | 534.5217 |  |  |  | -2975.1883
4.3 | Total Adjustment | -5431.2522 | 56.0527 | 116.4859 | 146.768 | 198.1259 | 244.6499 | 303.2527 | 402.5844 | 453.6227 | 534.5217 | 0 | 0 | 0 | -2975.1883
5 | Gross Profit (Item 3.0-4.3) | -76492.1893 | -60243.9921 | -4642.8314 | -8890.4883 | -9971.6114 | -14695.5454 | -7333.8094 | -27623.5221 | -8110.3592 | 4831.8051 |  |  |  | -213172.5436
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 29563.4271 | 308.16 | 379.44 | 480.69 | 421.02 | 343.14 | 49.68 | 724.56 | 660.9 | 1022.94 |  |  |  | 33953.9571
6.1.2 | BU Overhead (0.6000% of Total Income excl. PC & Provisional Sum) | 5912.6854 | 61.632 | 75.888 | 96.138 | 42.102 | 34.314 | 4.968 | 72.456 | 66.09 | 102.294 |  |  |  | 6468.5674
6.2 | Acc. Profit/(Loss) ~ B/F
7 | Acc. Net Profit/(Loss) | -111968.3018 | -60613.7841 | -5098.1594 | -9467.3163 | -10434.7334 | -15072.9994 | -7388.4574 | -28420.5381 | -8837.3492 | 3706.5711 |  |  |  | -253595.0681
(=Item5.0 - 6.0 + 6.2)

## Cash Flow
CW-KL JV
Print Date: 2026-01-16
Project Code: | 997
Project Name: | ND/2019/02 Kwu Tung North New Development Area, Phase 1, Roads and Drains between Kwu Tung North New Development Area and Shek Wu Hui
Report Date: | 2025-12-31
Start Date: | 2020-02-17 |  |  |  |  | Monthly Financial Report
Complete Date: | 2024-12-25 Time Consumed (%): | [12 empty] | Confidential
Target Complete Date: | 2026-05-31 Target Completed (%):
(HK$'000) | [5 empty] | Cash Flow
Item | Trade | Bal B/F | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
1 | Income
1.1 | Original Contract Works | 967611.8566 | 19844.09 | 10272 | 12648.1139 | 16023.4769 | 7017.53 | 5741 | 827.74 | 12076.0729 | 11015.012 |  |  |  | 1063076.8924
1.2 | V.O. / Compensation Events
1.2.1 | -V.O. / C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.2.2 | -Fee of C.E. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.3 | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.4 | Adjustment for Provisional Quantities (remeasurement) and PC Rates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.5 | NSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.6 | Profit & Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.7 | Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.8 | Price Fluctuation / CPF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.9 | MPF Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.10 | SA | 0.0225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0.0225
1.11 | CSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12 | Other Revenue / Pain Gain Sharing
1.12.1 | -Other Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.2 | -Pain Gain Sharing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.12.3 | -Stretch Target Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.13 | Less :LD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.14 | Less :Retention Money | -5769.9777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | -5769.9777
1.15 | Less :Retention Money (NSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.16 | Partialing Income Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
1.17 | Advance Payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Income | 961841.9015 | 19844.09 | 10272 | 12648.1139 | 16023.4769 | 7017.53 | 5741 | 827.74 | 12076.0729 | 11015.012 | 0 | 0 | 0 | 1057306.9372
2 | Less : Cost
2.1 | Preliminaries
2.1.1 | -Manpower (Mgt. & Supervision) | 85439.9507 | 1532.99 | 1943.64 | 1491.28 | 1207.6 | 1315.36 | 1311.06 | 1234.6007 | 1065.6485 | 1131.3624 |  |  |  | 97673.4923
2.1.13 | -Manpower (HO-Consultant) | 293.31 | -28.94 | 49.06 | 58.86 | 69.4 | 474.7994 | 315.2212 | 92.5101 | 101.5516 | 1113.1901 |  |  |  | 2538.9625
2.1.2 | -Manpower (RE) | 1380.7975 | -54.58 | 12.98 | 26.67 | 14.3 | 69.05 | 80.74 | 53.499 | 72.2555 | 72.45 |  |  |  | 1728.1621
2.1.3 | -Manpower (Labour) | 108135.864 | 4137.0236 | 511.5935 | 436.8661 | 1030.0734 | -82672.6552 | -3987.4524 | 388.0125 | 246.7586 | 339.3536 |  |  |  | 28565.4378
2.1.4 | -Adm. Cost one off item (Insurance, Bond & Levies) | 13786.8774 | 199.1535 | 1283.4614 | 433.9685 | 458.697 | 483.2982 | -539.617 | 447.72 | 759.9369 | 69.631 |  |  |  | 17383.127
2.1.5 | -Adm. Cost Others (General site overhead, includes RE) | 61928.5185 | -254.2405 | 1361.5763 | 2394.9791 | 2046.3307 | 839.7761 | 1559.9567 | 1162.1662 | 1170.1174 | 1498.1496 |  |  |  | 73707.3301
2.1.6 | -Adm. Cost Financial Cost (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.7 | -Adm. Cost Messing | 400.8169 | 1.024 | 6.877 | 5.823 | 7.966 | 9.683 | 0.192 | 5.629 | 10.067 | 0 |  |  |  | 448.0779
2.1.8 | -DSC | 27761.0881 | 40 | 940.8915 | 649.43 | 352.935 | 0 | 623.7 | 337.5899 | 304.8092 | 938.7516 |  |  |  | 31949.1953
2.1.9 | -General Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.10 | -Plant | 8796.3421 | 581.2954 | 88.463 | 273.5223 | 65.8954 | 273.542 | 205.2506 | 732.3916 | 11.402 | 184.727 |  |  |  | 11212.8315
2.1.11 | -JV Partner Management Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.1.12 | -Potential Savings (Preliminaries) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2 | Materials
2.2.1 | -Concrete | 10156.844 | 232.384 | 183.3565 | 376.7655 | 312.6815 | 463.7625 | 333.938 | 108.64 | 388.8355 | 115.2165 |  |  |  | 12672.424
2.2.2 | -Reinforcement | 4574.4225 | 283.6 | 1775.2533 | 244.4495 | 48.3936 | 58.0975 | 458.907 | 264.0325 | 54.4813 | 540.9742 |  |  |  | 8302.6115
2.2.3 | -Tile, Granite & Marble | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.4 | -Temporary Work (Structural Steel and Sheet Piles) | 11731.6372 | 0 | 765.8467 | 40.9 | 49.58 | 4187.04 | 397.3234 | 0 | 83.5655 | 51.3556 |  |  |  | 17307.2485
2.2.5 | -Structural Steel Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.6 | -Furniture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.7 | -Sanitary Fitting | 934.543 | 0 | 0 | 0 | 0 | 237.6485 | 37.3335 | 0 | 0 | 100.791 |  |  |  | 1310.316
2.2.8 | -Ironmongery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.9 | -MVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.10 | -Electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.11 | -P&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.12 | -FS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.13 | -Others Material Cost | 4258.0376 | 443.4221 | 191.2093 | 285.9 | 8.25 | 524.075 | 314.7982 | 74.8136 | 2315.3055 | 613.4999 |  |  |  | 9029.3112
2.2.14 | -Deposit | 16634.9821 | 1316.8935 | 180 | -158.1155 | -325.3487 | -8826.5376 | 0 | 0 | -671.2654 | 1146.8218 |  |  |  | 9297.4302
2.2.15 | -Potential Savings (Materials) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.16 | -Concrete (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.17 | -Reinforcement (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.2.18 | -P&D Material (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.1 | -Plant, Equipments & Tools (purchased) | 1524.772 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 |  |  |  | 1562.772
2.3.2 | -Plant, Equipments & Tools (external hire) | 30494.0989 | 1159.126 | 2759.458 | 1248.952 | 5617.4321 | 1818.6073 | 1558.4737 | 5488.4011 | 2385.1743 | 2388.8059 |  |  |  | 54918.5294
2.3.3 | -Diesel & Lubricant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.4 | -Repairing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.5 | -Resale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.6 | -Others Plant & Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.7 | -Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.8 | -Potential Savings (Plants) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3.9 | - Plant, Equipments & Tools (internal hire) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4 | Subcontractor
2.4.1 | -Contract Works | 429346.4591 | 7532.5342 | 5101.5187 | 3405.0872 | 8217.3387 | 2442.5047 | 5102.1776 | 5246.7 | 8129.2783 | 11228.4877 |  |  |  | 485752.0861
2.4.2 | -Variation | 30448.8968 | 22.7872 | 507.3333 | 2099.0381 | 3868.4303 | 1552.8148 | 960.5586 | 2327.0758 | 670.1147 | 1957.8064 |  |  |  | 44414.8559
2.4.3 | -Claim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.4 | -Contra Charge | 124684.9082 | 3436.0979 | 1511.956 | 1586.6811 | 948.416 | 5957.4007 | 635.6519 | 335.193 | 704.1746 | -709.4826 |  |  |  | 139090.9969
2.4.5 | -Down Payment | 583.239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 583.239
2.4.6 | -Retention | -33677.2469 | -105.5321 | -352.2919 | -445.039 | -587.4292 | -202.8184 | -223.8936 | 270.7548 | -639.0676 | -417.629 |  |  |  | -36380.193
2.4.7 | -Potential Savings (DSC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.4.8 | -Commercial Settlement | -9802.7555 | 0 | 0 | 0 | -1407.1728 | 0 | 0 | 0 | 0 | -341.3514 |  |  |  | -11551.2797
2.4.9 | -Contract Works (for Tunnel) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.5 | Manpower (Labour) for Works | 6800.129 | 8137.6287 | 5527.9478 | 4887.9738 | 5141.2916 | 88516.5463 | 9999.7903 | 5739.738 | 5962.5206 | 7227.2464 |  |  |  | 147940.8126
2.6 | Nominated Package
2.6.1 | -Nominated Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.6.2 | -Nominated Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.7 | Allow for Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.8 | Allow for Defects Rectification Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.9 | Tender Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.10 | Partialing Cost Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11 | Incentive / POR Bonus
2.11.1 | -Cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.2 | -Non-cost saving related bonus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.11.3 | -Cost saving achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.12 | CPR Penalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.13 | HO - Transformation Performance Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.14 | Stretch Target (Cost) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Total Cost | 936616.5323 | 28612.6674 | 24350.1306 | 19343.9917 | 27145.0606 | 17521.9949 | 19182.1096 | 24309.4677 | 23125.6639 | 29250.1577 | 0 | 0 | 0 | 1149457.7765
3 | Gross Profit (Item 1.0-2.0) (Financial A/C) | 25225.3692 | -8768.5774 | -14078.1306 | -6695.8778 | -11121.5837 | -10504.4649 | -13441.1096 | -23481.7277 | -11049.591 | -18235.1456 |  |  |  | -92150.8393
4 | Reconciliation
Less: Cost
2.1 | Preliminaries
2.1.6 | -Adm Reconciliation (TR interest & Bank charge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2.3 | Plant & Machinery
2.3.7 | Depreciation (in Ledger) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
4.1 | Less/(Add) : Internal Interest (5% for +) & (5% for -) | -5431.2522 | 56.0527 | 116.4859 | 146.768 | 198.1259 | 244.6499 | 303.2527 | 402.5844 | 453.6227 | 534.5217 |  |  |  | -2975.1883
4.3 | Total Adjustment | -5431.2522 | 56.0527 | 116.4859 | 146.768 | 198.1259 | 244.6499 | 303.2527 | 402.5844 | 453.6227 | 534.5217 | 0 | 0 | 0 | -2975.1883
5 | Gross Profit (Item 3.0-4.3) | 30656.6214 | -8824.6301 | -14194.6166 | -6842.6458 | -11319.7097 | -10749.1148 | -13744.3623 | -23884.3121 | -11503.2137 | -18769.6673 |  |  |  | -89175.651
6 | Overhead
6.1 | HO Overhead Rate % | 0.03 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06
6.1.1 | HO Overhead (6.0000% of Total Income excl. PC & Provisional Sum) | 28855.257 | 595.3227 | 308.16 | 379.4434 | 961.4086 | 421.0518 | 344.46 | 49.6644 | 724.5644 | 660.9007 |  |  |  | 33300.2331
6.1.2 | BU Overhead (0.6000% of Total Income excl. PC & Provisional Sum) | 5771.0514 | 119.0645 | 61.632 | 75.8887 | 96.1409 | 42.1052 | 34.446 | 4.9664 | 72.4564 | 66.0901 |  |  |  | 6343.8416
6.2 | Acc. Profit/(Loss) ~ B/F |  | -3969.6871 | -13508.7044 | -28073.113 | -35371.0909 | -47748.35 | -58960.6218 | -73083.8901 | -97022.833 | -109323.0675
7 | Acc. Net Profit/(Loss) | -3969.6871 | -13508.7044 | -28073.113 | -35371.0909 | -47748.35 | -58960.6218 | -73083.8901 | -97022.833 | -109323.0675 | -128819.7257 |  |  |  | -128819.7257
(=Item5.0 - 6.0 + 6.2)